## Metrics
GridPP Quarterly Report | [11 empty] | OK
Area | Tier-1 | [10 empty] | Close to target
Quarter | Q215 | [10 empty] | Not OK
Reported by | Andrew Sansum | [10 empty] | Not yet able to be measured
Suspended
GridPP no. | Tier-1 no. | Description | Source | Owner | Target | Q211 | Q311 | Q411 | Q1 12 | Q2 12 | Q3 12 | Q4 12 | Q113 | Q213 | Q313 | Q413 | Q114 | Q214 | Q314 | Q414 | Q115 | Q215 | Comment
A1.1 |  | Fraction of WLCG MoU commitment for CPU 100 % |  | Catalin Condurache | 100% | 110% | 113.6% | 100% | 100% | 113% | 119% | 126% | 124% | 103% | 102.5% | 105% | 105% | 109.7% | 105% | 105% | 105% | 115.3%
A1.2 |  | % met of GRIDPP T1-RB allocation for CPU 100 % |  | Catalin Condurache | 100% | 105.8% | 104.9% | 109.3% | 114.1% | 121.7% | 125.7% | 120.5% | 129% | 112% | 101% | 114% | 113% | 131% | 132% | 129.3% | 115.3% | 107.3%
A1.3 |  | Availability of LFC service 99% |  | Catalin Condurache | 99% | 99.97% | 99.61% | 99.8% | 99.56% | 97.36% | 100% | 98.28% | 99.5% | 99.53% | 99.97% | 99.43% | 99.96% | 99.53% | 99.97% | 99.59% | 100% | 99.72%
A1.4 |  | SAM availability of FTS service 99 % |  | Catalin Condurache | 99% | 99.94% | 99.61% | 99.75% | 98.88% | 99.26% | 99.83% | 97.5% | 99.55% | 99.6% | 100% | 99.03% | 99.8% | 97.53% | 99.98% | 100% |  |  | No measurement for FTS3.
A1.5 |  | SAM availability of MyProxy service 99 % |  | Catalin Condurache | 99% | 100% | 99.97% | 99.51% | 99.63% | 99.8% | 99.99% | 99.99% | 99.7% | 99.7% | 100% | 100% | 99.92% | 99% | 99.97% | 99.67% | 100% | 99.57%
A1.6 |  | SAM availability of toplevel BDII service 99 % |  | Catalin Condurache | 99% | 100% | 99.68% | 99.97% | 99.5% | 99.7% | 100% | 98.58% | 99.7% | 99.64% | 99.74% | 99.93% | 100% | 99.53% | 100% | 99.79% | 99.98% | 99.86%
A1.7 |  | Availability of WMS service 99 % |  | Derek Ross | 99% | 100% | 100% | 99.62% | 98.66% | 94.23% | 100% | 91.06% | 99.57% | 99.6% | 99.99% | 94.96% | 99.71% | 99.26% | 99.99% | 99.44% | 100% | 99.87%
A1.8 |  | Availability of LHCB VO box 98 % |  | Matt Hodges | 98% | 100% | 99.69% | 99.85% | 99.77% | 99.82% | 100% | 98.65% | 99.71% | 99.73% | 99.99% | 98.88% | 100% | 99.01% | 99.99% | 99.81% | 100% | 99.89%
A1.9 |  | Availability of ALICE VO box 98 % |  | Matt Hodges | 98% | 100% | 99.7% | 99.85% | 99.77% | 99.78% | 100% | 97.57% | 99.72% | 99.97% | 100% | 98.86% | 99.99% | 99.44% | 99.99% | 99.81% | 99.81% | 99.76%
A1.10 |  | Availability of CMS VO box 99 % |  | Matt Hodges | 99% | 100% | 99.7% | 99.85% | 99.77% | 99.83% | 100%
A1.11 |  | Availability of CE service 99 % |  | Matt Hodges | 99% | 100% | 99.54% | 99.6% | 96.45% | 99.12% | 99.89% | 91.24% | 99.15% | 99.02% | 99.4% | 97.69% | 99.87% | 95.47% | 99.25% | 98.5% | 99.95% | 96.02% | In early June there was a problem with the central monitoring tests. The overall site availability was fixed-up by request. However, this still reflects in this measure.
A1.12 |  | Number of Security Incidents 2 per year |  | Matt Hodges | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
A1.13 |  | # level 3 incidents(newly entered or active) in disaster management system 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A1.14 |  | # level 4 incidents (newly entered or active) in disaster management system 0 |  | Andrew Sansum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A1.15 |  | Percentage of GRIDPP4 Staff in Post 93 % |  | Gareth Smith | 93% | 80.53% | 75.33% | 70.6% | 80.23% | 88% | 86.92% | 87.44% | 84.44% | 82.91% | 84% | 92% | 97% | 98% | 83% | 81% | 89% | 98.92% | New achievable max staff count reduced to 18.5 during GridPP4+ (owing to overheads changes)
A2.1 |  | Fraction of WLCG MoU commitment for Disk 100 % |  |  | 100% | 122% | 149.3% | 146% | 136% | 121.3% | 114% | 119% | 114.7% | 128% | 127% | 130% | 133% | 134.7% | 135% | 136% | 133.3% | 163%
A2.2 |  | Fraction of WLCG MoU commitment for Tape 100 % |  | Andrew Sansum | 100% | 57% | 58.33% | 84.4% | 102% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
A2.3 |  | % met of GRIDPP T1RB Allocation for Tape 100 % |  | Jeremy Coles | 100% | 57% | 56.3% | 80.67% | 111.3% | 103.3% | 103.4% | 105.7% | 107% | 100% | 108% | 106.3% | 109.7% | 108.3% | 107.3% | 102.7% | 104% | 100%
A2.4 |  | % met of GRIDPP T1RB Allocation for Disk 100 % |  | Andrew Sansum | 100% | 107% | 119.6% | 118.4% | 125% | 123.7% | 115.8% | 113.2% | 123.3% | 142.7% | 126% | 113.3% | 119% | 112% | 118.7% | 116% | 106.7% | 102.7%
A2.5 |  | # Storage node failures leading to filesystem loss or damage |  | Andrew Sansum | 2 | 0.33333 | 0.66667 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0 | 0 | 0 | 0 | 0.33333 | 0.66667 | 0 | 0 | 0
A2.6 |  | % Lost disk server hours due to hardware problems over deployed base |  | Matt Hodges | 1% | 0.3333% | 0.2967% | 0.4833% | 0.04667% | 0.3333% | 0.003333% | 0.2233% | 0.03% | 0.01% | 0.01% | 0.003333% | 0.01% | 0.1% | 0.05333% | 0.04333% | 0.2133% | 0.1%
A2.7 |  | Damaged tapes/month, leading to data loss |  | Matt Hodges | 1 | 0 | 0.33333 | 0 | 0 | 0 | 0 | 0.33333 | 0.33333 | 0 | 0 | 0 | 0.33333 | 0 | 0 | 0 | 0 | 0
A2.8 |  | CASTOR SAM tests: ATLAS VO | Metric calculation changed in 12Q1 Now harder | Matt Hodges | 99% | 98.73% | 98.6% | 98% | 94.28% | 98.23% | 99.14% | 93.53% | 98.33% | 97.6% | 97.73% | 97.96% | 99.51% | 98.59% | 98.17% | 96.53% | 98.97% | 98.67%
A2.9 |  | CASTOR SAM tests: ALICE VO | Metric calculation changed in 12Q1 Now harder | Andrew Sansum | 99% | 99.77% | 99.63% | 99.72% | 98.29% | 98.6% | 99.91% | 96.5% | 99.58% | 99.8% | 99.27% | 99.39% | 100% | 99.07% | 100% | 99.44% | 100% | 100%
A2.10 |  | CASTOR SAM tests: CMS VO | Metric calculation changed in 12Q1 Now harder | Andrew Sansum | 99% | 97.19% | 99.62% | 99.05% | 87.36% | 97.83% | 99.64% | 94.75% | 98.64% | 98.7% | 98.1% | 98.9% | 97.97% | 98.6% | 99.62% | 97% | 98.97% | 98.33%
A2.11 |  | CASTOR SAM tests: LHCb VO | Metric calculation changed in 12Q1 Now harder | Matt Hodges | 99% | 98.4% | 99.64% | 99.46% | 97.26% | 98.01% | 99.86% | 96.44% | 99.11% | 99.77% | 99.3% | 99.17% | 99.23% | 98.93% | 99.88% | 98.03% | 96.87% | 98.67% | LHCb load (stripping campaign) in January affected LHCb SRMs causing tests to timeout.
A2.12 |  | Reliability of tape robot 99 % |  | Matt Hodges | 99% | 100% | 100% | 100% | 100% | 100% | 99.97% | 98.61% | 99.9% | 100% | 100% | 100% | 100% | 99.43% | 100% | 100% | 100% | 100%
A3.1 |  | WLCG Service Availability Target (set lower by WLCG than MoU, taken from OPS availability) 97 % |  | John Gordon | 97% | 99% | 98.67% | 98.33% | 93% | 99.67% | 100% | 95.67% | 99.33% | 99.33% | 99% | 98.67% | 100% | 99.67% | 100% | 99% | 100% | 99.67%
A3.2 |  | WLCG Service Availability for Alice 97 % |  | Matt Hodges | 97% | 96.33% | 99.67% | 100% | 97.67% | 99.67% | 99.67% | 95.33% | 99% | 99.67% | 99% | 97.33% | 100% | 99% | 100% | 99.67% | 100% | 100%
A3.12 |  | WLCG Availability Rank for Alice | [6 empty] | 5.6667 | 2.3 | 2.3333 | 5 | 2 | 2.3333
A3.3 |  | WLCG Service Availability for ATLAS 97 % |  | Matt Hodges | 97% | 96% | 93.67% | 95.17% | 91% | 97.67% | 99% | 93% | 97.67% | 97% | 97.33% | 96.33% | 99.67% | 98.67% | 98.33% | 96.67% | 99% | 98.67%
A3.13 |  | WLCG Availability Rank for ATLAS |  |  | 5.5 | 8 | 10.3333 | 8.6667 | 9.6667 | 8 | 5 | 6 | 7 | 6.3333
A3.4 |  | WLCG Service Availability for CMS 97 % |  |  | 97% | 97% | 97% | 97.5% | 96% | 97.67% | 99.67% | 93.67% | 98.33% | 98.67% | 97.67% | 99% | 97% | 98.67% | 99.67% | 96.33% | 99% | 98.67%
A3.14 |  | WLCG Availability Rank for CMS |  |  | 4 | 4.3333 | 6.3333 | 5 | 6.3333 | 5.3 | 1.6667 | 4 | 4.3333 | 4.3333
A3.5 |  | WLCG Service Availability for LHCB 97 % |  | Matt Hodges | 97% | 91% | 99% | 98.33% | 95.33% | 97.33% | 99.67% | 96.33% | 99% | 99.67% | 98.33% | 97.33% | 99.33% | 99% | 100% | 98% | 97% | 98.67% | See comment for A2.11
A3.15 |  | WLCG Availability Rank for LHCB |  |  |  | 4.3333 | 2.3333 | 2.3333 | 6.3333 | 6.3333 | 1 | 3 | 2.3333 | 1.6667
A3.6 |  | Respond to pager within 2 hours 95 % |  | Matt Hodges | 95% | 99.25% | 100% | 99.17% | 100% | 100% | 100% | 100% | 100% | 98% | 98.5% | 97.75% | 100% | 100% | 100% | 98.83% | 97% | 100%
A3.7 |  | Number of GGUS Tickets not responded to within two hours . |  | Matt Viljoen | 3 per month | 0 | 1.3333 | 0.66667 | 3 | 1 | 0.33333 | 1.6667 | 0 | 0 | 1.3333 | 0.33333 | 0 | 0.33333 | 1 | 0.33333 | 0.66667 | 0.66667
A3.8 |  | Job Efficiency (CPU/Wall) 70 % |  | David Corney | 70% | 80.43% | 82.8% | 83.8% | 85.37% | 90.6% | 89.63% | 91.1% | 92.13% | 89.3% | 93.5% | 90% | 88.23% | 85.83% | 78.33% | 81.67% | 85% | 83.33%
A3.9 |  | Farm Occupancy 70 % |  | Martin Bly | 70% | 79.83% | 85.5% | 88.23% | 84.77% | 92.4% | 94.9% | 87.87% | 82.23% | 72.6% | 88.5% | 83.67% | 84.57% | 84.97% | 81.33% | 74% | 79% | 90.67%
A3.10 |  | Percentage of available T1 Disk 1 used in quarter 20 % |  | Tim Folkes | 20% | 71% | 65.33% | 69.47% | 68.87% | 59.9% | 68.2% | 73.3% | 77.37% | 67.86% | 80% | 84% | 83.17% | 71.33% | 63.67% | 72.67% | 79.53% | 76%
A3.11 |  | Used tape capacity (TB) |  | Tim Folkes | 5416 | 3554.6667 | 4170.3333 | 4918.6667 | 5287 | 5986.3333 | 7133 | 8784.6667 | 9101.3333 | 9283.3333 | 9854 | 9933.3333 | 10566.6667 | 11250 | 11466.6667 | 11266.6667 | 10602.6667 | 10643.3333
Note on G34: Andrew Sansum: There were a number of CASTOR issues during June: 2011-06-20: CMS LSF accidently switched off 2011-06-21: DB deadlock due to incident the previous day, causing SAM tests to fail 2011-06-25/26: Oracle DB problems 2011-06-27: problems with cmsWanIn. To fix this, shared memory was cleared; LSF and job manager restarted Starting on 1st June, 2 cosmics workflows started running which each had over 170000 very tiny jobs (*). The CPU efficiency of these jobs was < %5 because they spent most of their time just opening files. This put a constant load of around 1000 requests/minute on the stager (and hence LSF) which is much higher than normal. The load on diskservers was negligible. However, the load on LSF caused it to sometimes take a very long time to process requests, resulting in occasional SAM test failures due to timeouts and FTS transfer failures due to timeouts. In the future if such workflows are run we could use xrootd instead of rfio, as xrootd is setup in the CMS instance to have unscheduled reads. Unfortunately we didn’t get xrootd working successfully until these workflows had almost finished. The problem might also be avoided in CASTOR 2.1.11 with the alternative scheduler.

## Milestones
GridPP Quarterly Report |  |  |  | Complete |  | Proposed to be Rescheduled
Area | Tier-1 |  |  | Overdue |  | Likely to be late
Quarter | Q215 |  |  | Not yet due |  | Proposed Milestone change
Reported by | Andrew Sansum |  |  | Suspended |  | Query
Based on Milestones 1.3d-2
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
A1.16 | External Review of Operations | Andrew Sansum | 2015-10-01
A1.17 | Strategic and operations plan agreed | Andrew Sansum | 2015-06-01
A4.1 | Internal strategic and technology review | Andrew Sansum | 2016-03-01
A4.2 | Produce the purchasing plan | Andrew Sansum | 2016-06-01
A4.3 | Capacity procurements started | Andrew Sansum | 2015-04-01 |  |  | Started
A4.4 | Capacity order placed | Andrew Sansum | 2015-09-01
A4.5 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2016-03-01

## Manpower Q1 15
GridPP Quarterly Report
Area | Tier-1
Quarter | Q1 15
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, | 2.8 | 2.8 | 2.8 | 0 | 0 | 0 |  | 8.4 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Barnsley | 5 | 5 | 4.8 | 0.5 | 0.5 | 0.5 |  | 16.3 | 1.5
Tier-1 | CASTOR/Tape | Viljoen, Canning , De Witt, Folkes, Prosser, Davies,Appleyard | 4.3 | 4.3 | 3.9 | 0 | 0 | 0 |  | 12.5 | 0
Tier-1 | Database | Cioffi, Viljoen, Smirnov | 2.29 | 2.29 | 2.29 | 0 | 0 | 0 | Short term effort increase to test DR | 6.87
Tier-1 | Management | Sansum | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | unfunded 0.4 is JCG APEL work temp on GridPP | 2.7 | 1.2
Tier-1 | Operations | Norris, Patel, Sheppard | 0.4 | 0.4 | 0.4 | 0.9 | 0.9 | 0.9 |  | 3.9 | 2.7
Tier-1 | Network |  | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 |  | 1.5 | 1.5
Tier-1 | Production | Smith, Idiculla, Kelly | 2.75 | 2.75 | 2.75 | 0 | 0 | 0 |  | 8.25 | 0
Total |  |  | 18.04 | 18.04 | 17.44 | 2.3 | 2.3 | 2.3

## Manpower Q2 15
GridPP Quarterly Report |  | GridPP Quarterly Report
Area | Tier-1 | Area | Tier-1
Quarter | Q215 | Quarter | Q215
Reported by | Andrew Sansum | Reported by | Andrew Sansum
Effort (FTE)
[5 empty] | GridPP Funded |  |  | Unfunded
Site | Work area | Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Tier-1 | Fabric | Bly, Hafeez, Harper, Walia | GridPP Funded Month 1: 2.8; GridPP Funded Month 2: 2.8; GridPP Funded Month 3: 3.3 | New HW person (Chetan Walia) started in June. | 8.9 | 0
Tier-1 | Grid | Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 5.4 | 5.4 | 5.4 | 0.4 | 0.4 | 0.4 |  | 16.2 | 1.2
Tier-1 | CASTOR/Tape | Tier-1 | CASTOR/Tape | Viljoen, Canning , De Witt, Folkes, Prosser, Davies,Appleyard, Johnson | GridPP Funded Month 1: 4.96; GridPP Funded Month 2: 4.96; GridPP Funded Month 3: 4.96 | Short Term programmer effort for GridFTP interface to CEPH. | 14.88 | 0
Tier-1 | Database | Tier-1 | Database | Cioffi, Viljoen, Smirnov | GridPP Funded Month 1: 1.29; GridPP Funded Month 2: 1.29; GridPP Funded Month 3: 1.29 |  | 3.87
Tier-1 | Management | Tier-1 | Management | Sansum | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5 |  | 1.5 | 0
Tier-1 | Operations | Tier-1 | Operations | Norris, Patel, Sheppard, Knightley | 0.4 | 0.4 | 0.4 | 0.9 | 0.9 | 0.9 |  | 1.2 | 2.7
Tier-1 | Network | Tier-1 | Network |  | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 |  | 1.5 | 1.5
Tier-1 | Production | Tier-1 | Production | Smith, Idiculla, Kelly | GridPP Funded Month 1: 2.8; GridPP Funded Month 2: 2.8; GridPP Funded Month 3: 2.8 |  | 8.4 | 0
Total |  | Total |  |  | 18.15 | 18.15 | 18.65 | 1.8 | 1.8 | 1.8

## Narrative
GridPP Quarterly Report
Area | Tier-1
Quarter | Q215
Reported by | Andrew Sansum
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General | Various changes have been made to setup the DiRAC VO - leading to the first successful file transfers (during June)
Management | New Ceph developer recruited (George Vasilaskos). New Year in Industry student Calum Williams recruited |  | Owing to a change in STFC overheads rates for GridPP4+ maximum affordable staff count at the Tier-1 has fallen from 19.5 FTE to 18.5 FTE. The Tier-1 manager continues to work at reduced effort of 0.5 FTE (reduced from 1 FTE) owing to a change of duties. Reduced management effort has led to degraded project and financial management and as well as project reporting and continuous service improvement.
CPU | In May initial tests took place with a new worker node configuration - using Aquilon for the deployment of the nodes and Grid middleware being picked up using CVMFS. 2014 batches of CPU brought online (by early June); Batch job limit for Alice completely removed (June);
Disk | Disk server deployments carried out? New team of > 1.5 FTE in place to deploy Ceph as a replacement to CASTOR disk. This project is expected to run for the full duration of GridPP4+
CASTOR | Separate Castor namesever box set-up to enable queries against Castor metadata to be made without affecting the throughput of production work (February); The migration of all data off T10000A & B media was completed (March); Castor minor version update (to version 2.1.14-15) in April; Castor tape servers updated to SL6 (by mid-May); Following a problem flagged by LHCb old files in Castor that did not have a recorded checksum has this retrospectively added (June); |  | Problems seen with throughput and file open times for CMS. Also - problem of AAA xroot redirection not working. In mid-May problems severe owing to hot files. Work on resolving performnce problems for CMS included allowing unscheduled xroot reads from CMS disks (June);
Grid Deployment | A new Stratum-1 system for the cern.ch domain set-up (March); Atlas FTS traffic started to be routed via development FTS3 systsem (as a test - in cooperation with Atlas); A number of FTS updates were applied to the service over the period (done in conjunction with VOs & developers).
Core Services
Production Team
Network |  |  | For all of this period (January - June) we were running with a single network router rather than a resilient pair; From end March started to see sporadic low level packet loss on external links; Early April: Network problem caused delay of Castor update (subject of post mortem). At the end of April there was a latency diffenence to/back over OPN - fixed early May.
Machine Room Operations | Safety check of the electrical power circuits in the machine room carried out in January.
Database team | Atlas Frontier (3D) moved to using new database backend (called "Cronos"). (February)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It isincreasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However r ecent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on disk storage project in case CASTOR not suitable for run 2.
Staffing levels will be difficult to sustain at planned levels. The considerable uncertainty in funding situation for GRIDPP5 continues to have a negative impact on staff retention. Recruitment and retention at STFC for computing positions has become increasingly difficult owing to uncompetative pay. This is further complicated by the increasing difficulty matching job description and salery for Tier-2 Visias against computing roles further reducing the pool of candidate labour. |  | Recruitment and retention has been raised by SCD to the highest level within the corporate risk register and is being treated as an urgent matter by Operations Board and the Head of HR. Approval to recruit, once slow and tortuous is now unimpeded allowing recruitments to start rapidly. HR are receptive to a variety of newer approaches to recruitments. SBS are increasingly efficient at initiating recruitments. Nevertheless the situation remains challanging.
The Tier-1 project to connect to the site core at 40Gb/s (and to terminate the LHC OPN on Tier-1 routers) has been delayed owing to Tier-1 team staff departures and operational problems.Network bandwidth limitations on the Tier-1 links to JANET. STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
A4.8 Produce the purchasing plan |  | 2015-06-30 |  | Plan 1.6 signed off with GridPP
A4.20 MoU Commitments met |  | 2015-03-31
A4.4 Internal Strategic and Technology review |  | 2015-03-31 |  | This was carried out and documented as part of the GridPP5 Proposal
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
A4.20 WLCG MoU Commitment met |  | 2015-03-01 |  | Hardware procurements are running a few weeks later than usual however we expect to be able to deliver both disk and tape resources through reserve capacity. CPU capacity may be a little tighter than planned in April.
A4.4 Internal strategic and tech nological review |  | 2015-03-01 |  | The GRIDPP5 proposal is expected to cover this milestone adaquatly.
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
A1.19 External review of operation |  | 2014-05-01 |  | TBC | PMB concluded review was inappropriate given uncertainty in Tier-1 funding in GRIDPP5
A1.23 Strategic and operations plan agreed |  | 2014-06-01 |  | TBC | Pending on A1.19
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on H51: Unable to set until new LHC schedule and revised experiment resource requirements
Note on H52: Unable to set until new LHC schedule and revised experiment resource requirements

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes