## Metrics
GridPP Quarterly Report | [14 empty] | OK
Area | ATLAS | [13 empty] | Close to target
Year | 2015 | [13 empty] | Not OK
Reported by | Roger Jones | [13 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q113 | Q213 | Q313 | Q413 | Q114 | Q214 | Q314 | Q414 | Q115 | Q215 | Comment Q113 | Comment Q213 | Comment Q313 | Comment Q413 | Comment Q114 | Comment Q214 | Comment Q314 | Comment Q414 | Comment Q115 | Comment Q215
A5.1 | Tier 1 -Required hardware deployed |  | Roger Jones | Requested share, dymanic
A5.2 | Tier 1 - Job success rates from ATLAS dashboard |  | Roger Jones | 0.95 | 0.974 | 0.961 | 0.979 | 0.992 | 0.994 | 0.98 | 0.981 | 0.98 | 0.986 | 0.991
A5.3 | Tier 1 - Data availability from ATLAS dashboard |  | Roger Jones | 0.98 | 0.992 | 0.991 | 0.984 | 0.987 | 0.996 | 0.988 | 0.986 | 0.98 | 0.99 | 0.991
A5.4 | Tier 1 - Data acceptance from Tier-0/1/2 - ATLAS SAM tests |  | Roger Jones | 0.98 | 0.95 | 0.972 | 0.993 | 0.994 | 0.996 | 0.989 | 0.985 | 0.967 | 0.985 | 0.96
A5.5 | Tier 1 - Data loss |  | Roger Jones | 0.01 | [12 empty] | 409 files lost, with 4 more lost and recovered
B1.2 | Tier 2 - Group data space deployed in space tokens |  | Roger Jones | Requested share, dynamic
B1.3 | Tier 2 - Production job success rates |  | Roger Jones | 0.95 | 0.955 | 0.961 | 0.956 | 0.954 | 0.961 | 0.973 | 0.974 | 0.97 | 0.985 | 0.973 |  |  |  | Sheffield and QMUL had particularly torrid times for analysis
B1.4 | Tier 2 - Data availability from the ATLAS dashboard |  | Roger Jones | 0.95 | 0.967 | 0.971 | 0.926 | 0.926 | 0.977 | 0.959 | 0.942 | 0.974 | 0.936 | 0.939 |  |  |  | The QMUL availability pulled this down |  |  | Sheffield and Manchester had low data availbaility figures
B1.5 | Tier 2 - Data acceptance |  | Roger Jones |  | 0.9 | 0.9526 | 0.972 | 0.962 | 0.977 | 0.989 | 0.982 | 0.9475 | 0.99 | 0.982 |  | Birmingham off a lot | [5 empty] | Pulled down by London - where the availability in Nov/Dec was poor
B1.6 | Tier 2 - Data loss |  | Roger Jones | 0.05 | [11 empty] | Over 700 files lost at Manchester | 134 files lost, 132 at QMUL. A further 17 were lost and recovered at QMUL | Server lost at Lancaster; 20k files recovered but 30k deemd easier to regenerate. Rucio renaming revealed smaller data losses at other sites | Rather large file loss at Glasgow |  |  |  | Tools were unavailable most of Q1 so reported numebrs are low - the next quarter may be higher as the information system catches up | Modest file loss, but spread across several sites
B1.7 | Tier 2 - ATLAS availabile simulation and user analysis slots |  | Roger Jones | Requested share, dynamic
B1.8 | Tier 2 - available storage in production space |  | Roger Jones | RRB vrs Space token
B1.9 | Tier 2 - available storage in user space |  | Roger Jones | RRB vrs Space token | [12 empty] | Manchester is about 1 server under pledged value (43TB under, about 5%)
B1.12 | Tier 2 - ATLAS job success rate in user analysis |  | Roger Jones | 0.95 | 0.934 | 0.967 | 0.897 | 0.909 | 0.895 | 0.959 | 0.943 | 0.876 | 0.92 | 0.921 |  |  | This is due to a reported analysis job success rate of 83.1% at QMUL, which is at variance with the reported production job success rate of 97% at the same site. |  | Significant failures e.g. QMUL but seem to be user payload related |  | Sheffeild and Manchester had low anlysis job success (sub 90%). RHUL was also a bit low. | The relatively poor number is uniform across tiers, probably reflecting issues with the new production system rather than the sites. | Variable analysis job event rate due to large tasks with problems hitting two tiers | Much more uniform site performance thanin recent quarters
Note on B16: gronbech: site only metric from PANDA dashboard
Note on B18: gronbech: via the Steve Lloyd page folded with the available storage (Peter Love page)
Note on B19: gronbech: Cedric's page

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | ATLAS |  |  | Overdue
Year | 2015 |  |  | Not yet due
Reported by | Roger Jones |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
A5.6 | Report to PMB on delivery during the year | Roger Jones | 2011-12-01 | 1.2.12 | AHM Paper
A5.7 | Report to PMB on delivery during the year | Roger Jones | 2012-12-01 | 1.8.13 | Report completed
A5.8 | Report to PMB on delivery during the year | Roger Jones | 2013-12-01 | 7.1.14 | Report completed
A5.9 | Report to PMB on delivery during the year | Roger Jones | 2014-12-01 |  | Report completed
A5.10 | Report to PMB on delivery during the year | Roger Jones | 2015-12-01

## Manpower Q1 2014
GridPP Quarterly Report
Area | ATLAS
Quarter | 2014 Q1
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q2 2014
GridPP Quarterly Report
Area | ATLAS
Quarter | 2014 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2014
GridPP Quarterly Report
Area | ATLAS
Quarter | 2014 Q3
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q4 2014
GridPP Quarterly Report
Area | ATLAS
Quarter | 2014 Q4
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q1 2015
GridPP Quarterly Report
Area | ATLAS
Quarter | 20145Q1
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q2 2015
GridPP Quarterly Report
Area | ATLAS
Quarter | 2015 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q312
GridPP Quarterly Report
Area | ATLAS
Year | 2015
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
ATLAS Ops | A generally good quarter. |  | Glasgow had poor availbaility due to power issues, and Cambridge had a large irrecoverable file loss. The get/put failures in analysis are under investigation - they may be user errors
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q412
GridPP Quarterly Report
Area | ATLAS
Year | 2015
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
Operations | High levels of production |  | Genrally good, but there are clear teething problems with the new ATLAS production system that are slowly being irnoend out. This was expected and planned for now in advance of Run 2.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q113
GridPP Quarterly Report
Area | ATLAS
Year | 2013
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
Operations | Some useful work from UCL and Durham |  | RAL networking a concern, scratch spaces, large memory jobs at some sites e.g. Glasgow
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q413
GridPP Quarterly Report
Area | ATLAS
Year | 2013
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
Operations | Genrally smooth running; multicore operations started at Lancaster, others following. |  | Aging disk servers start to give file losses, but often losses are because it is easier to regenerate. The operational issues at QMUL and Sheffiled hurt the stats.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q114
GridPP Quarterly Report
Area | ATLAS
Year | 2014
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
Alastair Dewhurst | Significant progress on IPV6 migration; planning for CEPH SE migration; ATLASLOCALGROUPDISK clean-up |  | Balancing tasks
Operations | Continued smooth operations |  | Low jobv traffic due to code revamps in ATLAS
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## Narrative Q214
GridPP Quarterly Report
Area | ATLAS
Year | 2014
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
Alastair Dewhurst | Became distributed production/analysis co-ordinator, improving site categorization, organized user testing of JEDI, much work on ATLAS ipv6 transition, testing CELPH at RAL for ATLAS workloads, LOCALGROUPDISK cleanup.
Operations |  |  | Job traffic still low because new releases are delayed
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## Narrative Q314
GridPP Quarterly Report
Area | ATLAS
Year | 2014
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
Alastair Dewhurst | Been working on migrating Frontier service from Ogma to Cronos databases to take advantage of Golden Gate. Project managing future Ceph Grid instance at Tier 1. IPv6 working group, pushing ATLAS to test Dual stack services and pushing sites to setup dual stack Perfsonar boxes. Also testing Squid 3.x with Frontier/CVMFS which should be IPv6 compatible. Trying to figure out how to improve operational workflows with Prodsys2, JEDI, BigPanda.
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## Narrative Q414
GridPP Quarterly Report
Area | ATLAS
Year | 2014
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Ganga Atlas
Alastair Dewhurst | There was the migration to Rucio which caused many operational problems that needed following up both in the UK cloud and as Distributed Analysis Coordinator. There was also the migration from Quattor to the Agile infrastructure at CERN. He was needed to help with Frontier and Squid. He has been organising the decommissioning of the 2006, 2007 and 2008 generations of disk and CPU. He has been organising the Ceph/New Storage project. It is a crucial period in its development, it will hopefully drop away. He ran an ATLAS Distributed computing tutorial in December. IPv6 continues to plod on in the background. His energy efficiency big idea got accepted and he had to write a business plan for it.
Operations | ATLAS was in the transition between the old and new production system. This went reasonably smoothly, but meant that queues were not as full as would have been desired. There are still teething problems, but there is confidence it will be fully functional in time for the new data.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## Narrative Q115
GridPP Quarterly Report
Area | ATLAS
Year | 2015
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Ensured disk disk and CPU deployment in production for ATLAS at Tier 1. Project managed the new CEPH storage at RAL. Many sucessess in co-ordinating and deployoing new anaysis system for ATLAS in Run 2.
Operations | ATLAS was more stable, but still establishing the new production system and software release. The latter had an effect in some large tasks that failed
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## Narrative Q215
GridPP Quarterly Report
Area | ATLAS
Year | 2015
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | One month of paternity leave and annual holiday. Work on understanding and implementing the new ATALS Computing Model. Project mamaging the new Ceph storage. Organising committee for CHEP15. Operational load high because of the start of run 2
Operations | All effort used effectively. |  | Grave concerns over the outcome of the PPGP grants round on future operations.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
CAP | 2011-
DPHEP Management group | 2012-
Other outputs and Knowledge | Date | Notes