## Metrics
GridPP Quarterly Report | [5 empty] | OK
Area | CMS |  |  |  |  | Close to target
Year | 2015 |  |  |  |  | Not OK
Reported by | Dave Colling |  |  |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q311 | Q411 | Q112 | Q212 | Q312 | Q412 | Q113 | Q213 | Q313 | Q413 | Q114 | Q214 | Q314 | Q414 | Q115 | Q215 | Q315 | Q415 | Q116 | Comment
A6.1 | T0-RAL T1 transfer rate |  | Dave Colling |  | OK | ok | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.2 | T0-RAL T1 transfer quality |  | Dave Colling |  | OK | ok | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.3 | T1-T1 (where Ral is one of T1) transfer rate |  | Dave Colling |  | OK | ok | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.4 | T1-T1 (where Ral is one of T1) transfer quality |  | Dave Colling |  | OK | ok | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.5 | Timely and efficient availability and use of resources at RAL T1 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | Some concerns about CPU efficiency. Being investigated. | Some concerns about CPU efficiency. Being investigated. | Some concerns about CPU efficiency but these are now understood. | Some concerns about CPU efficiency but these are now understood. And are being remidied | Some concerns about CPU efficiency but these are now understood and premixing will fix
A6.6 | Tape migration rate |  | Dave Colling |  | OK | OK – not specfically measured but apparent problems | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.7 | Data Loss at Tier-1 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.8 | Site availability at the Tier-1 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.9 | Site readiness at the Tier-1 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
A6.10 | Provide an appropriate level of resources to CMS |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.1 | Bristol - Transfer rates to the UK Tier 2 |  | Dave Colling |  | Not OK | Not OK
B2.2 | Bristol - Site availability at the Tier-2 |  | Dave Colling |  | Close | Not OK
B2.3 | Bristol - Site readiness at the Tier-2 |  | Dave Colling |  | Close | Not OK
B2.4 | Bristol - Unique data loss at Tier-2s |  | Dave Colling |  | Not OK | Not OK
B2.5 | Bristol - Failed analysis jobs |  | Dave Colling |  | Not OK | Not OK
B2.6 | Bristol - Failed production jobs |  | Dave Colling |  | Not OK | Not OK
B2.7 | Bristol - Provide an appropriate level of resource to CMS |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.8 | Brunel - Transfer rates to the UK Tier 2 |  | Dave Colling |  | OK | OK Just | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.9 | Brunel - Site availability at the Tier-2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.10 | Brunel - Site readiness at the Tier-2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.11 | Brunel - Unique data loss at Tier-2s |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.12 | Brunel - Failed analysis jobs |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.13 | Brunel - Failed production jobs |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.14 | Brunel - Provide an appropriate level of resource to CMS |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.15 | Imperial - Transfer rates to the UK Tier 2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.16 | Imperial - Site availability at the Tier-2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.17 | Imperial - Site readiness at the Tier-2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.18 | Imperial - Unique data loss at Tier-2s |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.19 | Imperial - Failed analysis jobs |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.20 | Imperial - Failed production jobs |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.21 | Imperial - Provide an appropriate level of resource to CMS |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.22 | RAL PP - Transfer rates to the UK Tier 2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.23 | RAL PP - Site availability at the Tier-2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.24 | RAL PP - Site readiness at the Tier-2 |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.25 | RAL PP - Unique data loss at Tier-2s |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.26 | RAL PP - Failed analysis jobs |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK
B2.27 | RAL PP - Failed production jobs |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK | OK | Ok | Ok | Ok | Ok | Ok | Ok | Ok | Ok | OK | OK | OK
B2.28 | RAL PP - Provide an appropriate level of resource to CMS |  | Dave Colling |  |  | OK | OK | OK | OK | OK | OK | OK | Ok | Ok | Ok | Ok | Ok | Ok | Ok | Ok | OK | OK | OK

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | CMS |  |  | Overdue
Year | 2015 |  |  | Not yet due
Reported by | Dave Colling |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
A6.11 | Report to PMB on delivery during the year | Dave Colling | 2015-12-01

## Manpower Q4 2014
GridPP Quarterly Report
Area | CMS
Quarter | 2014
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1
RAL | CMS | Jelena Ilic | bar: GridPP Funded Month 1
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Manpower Q1 2015
GridPP Quarterly Report
Area | CMS
Quarter | 2015
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | GridPP Funded Month 1: 0.5; GridPP Funded Month 2: 0.5; GridPP Funded Month 3: 0.5
RAL | CMS | Jelena Ilic | GridPP Funded Month 1: 0; GridPP Funded Month 2: 0; GridPP Funded Month 3: 0
Total |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0

## Manpower Q2 2015
GridPP Quarterly Report
Area | CMS
Quarter | 2015
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
RAL | CMS | Jelena Ilic | GridPP Funded Month 1: 0; GridPP Funded Month 2: 0; GridPP Funded Month 3: 0
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2015
GridPP Quarterly Report
Area | CMS
Quarter | 2015
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q4 2015
GridPP Quarterly Report
Area | CMS
Quarter | 2015
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q1 2016
GridPP Quarterly Report
Area | CMS
Quarter | 2015
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q1 2015
GridPP Quarterly Report
Area | CMS
Year | 2015
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Excellent!!!
Jelena Ilic | Gone!
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q2 2015
GridPP Quarterly Report
Area | CMS
Year | 2015
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Some concerns about CPU efficiency at RAL. Low effiencies were seen across all CMS Tier 1 sites because of a particular workflow. However RAL was worse than all other T1 sites. Possibly due to Disk access patterns.
Andrew Lahiff
Jelena Ilic
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q3 2015
GridPP Quarterly Report
Area | CMS
Year | 2015
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
CPU efficiency problems at RAL but this is now understood.
Andrew Lahiff | Very productive (as ever)
Jelena Ilic |  |  | Nolonger exists
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q4 2015
GridPP Quarterly Report
Area | CMS
Year | 2015
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Continuing as normal
Andrew Lahiff | Great success
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q1 2016
GridPP Quarterly Report
Area | CMS
Year | 2015
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
… preparing for run 2
Andrew Lahiff | Great success
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.