## Metrics
GridPP Quarterly Report | [11 empty] | OK
Area | LHCb | [10 empty] | Close to target
Year | Q215 | [10 empty] | Not OK
Reported by | Andrew McNab | [10 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q413 | Q114 | Q214 | Q314 | Q414 | Q115 | Q215 | Comment Q413 | Comment Q114 | Comment Q214 | Comment Q314 | Comment Q414 | Comment Q115 | Comment Q215
A7.1 | Processing: Fraction of jobs executed at UK T1 | Processing jobs at RAL | Andrew McNab | 15% | 14.2% | 16.2% | 9.6% | 30.8% | 15.7% | 24.02% | 31.9% |  |  | Not a problem - skewed by IN2P3 & GridKa with delayed processing | Fluctuation (low statistics) - no major processing done this quarter
A7.2 | Processing: Fraction of jobs that were successful in the RAL Tier-1 | Processing job status at RAL | Andrew McNab | T1>70% | 96.8% | 89.1% | 95.6% | 98.1% | 90.6% | 93% | 87.1%
A7.3 | Processing: Overall job efficiency | Ratio of http://tinyurl.com/5usmnn6 and http://tinyurl.com/6x5kcwu | Andrew McNab | 90% | 97.5% | 97.6% | 98.01% | 97.9% | 97.2% | 94.7% | 96.3%
A7.4 | UK T1 SE Reliability | SE Reliability | Andrew McNab | #lost files/Q=0 #diskservers down over 8 hours < 3 | 2 1 | 1 0 | 1 1 | 1 2 | 4 0 | 0 2 | 0 1
A7.5 | User analysis: Fraction of jobs that were successful in the RAL Tier-1 | Success fraction of User jobs at RAL | Andrew McNab | 50% | 86.3% | 86.9% | 89.9% | 82.7% | 83.7% | 78.1% | 89.3%
A7.6 | User analysis: Overall job efficiency | Ratio of http://tinyurl.com/64x95hx and http://tinyurl.com/5ufw9a4 | Andrew McNab | 70% | 92.3% | 94.2% | 92.2% | 92.7% | 94.06% | 81.3% | 84.6%
B3.1 | LHCb T2 data transfer upload rate | T2 Data upload rates | Andrew McNab | 10MB/s | 36 | 19.5 | 23.2 | 16.8 | 25.2 | 24.5 | 46.5
B3.2 | LHCb No. of sites below WLCG SAM tests uptime target | LHCb Dashboard history | Andrew McNab | <2 sites | 0 | 1 | 2 | 0 | 3 | 0 | 1 |  |  |  |  | 1 medium sized HEP site (Sheffield), plus Durham and EFDA, none of which are LHCb members institutes.
B3.3 | LHCb Fraction of simulation jobs in the UK | Simulation Job Fraction | Andrew McNab | >18% (WLCG MoU) | 19.2% | 17.3% | 23.5% | 20.3% | 23% | 19.4% | 19.9% |  | All well - large fraction of simulation done by Russia and CERN where processing jobs did not run
B3.4 | LHCb job success rates in simulation | Simulation Job Success rate | Andrew McNab | 90% | 94.4% | 92% | 90.2% | 95.9% | 92.22% | 96.8% | 97.1% |  |  | Note : Large number of incorrect MC productions were submitted recently due to lack of testing
Note on B18: Imported Author: gronbech: how do we measure this
Note on B19: Imported Author: gronbech: how do we measure this

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | LHCb |  |  | Overdue
Quarter | 2015 |  |  | Not yet due
Reported by | Andrew McNab |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
A7.7 | Report to PMB on delivery during year | Andrew McNab | 2015-12-31

## Manpower Q214
GridPP Quarterly Report
Area | LHCb
Quarter | 2014Q2
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | 1 | 1 | 1 | 0 | 0 | 0
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q314
GridPP Quarterly Report
Area | LHCb
Quarter | 2014Q3
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | 1 | 1 | 1 | 0 | 0 | 0
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q414
GridPP Quarterly Report
Area | LHCb
Quarter | 2014Q4
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | 1 | 1 | 1 | 0 | 0 | 0
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q115
GridPP Quarterly Report
Area | LHCb
Quarter | 2014Q4
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | 1 | 1 | 1 | 0 | 0 | 0
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q215
GridPP Quarterly Report
Area | LHCb
Quarter | Q215
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | 1 | 1 | 1 | 0 | 0 | 0
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q114
GridPP Quarterly Report
Area | LHCb
Quarter | 2014 Q1
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Stable running, among the first sites to finish the incremental re-stripping |  | Nothing really
Tier-2 | Quick response to OpenSSL vulnerability |  | EFDA-Jet still not working for LHCb
Raja Nadakumar | GEOC shifts
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Time running out for major site-wide changes before data-taking starts. Eg. CEPH for Castor-Disk |  | Current configuration should be good enough, but a site may not be happy with it.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q214
GridPP Quarterly Report
Area | LHCb
Quarter | 2014 Q2
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth castor upgrade
Tier-2 |  |  | EFDA-Jet still problematic
Raja Nadakumar | GEOC shifts
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Networking still not in its final state at RAL? |  | Small blips can easily be tolerated in the computing model
Vidyo stability for phone conferences - EVO subscription has ended. |  | Skype?
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q314
GridPP Quarterly Report
Area | LHCb
Quarter | 2014 Q3
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | NTR / smooth running - that is itself a success.
Tier-2
Raja Nadakumar | GEOC shifts Testing LHCbDirac for ipv6 compliance
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Memory requirement increase during move to root6 |  | Various root options being studied, developers involved
Insitute or area specific risks
Risk |  | Mitigating Action
Data rates incoming to Tier-1, when LHC starts in 2015 |  | Initial ramp-up will provide us some time to get prepared.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q414
GridPP Quarterly Report
Area | LHCb
Quarter | 2014 Q4
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Significant contribution to Stripping 21 campaign.
Tier-2 | T2-D sites (Manchester and RAL-PPD) received data from Stripping 21 campaign without problems.
Raja Nadakumar | GEOC shifts
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only (Ceph-fs) storage technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q115
GridPP Quarterly Report
Area | LHCb
Quarter | 2015 Q1
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Significant contribution to the Stripping 21 campaign which concluded this quarter
Tier-2 | Imperial joined RAL-PPD and Manchester as a third UK T2-D, all three of which received data from the Stripping 21 campaign.
Raja Nadakumar | GEOC shifts
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only (Ceph-fs) storage technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q215
GridPP Quarterly Report
Area | LHCb
Quarter | Q215
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth running in preparation for data taking
Tier-2 | User jobs at T2-D sites accessing data placed there, mainly during stripping 21.
Raja Nadakumar | GEOC shifts and expert LHCb liaison with Tier-1
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only (Ceph-fs) storage technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes