## Metrics
GridPP Quarterly Report | [9 empty] | OK
Area | Data Group | [8 empty] | Close to target
Year | 2015 | [8 empty] | Not OK
Reported by | Jens Jensen | [8 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q213 | Q313 | Q413 | Q114 | Q214 | Q314 | Q414 | Q115 | Q215 | Q315 | Comment Q114 | Comment Q214 | Comment Q314 | Comment Q414 | Comment Q115 | Comment Q215 | Comment Q315
C2.1 | Number of VO requested changes not implemented in a timely fashion across whole infrastructure (1wk for small changes, 3wks for medium size, 6wks for large.) - any GridPP VO |  | Jens Jensen | 0 | [10 empty] | OK. No major changes requested except a few bits associated with Rucio renaming for ATLAS. Removing files in PRODDISK | No major changes requested | OK; no major changes requested | OK: no major changes requested. | OK, no major changes requested. | OK, no major changes requested | First round of simplification of ATLAS space tokens seems to have gone well (T3s); now need T2s (QMUL (many), Lancs, RALPP) plus CASTOR (complicated)
C2.2 | Number of experiments whose data transfer rates from/to RAL to/from T2s do not meet their (realistic) requirements |  | Jens Jensen | 0 | [10 empty] | OK | There were problems but not to/from RAL. Some T2s had problems with transfers to/from sites like BNL (such as Cambridge, Oxford) but the problem could be at the BNL end. | (WLCG only) 579 MB/s avg over all countries with RAL as a source.. Some countries like China have low "efficiency" RAL as destination is 468MB/s avg, with avg success of 94%: again some countries like Israel and China perform poorly | Avg 150 MB/s overall (between all UK sites), so about 1192 TB. | WLCG transfer rates were low but seems to be lack of activity rather than performance problems: RAL to UK T2s was 634TB, or 82 MB/s, and the other way was 28 MB/s. | Avg into RAL (WLCG only) 115 MB/s for the whole quarter; out of RAL 130 MB/s. | Apart from the three main VOs supported, only T2K seem to have transferred appreciable volumes in Q3 within the UK. DiRAC may not be in the plot as transfers were done without accounting yet they seemed to not appear under 'nil' either?
C2.3 | FTS data transfer success rate |  | Jens Jensen | 85% |  | LHC: 92% RAL LHC: >88% UK | 96% |  |  |  |  | >90% but see text) | 94% (but see text) |  | OK | This number would be easier to assess if they didn';t delete data so zealously in the FTS database | Problems with ATLAS in particular, as they seem to be attempting to write to a disabled pool. It's hard to get numbers when both the RAL and the CERN FTS do not keep logs | 86% success rate (FTS). Matrix is quite consistently green except UCL as destination shows very low rates (0-3%) to other T2s. | All T2s are 91%-100%, but RAL-Bris is low (53%) and RAL-Susx (44%) - the other way (Bris-RAL and Susx-RAL) is OK. Also RAL-RAL is quite low (68%); Brian investigated and found ATLAS file-not-found. Most failures isolated to ~1wk | UK to RAL: 94% RAL to UK: 83% Some T2s have low success rates (and a small number of transfers) - SUSX, UCL, DURHAM | RAL to UK 89%, 220MB/s; RAL to World 86% at 562 MB/s (Chile and Sweden are poor destinations with poor transfer rates but it is also v low data volumes) World to RAL is 96% efficiency at 426MB/s; World to UK is 82% eff at 1GB/s. UCL looks poor as both source and destination but mostly due to low rates (OTOH, being poor can also lead to rates being low) (This is for ATLAS/CMS/LHCb only, using the BNL, FNAL, PNNL, CERN and RAL FTSes)
C2.4 | Conference paper (CHEP, AHM, or similar (or better)) produced each year describing GridPP developments and innovations in data management and storage area |  | Jens Jensen | 4/Y |  |  |  | 1 | [6 empty] | Submission to SLAC workshop, OSG/XSEDE all-hands: fedeared storage in GridPP (Wahid presented) Wahid produced a deliverable (or rather his wife did), Kieran, weighing in at 10lb 10oz | Papers prepared for WLCG workshop: | HEPiX preparations: a few GridPP presentations | hepsysman presentations.. Big data day at Wellcome, D Colling attended and we sent him (some) slides | Papers submitted to CHEP (in April 2015). Also HEPIX in Oxford. | CHEP2015 Stoeage/data papers from gridPP: Object storage via Shims in Grid m'ware (CHEP2015) Comparison of overheads of federation tech (Shaun, Wahid, CHEP2015), Filesize distribution at RAL (Brian, Shaun), perfSonar for non-HEP (Brian), DIRAC file mgmt with EC storage (Sam, et al); | no additional papers
C2.5 | Engage with storage and data management experts within WLCG/EGI/EMI/NGS or similar, or industry, to reinforce GridPP's recognised competence in this area (talks given, meetings, virtual meetings) |  | Jens Jensen | 4/Q | [11 empty] | Wahid chaired the pre-GDB at CERN on data access: http://indico.cern.ch/event/272787/ and presented with Dirk Duellmann a summary at the following GDB. "Federation" workshop at SLAC: again, Wahid travelled to it and presented. Many people atrended remotely at the DPM workshop https://indico.cern.ch/event/265334/ Hepsysman: http://hepwww.rl.ac.uk/SYSMAN/June2014/main.html | WLCG workshop in July: http://indico.cern.ch/event/305362/. GridPP meeting at Ambleside - "will stuff scale for run 2?" GDB with UK input: http://indico.cern.ch/event/272777/ | 1. DPM workshop (Oct) 2. Brunel working with DPM on CMS stress tests for DPM. 3. ATLAS Jamboree (Dec.) | Wahid attended the Jan pre-GDB on data preservation, the GDB on "the protocol zoo" | WLCG meeting co-located with CHEP2015. | ATLAS software week (July). GridPP meeting (Sept)
C2.6 | Number of incidents not resolved within 1wk after being reported on list |  | Jens Jensen | 0 | [10 empty] | No major incidents. | Mainly RUCIO again - removing empty directories.. Also a few WebDAV issues (eg at QMUL) |  | Mostly the ShellShock incidents at the beginning of the quarter. | Some problems with DPM 1.8.9 upgrades were reported but were debugged and resolved fairly quickly. | Incidents are mostly with the new VOs (DiRAC, LIGO) and those reported tend to get solved quickly (turnaround may depend on the VO end) | FTS backlog for CMS in Glasgow - seem to have been resolved (see 250708). New GFAL resolved issues A number of issues were resolved for DiRAC fairly quickly
C2.7 | Number of blog posts |  | Jens Jensen | 8 | 3 | 0 | 3 | 8 | 5 | 6 | 6 | 7 | 5 | 5 | Brian 2, Ewan 1, Jens 5 (not really how it's supposed to work, but we got there…) | Five: Ewan 1, Brian 2, Jens 2 | Chris 1, Ewan 1, Sam 1, Jens 3 (but shorter ones) | Brian 3, Jens 3 | A yellowish green for seven: Sam 2 Brian 2 Jens 3 | Five: Jens 4, Brian 1. (At Jens and Brian were not allowed to blog during the Purdah!) | 5 posts - Brian 4, Sam 1. Everybody else, nil.
Note on G11: Jensen, Jens (STFC,RAL,SC): Ukraine appears in the "UK" plot, skewing the result slightly.

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Data Group |  |  | Overdue
Year | 2015 |  |  | Not yet due
Reported by | Jens Jensen |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
C2.8 | Milestone for Q312: DPM planing document. Which is done, but needs post-GridPP29 update before going further. |  |  |  |  | Need to circulate the post-GridPP29 updated version (=final)
C2.9 | Great ATLAS space token Arkleseizure | Brian Davies | 2016-03-31 |  | lcg-infosites reporting correct (updated) space tokens for ATLAS | Completed for some sites. Still need Lancs, QMUL, RALPP, RALT1, OX
C2.10 | Syncat v2 testing completed | Sam Skipsey |  |  |  | See http://storage.esc.rl.ac.uk/weekly/20150701-minutes.txt for bkg info (item 2)
C2.11 | Syncat v2 rolled out to all sites supporting VOs that require it | Brian Davies | 2016-03-31 |  |  | Assumes no serious problems found in testing!
C2.12 | Present GridPP work at JISC E2E workshop | Brian Davies | 2015-10-19 | 2015-10-19 | http://storage.esc.rl.ac.uk/weekly/20151104-minutes.txt | https://www.jisc.ac.uk/events/janet-end-to-end-performance-initiative-workshop-19-oct-2015
C2.13 | (Re)present GridPP at DPM workshop | Sam Skipsey | 2015-12-10 |  | Presentation
C2.14 | DiRAC data transfer document published to other DiRAC sites | Jens Jensen | 2015-11-07 |  | Document

## Manpower Q212 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q312 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q412 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q113 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q213 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q115
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 0.5
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 2.5 | 0 | 0 | 0

## Manpower Q215
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 0 | 0 | 0
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 2 | 2 | 2 | 0 | 0 | 0

## Manpower Q315
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 0 | 0 | 0
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 2 | 2 | 2 | 0 | 0 | 0

## Narrative Q414
GridPP Quarterly Report
Area | Data Group
Year | 2014
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Continuing successful work with WebDAV, CEPH, and cloud things |  | robots: http access (no authentication) leaves SEs vulnerable to robots attack since they cannot always serve a robots.txt from the / location. Hard to persuade people to blog about the work they do (except Brian).
Data Management | FTS transferred almost three times more data in a year than globusonline has done in its lifetime. (Brian found that FTS numbers were about 220 PB; GO is on 77PB at the time of writing.) |  | Continued use of lcg-utils despite their being deprecated and no longer supported.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Again, responses from non-LHC VOs and their representation to the storage group is variable - from excellent to non-existent. |  | Prod absent VOs more vigorously. Need updated contacts list.
File deletion needs revisiting: deletion rates are reported too slow, and are slower still with some of the newer non-SRM protocols. Our earlier metric said 1Hz but we now need >= 10Hz |  | Needs investigation
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DPM workshop in Naples, Italy: prepare UK input and report back |  | 2014-10-15 |  | https://indico.cern.ch/event/324705/session/0/contribution/4 http://storage.esc.rl.ac.uk/weekly/20141015-minutes.txt
Run 2 preparations: plan for all remaining todos before Run 2 (such as DPM upgrades,. Xroot throttling, IPv6) |  | 2014-11-30 |  | See minutes of storage meetings. IPv6 is delayed; xroot throttling raised at workshop (but fix is not in 1.8.9). DPM upgrade to 1.8.9 needed improvement, and migration to EPEL; and upgrade had some minor issues (http://storage.esc.rl.ac.uk/weekly/20141119-minutes.txt) and failed SAM tests at Lancaster. This is the only remaining problem (that we know of).
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
We somehow need more experience with DIRAC's data model |  | 2015-03-31
Report on file deletion rate |  | 2015-02-28 |  | wiki entry

## Narrative Q115
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Managed to engage a few more "small" Vos in discussion (cf risk raised previous Q): LIGO, ILC |  | Some middleware issues: DPM 1.8.9 site config; StoRM issue with checksums on Lustre; LHCb problem with dCache open files.
Data Management | Ready for run 2! |  | Wahid leaving!
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Experiences with DIRAC (non-LHCb) data tools (cf last quarter's objective) found them flakey? |  | Work with new VOs? More debugging/testing?
Middleware: Couple of issues associated with DPM 1.8.9 upgrade (in addition to the ones reported in December) but seemed to be a site config issue and resolved. Also a StoRM bug with recent versions of Lustre, particularly affecting checksumming. |  | Not much else we can do: keep testing, report bugs
Insitute or area specific risks
Risk |  | Mitigating Action
Wahid leaving leads to loss of expertise in DPM or reduces our ability to support T2s |  | Replace Wahid? Retrain someone already part of GridPP storage and data management?
Some sites had poor performance for a ~week, leading to significant drops in their success rates |  | If probelsm recur, work more closely with sites where poor performance is a site problem (as opposed to timeout, experiments reading non-existing files)
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
We somehow need more experience with DIRAC's data model |  | 2015-03-31 |  | Preliminary reports in the storage meetings (see eg 25 Feb). Suggestion is that we follow up with new VOs which will be using DIRAC.
Report on file deletion rate |  | 2015-02-28 |  | Further experience/report available, e.g.: http://gridpp-storage.blogspot.co.uk/2015/02/so-atlas-have-just-finished-deletion.html Deletion rates are a tradeoff between submitting them individually (slowest), scheduled in bulk but executed individually, and executed in bulk (fastest but dangerous)
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Need to back up 5PB of DiRAC data - while it goes to T1 tape, it is an area where GridPP storage and data management should contribute expertise. Some DiRAC sites also host GridPP sites |  | 2015-06-30 |  | 1. Plan 2. Transfers started 3. Experiences from first transfers
New "small" VO feedback on DIRAC data management (e.g. LIGO) |  | 2015-06-30 |  | Presentation or report

## Narrative Q215
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | This time successes and weaknesses are related. Getting DiRAC started and moving was a success: an important customer and they are happyish |  | The surprising amount of effort/time required and gotchas found to get DiRAC set up and running (particularly the RAL end but in general). Same for users of DIRAC.
Data Management | FTS is proving useful in moving data for users |  | Some weaknesses found in FTS3 - need for long term VOMS proxies, need to check holdings against expectation
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Data support for small VOs: shared storage can be filled up (Liverpool) or tools can be hard to use (DiRAC, LIGO) |  | We are now doing (usually) weekly updates on the small or new VOs in the storage meeting (www.storage.esc.rl.ac.uk/weekly)
Recent and emerging changes in experiment data models lead to problems at T2s (or require changes in T2 software) |  | More testing is needed: particularly the T2C model
FTS3 has done well moving files for DiRAC (and others!) |  | Need for extra tools around FTS (which ATLAS and CMS already have) for "small" VOs: checking data holdings, accounting, scheduling FTS transfers
Insitute or area specific risks
Risk |  | Mitigating Action
Some technical risks have resurfaced: (a) deletion rates, particularly at RAL. Old target was 1Hz, we now need 10Hz? (b) delay in deploying bugfixes (eg GFAL) causing problems (c) difficulty in setting up or using new VOs lead to shareed VOs (eg SouthGrid) or 'NIL' VOs (which are not good for accounting) |  | (a) Improve documentation for users (b) more testing (c) write scripts/tools to make process friendlier for users? (d) make better use of existing tools to plug gaps for new VOs?
Problems in setting up new VOs lead to GridPP getting a bad reputation…? |  | (a) We now strongly recommend that members of GridPP join the new VOs to aid debugging. (b) We now have the GRIDPP-SUPPORT mailing list recommended for (technical) contacts in VOs
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Need to back up 5PB of DiRAC data - while it goes to T1 tape, it is an area where GridPP storage and data management should contribute expertise. Some DiRAC sites also host GridPP sites |  | 2015-06-30 |  | 1. Plan 2. Transfers started 3. Experiences from first transfers DONE: DIRAC-USERS mailing list records the experiences in detail See also http://gridpp-storage.blogspot.co.uk/2015/06/the-firewall-did-it.html
New "small" VO feedback on DIRAC data management (e.g. LIGO) |  | 2015-06-30 |  | So we got feedback from LIGO which we can summarise as follows: experiences with DIRAC are frustrating because (a) neither tools nor instructions work well, and (b) lack of progress due to lack of time on their side. It is known some problems were outside GridPP, too, such as networks at user location.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Proposal/plan for feasibility testing of future Tier 2 (aka T2D) based on cheaper erasure coded storage (with no SRM interface?) |  | 2015-08-15 |  | Proposal/plan
T2C experiences: rely on data from other T2s. Experience with either T2C (eg UCL or Oxford as a volunteer) or stress testing Bristol with data from other GridPP sites |  | 2015-09-30 |  | Tests run: results
(Objective for Q4) The "syncat" problem will need revisiting: checking SE contents against catalogues - CMS and ATLAS are both making "plans" requiring full namespace dumps and DiRAC highlighted issues |  | Q4

## Narrative Q315
GridPP Quarterly Report
Area | Data Group
Year | 2015
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | MICE "close to taking data" |  | some problems with testing of the syncat dumps - script didn't work in SL5 (ATLAS)
Data Management | DiRAC seem to be pretty pleased with their stuff or at least they present it to others as a success. Document could be interesting. |  | Some slowish response rates from small VOs (again) such as UKQCD and LIGO
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
xrootd4 upgrades causing problems (as of this writing not yet in baseline), as testing reported problems with FAX |  | Testing at Glasgow upgrading head node (with redirector) to xroot4
IPv4/6 dual stack causing problems - seem to cause problems for LHCb on dCache (not in UK though) - could be xroot problem |  | More testing with Ewan's dual stack SE
syncat requirements from different VOs will differ - eg CMS seem to have their own documentation of (proposed) expectations - and different places to publish metadata |  | More work with experiemtns (representatives)?
Insitute or area specific risks
Risk |  | Mitigating Action
Storage accounting seems to be popping up again following recent work in EGI. At the same time some in WLCG VOs/sites are moving away from BDIIs. Main risk is that we need to change things again and VOs get confused (again) |  | … raise with GDB? … discussion with EGI acct team? … SE m'ware developers?
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Proposal/plan for feasibility testing of future Tier 2 (aka T2D) based on cheaper erasure coded storage (with no SRM interface?) |  | 2015-08-15 |  | two-and-a-bit pages of proposal written; however, it's Ewan's doc so please ask Ewan for access.
T2C experiences: rely on data from other T2s. Experience with either T2C (eg UCL or Oxford as a volunteer) or stress testing Bristol with data from other GridPP sites |  | 2015-09-30 |  | Delayed due to CMS's "volunteer" having higher priorities; howver, we have reminded the lucky person and Plan B is to do the testing with LHCb
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
(Q3 delayed) T2C experiences: rely on data from other T2s. Experience with either T2C (eg UCL or Oxford as a volunteer) or stress testing Bristol with data from other GridPP sites |  | 2015-09-30 |  | tests/report
The "syncat" problem will need revisiting: checking SE contents against catalogues - CMS and ATLAS are both making "plans" requiring full namespace dumps and DiRAC highlighted issues. |  | 2015-12-01 |  | Feedback to experiments from our tests
Work with DiRAC to turn the DiRAC document into something useful for UKT0 communities |  | Early Jan '16 (for EUT0) |  | document or publication

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes