## Metrics
GridPP Quarterly Report | [6 empty] | OK
Area | Security | [5 empty] | Close to target
Year | 2016 | [5 empty] | Not OK
Reported by | Dave Kelsey | [5 empty] | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q214 | Q314 | Q414 | Q115 | Q215 | Q315 | Q415 | Q116 | Comment Q214 | Comment Q314 | Comment Q414 | Comment Q115 | Comment Q215 | Comment Q315 | Comment Q415 | Comment Q116
C3.1 | Number of Tier 2 security incidents in the last quarter |  | ? | Green <=1, Amber 2 or 3 and Red >=4 | 1 | 3 | 0 | 0 | 2 | 0 | 0 | 1 | 1 incident at Glasgow reported to UK NGI Security and EGI CSIRT on 25 April (EGI RT #6949, 6951, 6954, 6957) | 1 incident at Manchester - reported to UK NGI Sec and EGI CSIRT on 15 Aug (EGI RT #7344). 1 incident at Glasgow and 1 at Liverpool all reported (UK and EGI) on 29 Sep (EGI RT #7480 and 7484) | no incident reported | no incident reported | 1 incident at Glasgow reported to UK NGI Sec and EGI CSIRT on 11 June [EGI-20150611] and related incident at ECDF/Edinburgh on 12 June [EGI-20150612]. | no incident reported | no incident reported | 1 incident at Imperial College reported to UK NGI Security and EGI on 28 February 2016. [EGI-20160228-01].
C3.2 | Number of sites responding poorly to a security incident in last quarter |  | ? | Green 0, Amber 1 Red >=2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Well handled | Well handled |  |  | Very well handled by both sites. |  |  | Very well handled
Note on B10: gronbech: Green 0, Amber 1, Red >=2

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Security |  |  | Overdue
Year | 2016 |  |  | Not yet due
Reported by | Dave Kelsey |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
C3.3 | Security Service Challenge | Ian Neilson | 31/12/2013 (new date 30/06/2016) |  |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson has taken over responsibility for this now Ewan McM has left Oxford and will run a full test at some suitable time in first half of 2016, i.e. this might continue into GridPP5.
C3.4 | Security recommendations for the future. | D.P.Kelsey | 30/06/2014 (new date 31/03/2016) | 2016-04-15 | URL to PMB document | This report describes how security will be taken forward in GridPP5, EGI and WLCG. This was delayed given the extensions to GridPP and EGI-InSPIRE until the GridPP5 allocations and various EU H2020 project allocations were clearer.

## Manpower Q414
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.5 | 0.5 | 0.5
RAL | Deployment | Dave Kelsey | 0.2 | 0.2 | 0.2
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.5 | 0.5 | 0.5
RAL | Policy | Dave Kelsey | 0.43 | 0.44 | 0.43 | 0.15 | 0.14 | 0.13
Total |  |  | 1.13 | 1.14 | 1.13 | 0.65 | 0.64 | 0.63

## Manpower Q115
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.5 | 0.4 | 0.44
RAL | Deployment | Dave Kelsey | 0.2 | 0.2 | 0.1
RAL | Deployment | Ian Neilson |  | 0.1 | 1
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.5 | 0.6 | 0.56
RAL | Policy | Dave Kelsey | 0.58 | 0.24 | 0.6 |  | 0.33 | 0.07
Total |  |  | 1.28 | 0.94 | 2.14 | 0.5 | 0.93 | 0.63

## Manpower Q215
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.56 | 0.5 | 0.5
RAL | Deployment | Dave Kelsey | 0.1 | 0.1 | 0.1
RAL | Deployment | Ian Neilson | 1 | 1 | 1
RAL | Vulnerabilities | Linda Cornwall |  |  |  | 0.44 | 0.5 | 0.5
RAL | Policy | Dave Kelsey | 0.47 | 0.33 | 0.22 | 0.13 | 0.29 | 0.5
Total |  |  | 2.13 | 1.93 | 1.82 | 0.57 | 0.79 | 1

## Manpower Q315
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.32
RAL | Deployment | Dave Kelsey | 0.1 | 0.1 | 0.1
RAL | Deployment | Ian Neilson | 0.94 | 0.99 | 0.98
RAL | Vulnerabilities | Linda Cornwall | 0.2 | 0.2 | 0.2 | 0.18 | 0.15 | 0.12
RAL | Policy | Dave Kelsey | 0.29 | 0.42 | 0.46
Total |  |  | 1.85 | 1.71 | 1.74 | 0.18 | 0.15 | 0.12

## Manpower Q415
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.91 | 0.82 | 0.9
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.22 | 0.17 | 0.13 | 0.13 | 0.13
RAL | Policy | Dave Kelsey | 0.39 | 0.15 | 0.17 | 0.13 | 0.13 | 0.13
Total |  |  | 1.47 | 1.19 | 1.24 | 0.26 | 0.26 | 0.26

## Manpower Q116
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.72 | 0.83 | 0.97
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.19 | 0.23 | 0.13 | 0.13 | 0.13
RAL | Policy | Dave Kelsey | 0.27 | 0.38 | 0.27 | 0.13 | 0.13 | 0.13
Total |  |  | 1.16 | 1.4 | 1.47 | 0.26 | 0.26 | 0.26

## Narrative Q414
GridPP Quarterly Report
Area | Security
Year | 2014
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Chaired EGI CSIRT F2F meeting in Prague in December. Also lead the UK NGI security team with fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Ongoing discussions and development work for EGI Cloud Security issues. |  | John Green left in June 2013. The first attempt to replace via recruitment resulted in an offer to the preferred candidate but this was refused. A second attempt in the summer also failed. This post was re-advertised before Christmas with a different thrust and requirements. A person has been appointed and is due to start on March 1st 2015. Note that between DPK and LAC we are covering about two-thirds of the activities with strong support from the UK NGI security team.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. An essential component of EGI/WLCG security operations. GridPP provides matching funding for the EGI.eu funded work. Much work on vulnerability handling this quarter.
Policy | Continue to lead EGI SPG and WLCG security policy. Chaired WLCG security annual meeting at FNAL in November discussing main issues and plans for the future. Attended TAGPMA monthly meetings. Lead Sirtfi activity to define Trust Framework for operational security in Federated Identity. Gave talks on this at REFEDS and ACAMP as part of Internet2/ESnet TechX meeting in Indianapolis (Oct). Member of RCUK/JISC eInfrastructure Security and AAI working group. One meeting held this quarter.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 2013-12-31 |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. A task for the new security officer once in post and up to speed.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2014-06-30 |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Spring/Summer 2015.

## Narrative Q115
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Also lead the UK NGI security team with fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Ongoing discussions and development work for EGI Cloud Security issues. Successful security training workshop at ISGC2015 Taipei in March. New UK NGI Security Officer (Ian Neilson) started at the end of February.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. An essential component of EGI/WLCG security operations. GridPP provides matching funding for the EGI.eu core funded work. Much work on vulnerability handling this quarter.
Policy | Continue to lead EGI SPG and WLCG security policy. Chaired SCI meeting in Berlin (January) Attended TAGPMA monthly meetings. Lead Sirtfi activity to define Trust Framework for operational security in Federated Identity. Member of RCUK/JISC eInfrastructure Security and AAI working group. One meeting held this quarter. Preparing for start of EGI-Engage and AARC H2020 projects.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 2013-12-31 |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. A task for the new security officer once in post and up to speed.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2014-06-30 |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Autumn 2015 after the results of the GridPP5 bid are known.

## Narrative Q215
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. Ian Neilson now established in post and has taken over leadership of the UK NGI security team with fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Improving and documenting EGI procedures and ticket handling has been an important success of this quarter. Ongoing discussions and development work for EGI Cloud Security issues. Successful security training workshop at the UK HEP SYSMAN meeting. |  | The total effort booked for Security in Q2 2015 is larger than the 1.5 FTE allocated. Work on the related EU H2020 projects will increase during the remaining 3 quarters of the FY so less effort will be charged to GridPP in future. The integrated spend over the year will fit the allocation.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group, 14 new vulnerabilities were reported during the quarter. This work is an essential component of EGI/WLCG security operations and GridPP provides matching funding for this EGI.eu core funded work. New SVG procedures have been drafted to take account of greater usage of VMs and Cloud Technology and the greater diversity of software deployed on the infrastructure (much of this done with EGI-Engage funding). New members with expertise in Cloud technology have joined SVG. Plans were presented at the EGI Conference and UK HEP SYSMAN.
Policy | Continue to lead EGI SPG and WLCG security policy. Produced new draft policy documents (4 of them) and much activity on a new Data Protection policy for WLCG/EGI. Attended EUGridPMA and TAGPMA meetings. Leadership of the Sirtfi activity now being done by CERN to define Trust Framework for operational security in Federated Identity. Work on EGI-Engage and AARC H2020 projects (the unfunded work from GridPP point of view) has started with good planning sessions at the EGI Conference in Lisbon, the AARC kickoff meetings and TNC2015. Planning for a joint EGI/EUDAT/GEANT/PRACE security workshop in October.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 31/12/2013 (new date 31/12/2015) |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson and Ewan Macmahon will run a full test in Q4.
C3.13 Security Plans for the future |  | 30/06/2014 (new date 31/12/2015) |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Q4 2015 after the results of the GridPP5 bid are known.

## Narrative Q315
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings, including chairing a CSIRT F2F meeting in Paris (2-4 Sep). UK NGI security team fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. No UK security incidents this quarter. Ongoing development work for EGI Cloud Security issues. Studying IPv6 security.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. ~10 new vulnerabilities were reported during the quarter. New SVG procedures were close to finali to take account of greater usage of VMs and Cloud Technology and the greater diversity of software deployed on the infrastructure (much of this done with EGI-Engage funding). Work started on a revised security risk assessment for EGI.
Policy | Continue to lead EGI SPG and WLCG security policy. Continue work on new policy documents (4 of them) and much activity on a new Data Protection policy for WLCG/EGI. Attended EUGridPMA and TAGPMA meetings. Presented current policy status to WLCG GDB on 8th July including a new policy to use IGTF IOTA for a new CERN CA to use federated identity for webFTS. Planning for a joint EGI/EUDAT/GEANT/PRACE security workshop in October.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 31/12/2013 (new date 31/12/2015) |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson and Ewan Macmahon will run a full test in Q4.
C3.13 Security Plans for the future |  | 30/06/2014 (new date 31/12/2015) |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Q4 2015 after the results of the GridPP5 bid are known.

## Narrative Q415
GridPP Quarterly Report
Area | Security
Year | 2015
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT. Regular weekly/monthly meetings. UK NGI security team fortnightly meetings. Ongoing routine security operations including handling incidents and tracking required updates to software for security reasons and handling vulnerabilities. Attended 1st WISE meeting - a joint EGI/EUDAT/GEANT/PRACE security workshop Oct 19-21. Security talks at EGI Community Forum Bari 9-13 Nov.No UK security incidents this quarter. Ongoing development work for EGI Cloud Security issues. IPv6 security.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities as reported during the quarter. SVG procedures finalised (co-funded by EGI-Engage). Work on an updated security risk assessment for EGI. Attended 1st WISE meeting - a joint EGI/EUDAT/GEANT/PRACE security workshop Oct 19-21. Security talks at EGI Community Forum Bari 9-13 Nov.
Policy | Continue to lead EGI SPG and WLCG security policy. Continue work on new policy documents and much activity on a new Data Protection policy for WLCG/EGI. New AUP finalised and approved by EGI OMB. Attended REFEDs and I2 TechX meetings in Cleveland (4-8 Oct). Attended TAGPMA meetings. Attended 1st WISE meeting - a joint EGI/EUDAT/GEANT/PRACE security workshop Oct 19-21. Security talks at EGI Community Forum Bari 9-13 Nov.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 31/12/2013 (new date 30/06/2016) |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson has taken over responsibility for this now Ewan McM has left Oxford and will run a full test at some suitable time in first half of 2016, i.e. this might continue into GridPP5.
C3.13 Security Plans for the future |  | 30/06/2014 (new date 31/03/2016) |  | Should report how security will be taken forward in GridPP5, EGI and WLCG. This will be delayed given the extensions to GridPP and EGI-InSPIRE until Q1 2016 after the results of the GridPP5 bid are known. A short document will be written before the end of GridPP4+

## Narrative Q116
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT with regular weekly/monthly meetings. UK NGI security team fortnightly meetings. Ewan has left the UK NGI team and been replaced by David Crooks who is also co-leading a GDB WG on Security Operations Centres. Ian Neilson is following up on Ewan's Argus banning tests and now participates in EGI CSIRT Officer on Duty rota handling incident and monitoring/issuing vulnerability tracking tickets. One UK security incident reported, impacting only the reporting site, from Imperial College involving a poorly configured, user-provided Virtual Machine. Participated at meetings of IGTF, WLCG Collaboration Workshop and security-focussed GDB, Geant TF-CSIRT and EGI CSIRT F2F. Ongoing development work for EGI Cloud Security issues. IPv6 security.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities as reported during the quarter. Complete updated security risk assessment for EGI. Reported status and plans at EGI CSIRT F2F meeting Prague 27-29 Jan.
Policy | Continue to lead EGI SPG and WLCG security policy. Completed work on Revised VM Endorsement and Operations policy and new Data Protection Policy. Attended EUGridPMA meeting Bratislava 18-20 Jan. Chaired EGI CSIRT F2F meeting Prague 27-29 Jan. Attended security workshop, APGridPMA and ISGC2016 conference Taipei 13-18 March. Chaired session on Identity Management and spoke on IPv6 security. Attended WLCG Workshop in Lisbon 1-3 Feb.
GridSite, VOMS and Shibboleth
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2016-04-15 |  | This report describes how security will be taken forward in GridPP5, EGI and WLCG. URL
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 31/12/2013 (new date 30/06/2016) |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson has taken over responsibility for this now Ewan McM has left Oxford and will run a full test at some suitable time in first half of 2016, i.e. this will continue into GridPP5.

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes