## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Tier-1 |  |  | Close to target
Quarter | Q316 |  |  | Not OK
Reported by | Gareth Smith |  |  | Not yet able to be measured
Suspended
GridPP no. | Tier-1 no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Comment Q116 | Comment Q216 | Comment Q316
1.1.1 |  | Fraction of WLCG MoU commitment for CPU 100 % |  | Andrew Lahiff | 100% | 117.7% | 104.7% | 143.3%
1.1.2 |  | % met of GRIDPP T1-RB allocation for CPU 100 % |  | Andrew Lahiff | 100% | 127% | 115% | 124.3%
1.1.3 |  | Availability of CE service 99 % |  | Catalin Condurache | 99% | 99.58% | 99.62% |  |  |  | Problem getting this figure for one of months.
1.1.4 |  | Number of Security Incidents 2 per year |  | Gareth Smith | 2 | 0 | 0 | 0
1.1.5 |  | # level 3 incidents(newly entered or active) in disaster management system 0 |  |  | 0 | 0 | 0 | 0
1.1.6 |  | # level 4 incidents (newly entered or active) in disaster management system 0 |  | Andrew Sansum | 0 | 0 | 0 | 0
1.1.7 |  | Percentage of GRIDPP4 Staff in Post 93 % |  | Gareth Smith | 93% | 94% |  |  | New achievable max staff count reduced to 18.5 during GridPP4+ (owing to overheads changes). As staff count needs to fall to 17.5 in April it is not feasible to hit hurrent target.
1.2.1 |  | Fraction of WLCG MoU commitment for Disk 100 % |  | Andrew Lahiff | 100% | 168% | 125% | 125%
1.2.2 |  | Fraction of WLCG MoU commitment for Tape 100 % |  | Andrew Lahiff | 100% | 100% | 100% | 100%
1.2.3 |  | % met of GRIDPP T1RB Allocation for Tape 100 % |  | Andrew Lahiff | 100% | 100% | 100% | 100%
1.2.4 |  | % met of GRIDPP T1RB Allocation for Disk 100 % |  | Andrew Lahiff | 100% | 132% | 98.67% | 101%
1.2.5 |  | # Storage node failures leading to filesystem loss or damage |  | Kashif Hafeez | 2 | 0.66667 | 0 | 0
1.2.6 |  | % Lost disk server hours due to hardware problems over deployed base |  | Kashif Hafeez | 1% | 0.23% | 0.3267% | 0.1867%
1.2.7 |  | Damaged tapes/month, leading to data loss |  | Tim Folkes | 1 | 0.33333 | 0 | 0
1.2.8 |  | CASTOR SAM tests: ATLAS VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 96.33% | 99.67% | 100% | Poor availability in Jan. Problem with OPN link caused incoming tests to fail.
1.2.9 |  | CASTOR SAM tests: ALICE VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 100% | 100% | 99.67%
1.2.10 |  | CASTOR SAM tests: CMS VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 96.67% | 99.33% | 99.33% | Poor availability in Jan. Problem with OPN link caused incoming tests to fail. Plus tests run against CMSTape area in Castor which was under high load for a couple of days.
1.2.11 |  | CASTOR SAM tests: LHCb VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 98.33% | 99% | 99.67% | Poor availability in Jan. Problem with OPN link caused incoming tests to fail.
1.2.12 |  | Reliability of tape robot 99 % |  | Tim Folkes | 99% | 100% | 92.33% | 100% | Significant problems with the tape library in May and June. Initially hardware then stability of control software.
1.3.1 |  | WLCG Service Availability Target (set lower by WLCG than MoU, taken from OPS availability) 97 % |  | Gareth Smith | 97% | 99.33% | 99% | 100% |  |  |  | 0.90811
1.3.2 |  | WLCG Service Availability for Alice 97 % |  | Gareth Smith | 97% | 100% | 100% | 99.67%
1.3.3 |  | WLCG Service Availability for ATLAS 97 % |  | Gareth Smith | 97% | 98% | 100% | 100%
1.3.4 |  | WLCG Service Availability for CMS 97 % |  | Gareth Smith | 97% | 97% | 99% | 99.33% | Q116 CMS tests poor in January. There was a problem on the network bypass' that affected all VOs. For CMS the SRM tests run agains CMSTape which was under high load and saw problems during January.
1.3.5 |  | WLCG Service Availability for LHCB 97 % |  | Gareth Smith | 97% | 98.33% | 99.33% | 99.67%
1.3.6 |  | Respond to pager within 2 hours 95 % |  | Gareth Smith | 95% | 100% | 95% | 100% | Failed for one out of hours callout in May. There were low statistics with only a total of 5 callouts out of hours in the month.
1.3.7 |  | Number of GGUS Tickets not responded to within two hours . |  | Gareth Smith | 3 per month | 0.66667 | 0 | 0.33333
1.3.8 |  | Job Efficiency (CPU/Wall) 70 % |  | Andrew Lahiff | 70% | 83.67% | 86% | 89.33%
1.3.9 |  | Farm Occupancy 70 % |  | Andrew Lahiff | 70% | 88.67% | 92% | 92%
1.3.10 |  | Percentage of available T1 Disk 1 used in quarter 20 % |  | Andrew Lahiff | 20% | 78.33% | 77.33% | 79%
1.3.11 |  | Used tape capacity (TB) |  | Tim Folkes | 5416 | 15744.6667 | 17233.3333 | 19006.6667
NGI
3.4.1 |  | UK CPU and storage delivered to EGI |  | Ian Collier
3.4.2 |  | Monthly timesheets complete by 10th of each month |  | Ian Collier
3.4.3 |  | GridPP staff PM delivered as required |  | Ian Collier
3.4.4 |  | GOCDB Availability |  | Ian Collier | >99% |  | (98.96, 100, 100) == 99.53 | (100,100,100) ==100
3.4.5 |  | APEL Availability |  | Ian Collier | >99%

## Milestones
GridPP Quarterly Report |  |  |  | Complete |  | Proposed to be Rescheduled
Area | Tier-1 |  |  | Overdue |  | Likely to be late
Quarter | Q316 |  |  | Not yet due |  | Proposed Milestone change
Reported by | Gareth Smith |  |  | Suspended |  | Query
Based on Milestones 1.3d-2
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.4.1 | Produce the purchasing plan | Andrew Sansum | 2016-06-01 |  |  | A purchasing plan swas produced but changes in the amount of money available require the plan to be re-visited.
1.4.2 | FY16 Capacity order placed | Andrew Sansum | 2016-11-01
1.4.3 | FY16 Purchase in production | Andrew Sansum | 2017-04-01
1.4.4 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2017-05-01
1.4.5 | Produce the purchasing plan | Andrew Sansum | 2017-06-01
1.4.6 | FY17 Capacity order placed | Andrew Sansum | 2017-11-01
1.4.7 | FY17 Purchase in production | Andrew Sansum | 2018-04-01
1.4.8 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2018-05-01
1.4.9 | Produce the purchasing plan | Andrew Sansum | 2018-06-01
1.4.10 | FY18 Capacity order placed | Andrew Sansum | 2018-11-01
1.4.11 | FY18 Purchase in production | Andrew Sansum | 2019-04-01
1.4.12 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2019-05-01
1.4.13 | Produce the purchasing plan | Andrew Sansum | 2019-06-01
1.4.14 | FY19 Capacity order placed | Andrew Sansum | 2019-11-01
1.4.15 | FY19 Purchase in production | Andrew Sansum | 2020-04-01
1.4.16 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2020-05-01

## Manpower Q116
GridPP Quarterly Report
Area | Tier-1
Quarter | Q116
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia | 3.8 | 3.8 | 3.8 |  |  |  |  | 11.4 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 4.55 | 4.55 | 4.55 |  |  |  | reduction as increased cost sharing with ISIS | 13.65 | 0
Tier-1 | CASTOR/Tape | Canning , De Witt, Folkes, Prosser, Davies,Appleyard, Johnson | 4.6 | 4.6 | 4.6 |  |  |  | A temporary increase of 1 FTE over previous quarter - code developer effort for CEPH xrootd/gridftp plug in. | 13.8 | 0
Tier-1 | Database | Sierra, Smirnov, Packer | 1.1 | 1.1 | 1.1 |  |  |  |  | 3.3
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | Load sharing of T1 Manager role amongst several staff. But not sustainable long term | 0.6 | 0
Tier-1 | Operations | Norris, Patel, Sheppard, Knightley | 0.4 | 0.4 | 0.4 | 0.9 | 0.9 | 0.9 |  | 1.2 | 2.7
Tier-1 | Network |  |  |  |  | 0.5 | 0.5 | 0.5 |  | 0 | 1.5
Tier-1 | Production | Smith, Idiculla, Kelly | 2.8 | 2.8 | 2.8 |  |  |  |  | 8.4 | 0
Total |  |  | 17.45 | 17.45 | 17.45 | 1.4 | 1.4 | 1.4

## Manpower Q216
GridPP Quarterly Report
Area | Tier-1
Quarter | Q316
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia | 3.8 | 3.8 | 3.8 |  |  |  | 11.4 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 4.13 | 4.13 | 4.13 |  |  |  | 12.39 | 0
Tier-1 | CASTOR/Tape | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | 3.8 | 3.8 | 3.8 |  |  |  | 11.4 | 0
Tier-1 | Database | Smirnov, Packer | 0.85 | 0.85 | 0.85 |  |  |  | 2.55
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | 0.6 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | 2.8 | 2.8 | 2.8 |  |  |  | 8.4 | 0
Total |  |  | 15.58 | 15.58 | 15.58 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5

## Manpower Q316
GridPP Quarterly Report
Area | Tier-1
Quarter | Q316
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia, Chambers, Masaitis, Gale | 4.5 | 4.5 | 5.9 |  |  |  | 14.9 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 4.6297 | 4.07 | 4.07 |  |  |  | 12.7697 | 0
Tier-1 | CASTOR/Tape | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | 4.4 | 4.4 | 4.4 |  |  |  | 13.2 | 0
Tier-1 | Database | Smirnov, Packer, Contractor | 0.85 | 1.35 | 1.35 |  |  |  | 3.55 | 0
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | 0.6 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | 2.8 | 2.8 | 2.2054 |  |  |  | 7.8054 | 0
Total |  |  | 17.3797 | 17.32 | 18.1254 | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL | [7 empty] | 0 | 0
Tier-1 | GOCDB |  | 0.29 | 0.29 | 0.278 |  |  |  | 0.858 | 0
Total |  |  | 0.29 | 0.29 | 0.278 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE
Note on B22: gronbech: Expect 0.3FTE

## Narrative Q116
GridPP Quarterly Report
Area | Tier-1
Quarter | q116
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General |  |  | Two members of staff left at the end of this quarter: Shaun De Witt (Castor Team) Juan Sierra (Database Team)
Management | The Tier1 manager role is being filled by 20% of Andrew.
CPU | Capacity Purchases received by end of quarter.
Disk | Capacity Purchase received by end of quarter. Eight Disk servers, with a total capacity of almost 900TB added to Atlas Castor. |  | There have been problems with one of the older batches of disk servers (CV'11) used in the tape caches. Action has been taken to mitigate this (firmware updates, using spare disks from a different manufacturer that were in a decommissioned batch of servers). Some new disk servers are being purchased to go into the disk caches so that the older servers can be retired.
CASTOR |  |  | The Castor 2.1.15 update has not been rolled out. Early tests showed load problems on the Oracle Database. Tests have been hidered by problems within the test database system which has had to be rebuilt.
Grid Deployment
Core Services
Production Team
Network | We have seen increased use of the OPN link for part of this quarter. |  | There have been a few network problems: Twice during the quarter there were problems with one of the four links between the 'UKLight' router and the Tier1 core network. Also there was a site networking problem at the end of March. The Tier1 router pair didn't failover owing to a configuraion error.
Machine Room Operations
Database team |  |  | Following the deoparture of Juan Sierra the Database Team is down to one person - which is below the critical threshold. The use of a contractor and the recruitment of more DB Admins are being followed up as a matter of urgency.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project.
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
The Tier-1 project to replace (remove) the old UKLight router has been delayed owing to Tier-1 team staff departures and operational problems. Network bandwidth limitations on the Tier-1 links to JANET. STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set. Following a review of the UKLight router replacement a simpler course of action (as compared to that previously proposed) was agreed. Progress towards this replacement is being tracked by the Tier1 Production Manager.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
A4.5 Tier-1 WLCG MoU commitments met |  | 2016-03-31 |  | MOU commitments have been met. Capacity order received.
A4.1 Internal strategic and technology review |  | 2016-03-01 |  | Propose Re-scheduling: Was awaiting completion of GridPP5 bid. Partly dependent on appointment of new Tier1 manager.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
A4.2 Produce the purchasing plan |  | Jun '16
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
A1.16 External review of operation |  | 2015-10-01 |  | propose autumn-2016 | A review has been requested by the PMB for this timescale.
A1.17 Strategic and operations plan agreed |  | 2015-06-01 |  | propose 01/Sep/2016 | This will need to take into account the GridPP5 bid and may depend on when a new Tier1 Manager is recruited.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output
Capacity Procurements Started |  | 2016-07-01
Capacity Order Placed |  | 2016-10-01 |  | Order placed.
Note on H49: Unable to set until new LHC schedule and revised experiment resource requirements
Note on H50: Unable to set until new LHC schedule and revised experiment resource requirements

## Narrative Q216
GridPP Quarterly Report
Area | Tier-1
Quarter | q216
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General
Management | The Tier1 manager role continues to be covered by 20% of Andrew.
CPU | One of the two batches of capacity CPU purchases (that from XMA) was put into production at the end of May. We have sufficient capacity in place to meet MOU requirements. |  | Deployment to production of the second of the batches of capacity CPU purchases (that from HPE) has not yet taken place owing ting to various problems post delivery. However, MOU commitments already met.
Disk | Capacity procurement of disk delivered and readied for putting into ECHO CEPH cluster.
CASTOR | Castor "GEN Scratch" storage atrea was decommissioned slightly simplifying the Castor set-up. |  | The Castor 2.1.15 update has still not been rolled out. The test database system has been rebuilt. However work has not progressd as fast as we would like owing to the limited manpower available.
Grid Deployment | HAProxy load balancers introduced in front of the production and test FTS3 services. One of the three production WMS systems was decommissioned simplifying the service. Machine Job Features rolled out across batch farm.
Core Services | The migration of the Atlas data from 'C' to 'D' tapes was stared in this period. By end June it was around 50% complete. |  | During May and into June there were significant problems with the tape library leading to periods when it was not available. This was caused by three separate issues: - Significant hardware problem with the fix confused by a spare board failing soon after installation. - Faulty replacement handbot within the library led to safety concern. - Problem with library control software hanging.
Production Team
Network |  |  | We are seeing increased usage of the OPN link to/from CERN with the inbound traffic saturating the 10Gbit link for increasingly long periods. There was a problem with the RAL core networkin mid-April, strating late on a Friday and continuing until the Saturday afternoon. We experienced four significant breaks in connectivity during this period. A fifteen hour outage was been declared in the GOC DB.
Machine Room Operations |  |  | There was a failure of the air conditioning to the machine room early in May. Both chillers and pumps stopped. After around 30 minutes the air conditioning (pumps & chillers) was restarted and temperatures fell back down. See blog post at: http://www.gridpp.rl.ac.uk/blog/2016/05/10/r89-water-pump-outage/
Database team |  |  | During the quarter we had only one person in the Database Team - which is below the critical threshold. Work on finding a contractor and the recruitment of more DB Admins were actvely followed up.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
The Tier-1 project to replace (remove) the old UKLight router has been delayed owing to Tier-1 team staff departures and operational problems. Network bandwidth limitations on the Tier-1 links to JANET. STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set. Following a review of the UKLight router replacement a simpler course of action (as compared to that previously proposed) was agreed. Progress towards this replacement is being tracked by the Tier1 Production Manager.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
A4.2 Produce the purchasing plan |  | Jun '16 |  | Taking this as the purchasing plan for spendind within the 2016/17 FY. Plan has been produced but not yet disseminated.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
Capacity procurements started |  | July '16
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
A1.16 External review of operation |  | 2015-10-01 |  | propose autumn-2016 | A review has been requested by the PMB for this timescale.
A1.17 Strategic and operations plan agreed |  | 2015-06-01 |  | propose 01/Sep/2016 | This will need to take into account the GridPP5 bid and may depend on when a new Tier1 Manager is recruited.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output
Capacity Procurements Started |  | 2016-07-01
Capacity Order Placed |  | 2016-10-01 |  | Order placed.
Tier-1 WLCG MoU commitments met |  | 2017-03-01
Note on H49: Unable to set until new LHC schedule and revised experiment resource requirements
Note on H50: Unable to set until new LHC schedule and revised experiment resource requirements

## Narrative Q316
GridPP Quarterly Report
Area | Tier-1
Quarter | Q316
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General | Contractor (Phani Yeluri) started to work in Database Team in early July. |  | One members of staff left at the end of this quarter: Tiju Idiculla (Productio Team) In addition one person reduced their hours (to around 45%) at the end of August: Gareth Smith (Production Team)
Management | The Tier1 manager role continues to be covered by 20% of Andrew.
CPU | We have sufficient capacity in place to meet MOU requirements. The LSST VO was enabled on the batch farm at the end of July. |  | The second of the batches of capacity CPU purchases (that from HPE) is not yet in full production. It is being used to set-up and test a new configuration of worker nodes for use with CEPH. (These will run SL7 with an xroot gateway with the "worker node" in a SL6 container.)
Disk | Three disk servers each of 57TB capacity have been deployed into each of the following tape caches: AtlasTape, cmsTape, lhcbRawRdst. (I.e. a total of nine servers) at the end of July.
CASTOR
Grid Deployment | The database behind the LFC was moved to new hardware at the start of August. During September services running on the Microsoft Hyper-V 2008 infrastructure were moved to the Hyper-V 2012 infrastrcucture.
Core Services | Problems reported in last quarter on the tape libraries were resolved early in July. Since then these have operated stably. The migration of the Atlas data from 'C' to 'D' tapes was completed in August. Additional 'D' drives have been ordered (and at the time of this report delivered) to provide additional capacity ahead of migrating the LHCb data.
Production Team |  |  | Significant loss in effort in Production Team.
Network | Following saturation of the single 'primary' 10Gbit OPN link at the start of this quarter the OPN connection was reconfigured to use both 10Gbit links at the start of August. On Wednesday 5th October (just after period of report) the UKLight Router was replaced. This has also enabled a a 40 GBit connection to the RAL border routers (i.e. giving a datapath of up to 40Gbit for the bypass connection.) We have seen a significant increase in traffic over the bypass route since this change - well exceeding the previous 10Gbit limit. |  | At the end of August there was a problem with packet loss seen across a part of the Tier1 network. Finally traced to a faulty transceiver which was replaced.
Machine Room Operations | A brief power dip affected parts of the RAL site on Wedesday afternoon, 14th Sep. The R89 machine room was OK. However, it was seen by equipment in the Atlas building. This had no affect on our services.
Database team
APEL
GOCDB | Deployed v5.7 onto gocdb-test instance to include cursor-based paging and replace offset-based paging. Work with EGI + WLCG InfoSysTF to agree on new extensions for new write API and ServiceEndpoint extensions (longer term aim of reducing WLCG dependency on BDII)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
Changes to purchasing plan may add delays and lead to purchasing items earlier at less favourable prices/performance. |  | Purchasing against the revised plan will be prioritsied to expedite the processing and examined thoroughly.
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
1.4.2 FY16 Capacity order placed |  | Nov '16 |  | Needs the plan to be finalised.
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
1.4.1 Produce the purchasing plan |  | Jun '16 |  | Propose Oct/Nov '16 | Taking this as the purchasing plan for spendind within the 2016/17 FY. A plan was produced but has had to be changed as some spend originally earmarked for Tier2s is being moved to the Tier1.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes