## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | ATLAS |  |  | Close to target
Year | 2016 |  |  | Not OK
Reported by | Roger Jones |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Comment Q116 | Comment Q216 | Comment Q316
1.5.1 | Tier 1 -Required hardware deployed |  | Roger Jones | Requested share, dymanic
1.5.2 | Tier 1 - Job success rates from ATLAS dashboard |  | Roger Jones | 0.95 | 0.983 | 0.991 | 0.997
1.5.3 | Tier 1 - Data availability from ATLAS dashboard |  | Roger Jones | 0.98 | 0.965 | 0.957 | 0.973
1.5.4 | Tier 1 - Data acceptance from Tier-0/1/2 - ATLAS SAM tests |  | Roger Jones | 0.98 | 0.986 | 0.993 | 0.999
1.5.5 | Tier 1 - Data loss |  | Roger Jones | 0.01
2.1.1 | Tier 2 - Requested disk space deployed |  | Roger Jones | Requested share, dynamic
2.1.2 | Tier 2 - Production job success rates |  | Roger Jones | 0.95 | 0.915 | 0.958 | 0.969
2.1.3 | Tier 2 - Data availability from the ATLAS dashboard |  | Roger Jones | 0.95 | 0.933 | 0.93 | 0.954
2.1.4 | Tier 2 - Data acceptance |  | Roger Jones |  | 0.952 | 0.958 | 0.976
2.1.5 | Tier 2 - Data loss |  | Roger Jones | 0.05 |  |  |  |  | There was a significant irretrievable data loss at Glasgow due to a RAID card failure | An excellent quarter in terms of data loss - literally half a dozen, all of which were recovered.
2.1.6 | Tier 2 - ATLAS Available slots |  | Roger Jones | Requested share, dynamic
2.1.7 | Tier 2 - Atlas job success in production |  | Roger Jones
2.1.8 | Tier 2 - ATLAS job success rate in user analysis |  | Roger Jones | 0.95 | 0.941 | 0.93 | 0.969 | This is pulled dpwn by Sussex and Birmingham (65%and 82% availability respectively) | This is considerably depressed by problems at RALPP (72% success rate) | Birmingham and Sussex reamin low. ECDF is also below 90%
Note on B16: gronbech: site only metric from PANDA dashboard
Note on B18: gronbech: via the Steve Lloyd page folded with the available storage (Peter Love page)
Note on B19: gronbech: Cedric's page

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | ATLAS |  |  | Overdue
Year | 2016 |  |  | Not yet due
Reported by | Roger Jones |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
A5.6 | Report to PMB on delivery during the year | Roger Jones | 2016-12-01
A5.7 | Report to PMB on delivery during the year | Roger Jones | 2017-12-01
A5.8 | Report to PMB on delivery during the year | Roger Jones | 2018-12-01
A5.9 | Report to PMB on delivery during the year | Roger Jones | 2019-12-01

## Manpower Q2 2016
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2016
GridPP Quarterly Report
Area | ATLAS
Quarter | 2016 Q2
Reported by | Roger Jones
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | ATLAS | Alastair Dewhurst | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q216
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2016
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Project managing new disk only storage at RAL Echo. IPv6 deployment planning - For both ATLAS and WLCG in general. Arranging summer placements (5 proposed, 3 arranged). Attended ATLAS software week as well as site Jamboree at CERN. Also addressed ALICE long term stoarge issues at RAL and operational issues such as lost tape-based data at RAL and RHUL data lossed during migration. |  | - Echo project management - S3 / Event service development/testing - IPv6 only CPU deployment strategy - ADC review (I was one of the reviewers) - Various squid/Frontier monitoring improvements - Attended ADC TIM and CHEP days at CERN, as well as CVMFS workshop at RAL. - LocalGroupDisk management including requesting improvements from Rucio developers.
Operations | Generally good performance in T2s, but some T3 or near T3 sites (Sussex, Bham) pull the averages down. The T1 was having increasing networking issues. |  | Generally good performance at T2s, though some isses at RALPP. There are growing concerns over the absence of dedicated T1 manager; the workload is being spread over the team, to the detriment of development activities, which may have a downstream impact on operations.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
DC14 production |  | Sliding (external delay) |  | Smooth operations, feedback on new systems

## Narrative Q316
GridPP Quarterly Report
Area | ATLAS | old text
Year | 2016
Reported by | Roger Jones
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Alastair Dewhurst | Alastair has been working on the ipV6 only CPU plan for WLCG and ATLAS, and proejct managing the Echo aprt of the Ceph plan. He also supervised summer students on Ceph. |  | The majority of his time is currently on Tier 1 issues, not specificially ATLAS. It would help if a clear plan was in place for the Tier 1 responsibilities, with roles filled, so the ATLAS specific work can also be planned in a coherent fashion.
Operations
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Aging hardware |  | (Partial) hardware refresh
ipv6 transition |  | Task force established
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
CAP | 2011-
DPHEP Management group | 2012-
Other outputs and Knowledge | Date | Notes