## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | CMS |  |  | Close to target
Year | 2016 |  |  | Not OK
Reported by | Dave Colling |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q316 | Q416 | Comment Q3 | Comment Q4
1.6.1 | Data Transfer quality | PhEDEx | Dave Colling | As needed by CMS | OK | OK | This will generally be OK but will flagged as not OK if a backlog builds up.
1.6.2 | Timely and efficient availability and use of resources at RAL T1 |  | Dave Colling |  | OK | OK | CMS usage was capped during this period, however those available resources were efficientyly available.. There were also job efficiency issues but these were of CMS’ making.
1.6.3 | Data Loss at Tier-1 |  | Dave Colling |  | OK | OK | This will generally be OK but will flagged as not OK if custodial data is lost.
1.6.4 | Site availability at the Tier-1 | 90% | Dave Colling |  | 99% | OK
1.6.5 | Data availability via AAA |  | Dave Colling |  | Almost | OK | Had some problems during this period. This is being worked upon.
1.6.6 | CMS Fraction of Tier-1 work carried out at RAL |  | Dave Colling | 8% |  |  | Not Great | Between 6.8% and 13% depending on how measured
2.2.1 | Transfer rates to the UK Tier 2s |  | Dave Colling |  |  | OK
2.2.2 | Site availability at the Tier-2s |  | Dave Colling | 80% | 77% - Bristol, 98% RALPP, 99% Brunel, 100% Imperial | Bristol 90%, RALPP ~93%, Imperial 100%, Brunel 95%
2.2.3 | Site readiness at the Tier-2s |  | Dave Colling | 80% | 79% - Bristol, 98% RALPP, 89% Brunel, 100% Imperial | Bristol 93%, RALPP 89%, Brunel 100%, Imperial 100%
2.2.4 | Unique data loss at Tier-2s |  | Dave Colling |  | OK | OK | This is generally OK unless data is lost.
2.2.5 | Failed analysis jobs |  | Dave Colling |  | 30% on average across all UK sites | 35% | This seems high but is not abnormal. It appears that about 1/3 of the failures are down as site failure. I don’t really know what a good target is here have marked as OK for now. This will evolve. | not good
2.2.6 | Failed production jobs |  | Dave Colling |  | 32% | 12% failed, 10% unknown | This varies greatly from site to site. The efficiency (1-fail rate) is ~85% for Imperial at one end and about 35% at Brunel.
2.2.7 | T2 sites provide an appropriate level of resource to CMS |  | Dave Colling |  | OK | 6% or 7% depending on how mentioned | Yes
2.2.8 | AAA data transfer performance |  | Dave Colling |  | OK | OK | Worked very well | Just fine

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | CMS |  |  | Overdue
Year | 2016 |  |  | Not yet due
Reported by | Dave Colling |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.6.9 | Report to PMB on delivery during the year | Dave Colling | 2016-12-01 | 2016-12-01 | OC Docs | OC Docs and review SS
1.6.10 | Report to PMB on delivery during the year | Dave Colling | 2017-12-01 |  | OC Docs
1.6.11 | Report to PMB on delivery during the year | Dave Colling | 2018-12-01 |  | OC Docs
1.6.12 | Report to PMB on delivery during the year | Dave Colling | 2019-12-01 |  | OC Docs

## Manpower Q2 2016
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q3 2016
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q4 2016
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Andrew Lahiff | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q2 2016
GridPP Quarterly Report
Area | CMS
Year | 2016
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Lots of cloud stuff
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q3 2016
GridPP Quarterly Report
Area | CMS
Year | 2016
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Lots of cloud stuff and some container stuff
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q4 2016
GridPP Quarterly Report
Area | CMS
Year | 2016
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Andrew was very effective this quarter, especially interesting was his work running CMSjobs on different cloud infrastructures.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.