## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Data Group |  |  | Close to target
Year | 2016 |  |  | Not OK
Reported by | Jens Jensen |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Comment Q116 | Comment Q216 | Comment Q316
3.2.1 | Number of VO requested changes not implemented in a timely fashion across whole infrastructure (1wk for small changes, 3wks for medium size, 6wks for large.) - any GridPP VO |  | Jens Jensen | 0 |  |  |  | Main change was the ATLAS catalogue upload (make SE contents available at well def'd location) - seems to have completed OK. Mostly slow feedback from ATLAS | No changes | No additional changes requested.
3.2.2 | Number of experiments whose data transfer rates from/to RAL to/from T2s do not meet their (realistic) requirements |  | Jens Jensen | 0 |  | See plot |  | 350 MB/s overall avg for CMS, LHCb, ATLAS. Also DiRAC got up to 400MB/s. | Transfer and success rates for ATLAs, LHCb, and CMS mostly OK (see plot) | Avg is 82 MB/s into RAL and 110 out.
3.2.3 | FTS data transfer success rate |  | Jens Jensen | 85% |  |  |  | CERN FTS plot shows excellent success rates between sites, but one needs to dig into it a bit because in the summary the rates is marred by a large number of failures to the test instances | OK - see plot. Note the slightly dodgy destinations at ECDF, Glasgow, and Oxford are due to the test SEs (e.g. IPv6) being included in the metrics. | Success rate into RAL for main expts is 98%; from RAL is only 81% though. See plot: the failure rates are due to test SEs being included, notably Glasgow and Oxford. (NOTE: this uses the GridPP FTS servers which have done the bulk of the transfers; not the CERN or FNAL ones.)
3.2.4 | Conference paper (CHEP, AHM, or similar (or better)) produced each year describing GridPP developments and innovations in data management and storage area |  | Jens Jensen | 4/Y |  |  |  | None this quarter except people are preparing stuff for CHEP (for next Q), and for GridPP36 of course | 6-7 abstracts submitted to CHEP for storage group; Marcus' was for a presentation, the others for posters | One or two CHEP submissions were withdrawn, but still met the target:
3.2.5 | Engage with storage and data management experts within WLCG/EGI/EMI/NGS or similar, or industry, to reinforce GridPP's recognised competence in this area (talks given, meetings, virtual meetings) |  | Jens Jensen | 4/Q |  |  |  | Site report to WLCG early Feb (Sam) ATLAS Jamboree (Brian, Elena) | Sam attended the DPM collaboration meeting in April (https://indico.cern.ch/event/522634/) Good (re)presentation at hepsysman at RAL (June) | Good representation at the pre-GDB on data management; Brian attended to speak on behalf of GridPP. http://indico.cern.ch/event/394833/. Some work on accounting (cf 13 July), also July GDB. GridPP37, of course. Finallly, input from Sam and marcus on DPM-as-a-cache to DPM community.
3.2.6 | Number of incidents not resolved within 1wk after being reported on list |  | Jens Jensen | 0 |  |  |  | None reported |  | No incidents reported
3.2.7 | Number of blog posts |  | Jens Jensen | 5 | 7 | 3 | 6 | Brian 2, Marcus 2, Jens 2, Daniel 1 | Hmm are we already failing our new lower target? The purdah didn't help though. Marcus wrote all three (excellent) posts | Daniel: 4 excellent posts on Lustre upgrade; Jens 2.

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Data Group |  |  | Overdue
Year | 2016 |  |  | Not yet due
Reported by | Jens Jensen |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
3.2.8 | Deploy and test "solution" for T2C storage (e.g. cache+local storage) | Sam Skipsey | 2017-01-31 |  | Feedback to GDB
3.2.9 | Present GridPP work at data workshop at CERN | Brian Davies | 2016-09-30 |  | Presentation
3.2.10 | Develop GridPP as a "data einfrastructure" in the context of UKT0 | Jens Jensen | 2016-12-31 |  | Report?
3.2.11 | Data transfer/management comparison with climate | Jens Jensen | 2016-11-30 |  | Report, workshop, or publication

## Manpower Q212 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q312 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q412 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q113 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q213 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q116
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q216
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q316
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Narrative Q116
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Very interesting work from Marcus on ZFS! (see blog) https://gridpp-storage.blogspot.com/ |  | Very high failure rates on test SEs (particularly the IPv6 ones)
Data Management | GridPP as a data infrastrcuture: good progress with DiRAC at least; LIGO is mostly jobs and LSST not sure what to do. |  | Slow progress with LSST… some issues with integration of communities that already have their own catalogues?
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
High risks associated with future T2 - due to lots of unknowns (interfaces, infrastructure, T2C/T2D, etc.) |  | Engage with WLCG (=GDB) and experiments as much as we can. Needs some planning.
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still problematic - the few test SEs show nothing but failures?! |  | Test with lower level tools?
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Get Leicester moving data for DiRAC |  | 2016-01-31 |  | Leicester got certificates, set up services, customised the Durham script - and then "had no data to back up yet"
Finish ATLAS space token cleanup |  | 2016-03-31 |  | Considered done (by ATLAS).
All sites required to publish catalogues, er, publish catalogues |  | 2016-03-31 |  | GGUS tickets closed
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Input on data einfra to national e-infrastructure project directors' group |  | 2016-05-01
T2C testing: ATLAS hammercloud report |  | 2016-05-15
Status of future T2:summary of current issues and recommendations |  | 2016-06-30 |  | short report (to PMB)

## Narrative Q216
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Loads of good stuff submitted to CHEP |  | Very high failure rates on test SEs (particularly the IPv6 ones) - this is still a problem (see plot for Oxford on the Metrics page)
Data Management
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
High risks associated with future T2 - due to lots of unknowns (interfaces, infrastructure, T2C/T2D, etc.) |  | Update: seems to now be mostly an issue of managing experiments' expectations
Note that as of April 2016 Brian has started doing some work on a H2020 funded climate project (bringing his expertise from GridPP). However, at this momemtn his delivery to T2 support does not seem to have affected.
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still problematic - the few test SEs show nothing but failures?! |  | Test with lower level tools?
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Input on data einfra to national e-infrastructure project directors' group |  | 2016-05-01 |  | Presentation given at event at Milton Hill House
T2C testing: ATLAS hammercloud report |  | 2016-05-15 |  | Still waiting for report from Alastair Dewhurst (delayed).Delay thought to be caused by person in ATLAS HQ who is overloaded with work.
Status of future T2:summary of current issues and recommendations |  | 2016-06-30 |  | Sam's writeup of discussion(s) https://docs.google.com/document/d/1fEJtO0xANVClJrSIh8jeH30fBMtAbLyzLzzrJwTwiog/edit?usp=sharing
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Input to data workshop at CERN in September |  | 2016-09-13 |  | Presentation given on behalf of all of GridPP (by Brian Davies) http://indico.cern.ch/event/394833/
Report on the future of tape storage (Brian Davies) and expected impact on archiving operations at T1 |  | 2016-09-30 |  | Report to GridPP storage

## Narrative Q316
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | GridPP has a Science DMZ. This could be another opportunity to fly the flag. |  | Accounting may need to be looked at again…
Data Management | IPv6 seems to be working OK for (most of) the sites participating in the FTS-at-IC (ie Brunel, Imperial itself, QMUL, RHUL, and Glasgow) |  | Need to separate test traffic from production traffic for this report! (cf last Q's narrative)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Risk of storage interfaces diverging: DPM is getting DAV with "quota tokens", dCache and StoRM supporting Macaroons (=fancy cookies); CASTOR remaining at SRM |  | No mitigating action known. However, if we end up in a mess, we know who to thank…
Risks of information systems being redesigned and the same old wheel being reinvented yet again.(see July GDB); see also https://ggus.eu/?mode=ticket_info&ticket_id=117683 |  | GLUE people (incl GridPP) could work with WLCG/CERN on adopting the GLUE2 JSON schema
Insitute or area specific risks
Risk |  | Mitigating Action
Yet another redefinition of storage accounting will lead to more effort being required. See also https://ggus.eu/?mode=ticket_info&ticket_id=117683 for CASTOR's issue. |  | No mitigating action.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
T2C testing: ATLAS hammercloud report |  | 2016-05-15 |  | Still waiting for report from Alastair Dewhurst (delayed).Delay thought to be caused by person in ATLAS HQ who is overloaded with work.
Input to data workshop at CERN in September |  | 2016-09-13 |  | Presentation given on behalf of all of GridPP (by Brian Davies) http://indico.cern.ch/event/394833/
Report on the future of tape storage (Brian Davies) and expected impact on archiving operations at T1 |  | 2016-09-30 |  | Brian has been to meetings with vendors - Oracle, SpectraLogic, and LTUG (Large Tape User Group). Unfortunately roadmaps are generally under NDA, so we cannot report those to GridPP, but SpectraLogic have promised to send us information we can share.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
GridPP Input to DPM workshop in November (Sam) |  | 23-24 Nov. |  | http://indico.cern.ch/event/559673/
3.2.10. Develop GridPP as a "data einfrastructure" in the context of UKT0 |  | 2016-12-31 |  | Report/proposal
3.2.11. Data transfer/management comparison with climate |  | 2016-11-30 |  | Report or publication

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
GridPP as a data infrastructure | 2016-03-31 | All areas of research need data storage and movement even if they don't compute like HEP. Opportunity with MSDC ("UKT0") collaboration.
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Wahid Bhimji went to NERSC | 2015-03-11
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes