## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Operations |  |  | Close to target
Year | 2016 |  |  | Not OK
Reported by | Jeremy Coles |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Comment Q116 | Comment Q216 | Comment Q316
3.1.1 | Fraction of UK sites in Production | Manual - Information available from GOCDB | Jeremy Coles | Number of GridPP sites in certified status. Require 100% | 100% | 100% | 95% | At least one site will be lost from production soon - EFDA-JET is about to start being decommisioned. | EFDA-JET still in decommissioning. | EFDA-JET was decommissioned during August.
3.1.2 | Number of supported VOs | Manual - Tier-2 quarterly reports and Tier-1 | Jeremy Coles | Sum of unique VOs supported across GridPP sites - target 4 LHC + 5 other | 55 | 57 | 48 |  | Review needed.Dune and skatelescope.org added but some other claimed Vos are not active. | Using the vo table published by QMUL as opposed to counting unique instances in reports (where there may be duplication)
3.1.3 | Fraction of HEPSPEC06 used | From APEL accounting | Jeremy Coles | HEPSPEC06 used/ HEPSPEC06 available - 80% | 60% | 68% | 71% |  |  | Tier-1 occupancy varied from 90.7% to 93% and CPU/WALL 0.89 to 0.92. | Should we reduce the target value?
3.1.4 | GridPP HEPSPEC06 Available | Manual sum over entries in quarterly reports | Jeremy Coles | Total GridPP HEPSPEC06 nominally available at the end of the last quarter. Target WLCG pledge | 593910 | 591809 | 644000 |  | TBC - vs 644000
3.1.5 | GridPP disk storage available | Manual sum over entries in quarterly reports | Jeremy Coles | Total TB of disk storage nominally available from GridPP at the end of the last quarter. Target WLCG pledge | 41023 | 40946 | 38500 |  | TBC
3.1.6 | UK contribution to LHC experiments | Manual sum over data provided by accounting portal | Jeremy Coles | Percentage of jobs run by LHC V0s processed in UK in last quarter. Target is as pledged shares (11%?) | 14.07% | 11.42% | 11.13% |  |  | There were some issues identified with accounting during this period.
3.1.7 | GridPP site response to tickets |  | Jeremy Coles | Number of flagged tickets <3 | 0 | 0 | 0 |  |  | UKI was one of the better performing NGIs.
3.1.8 | Scotgrid % of promised (by that time) disk available to GridPP |  | Jeremy Coles | 100% | 335% | 192% | 192% |  | Q-1 not consistent with previous report
3.1.9 | Scotgrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 636% | 501% | 501% |  | Q-1 not consistent with previous report
3.1.10 | Scotgrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 100% | 99% | 99% |  |  | Previously Q2 showed 99% but in Q3 report is appears as 100%.
3.1.11 | Scotgrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 100% | 99% | 99%
3.1.12 | Scotgrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 58% | 69% | 68%
3.1.13 | Scotgrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 45% | 52% | 59% |  | Main decrease seen due to ATLAS i/o associated with workloads. | Big improvement this quarter. Related to better ATLAS workloads?
3.1.14 | Southgrid % of promised (by that time) disk available to GridPP |  | Jeremy Coles | 100% | 249% | 188% | 187%
3.1.15 | Southgrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 327% | 311% | 311%
3.1.16 | Southgrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 98% | 98% | 98% |  |  | Odd that it is so consistent. Anyway we abandoned it!
3.1.17 | Southgrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 98% | 98% | 98%
3.1.18 | Southgrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 64% | 65% | 66%
3.1.19 | Southgrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 56% | 57% | 57%
3.1.20 | Londongrid % of promised (by that time) disk available |  | Jeremy Coles | 100% | 303% | 215% | 215% |  | Q-1 adjusted to 303% | Adjusted Q1
3.1.21 | Londongrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 305% | 278% | 278% |  | Q-1 adjusted to 305% | Adjusted Q1
3.1.22 | Londongrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 100% | 100% | 100%
3.1.23 | Londongrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 100% | 100% | 100%
3.1.24 | Londongrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 64% | 84% | 83% | Brunel comes in at 45%
3.1.25 | Londongrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 50% | 65% | 69% | Brunel comes in at 27%. No explanation given in London report. | Brunel still low at 45%. UCL not considered. | Brunel still low and dropped to 37%.
3.1.26 | Northgrid % of promised (by that time) disk available to GridPP |  | Jeremy Coles | 100% | 229% | 159% | 160% |  | Now using new MoU numbers
3.1.27 | Northgrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 520% | 323% | 323%
3.1.28 | Northgrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 100% | 100% | 100%
3.1.29 | Northgrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 100% | 100% | 100%
3.1.30 | Northgrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 66% | 74% | 78%
3.1.31 | Northgrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 56% | 62% | 71%

## Manpower Q116
GridPP Quarterly Report
Area | Operations
Year | 2016
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.7 | 0.6 | 0.65
Jeremy Coles
Total |  |  | 0.7 | 0.6 | 0.65 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Alessandra appears to be 1FTE GridPP and 1 FTE unfunded for EGI?
Ivan Reid is not seen at any ops meetings. It sounds like he Is working on Boinc for CMS!
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q216
GridPP Quarterly Report
Area | Operations
Year | 2016
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q316
GridPP Quarterly Report
Area | Operations
Year | 2016
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded |  |  | Note
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.85 | 0.7 |  |  |  | Extra effort required for CHEP involvement and due to GridPP collaboration meeting.
Oxford | Deployment and operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1.35 | 1.2 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Brunel | Still unclear of I Reid contributions. Focus is on CMS@Home.
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Narrative Q116
GridPP Quarterly Report
Area | Operations
Year | 2016
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  | Problems/Issues
Site resources available | * New hardware delivered for (most) sites in required procurement window - much of it still needs to be commissioned though. |  |  | * Additional notes in the last quarter about old kit becoming problematic (Liverpool). 2005 Dells removed at Manchester. * Bristol: Space in HPC room is getting rare, new hardware had to wait for installation. * Glasgow lost 8481 HS06 in damage associated with local power failure.
Vos | * LSST now at Lancaster & Liverpool. * Microboone being set up (e.g. at Lancaster and Manchester (both single and multi core). * LSST first production run on grid using ganga/dirac (and using DFC). * Cron jobs in place for ATLAS - requested for storage dumps. * UCL VAC now working for ATLAS * CMS now using multi-core pilots at RALPP * Tom put forward a VO-GridPP MoU proposal. * Data models of several VOs reviewed by Storage Group |  |  | * Very few Vos running work at EFDA-JET. Fusion VO is no longer running jobs. * Some CMS workflows overloaded RALPP storage. * ITS at Sussex did not notice problems after renaming their SRM - ATLAS had agreed to update AGIS but it did not happen and led to almost no production work in Q1. * Sussex need a cross-check of their atlaslocagroupdisk following Lustre migration.
Middleware/services | * SL5 based services removed at many sites * Sheffield publishing issues fixed. * Sheffield uncovered a bug in rfcp and DPM are fixing this in next release. * Bristol deployed HTCondor CE - 2nd site outside OSG (1st is CERN). * Bristol: Most WNs are now migrated to the new Puppet master (SL 7.2, Puppet 4). Started to migrate WNs from CREAM CEs to the ARC & HTCondor CEs. * Machine job features implemented on all WNs at Cambridge * Oxford completed major DPM SE upgrade. * RALPP testing CentOS7 * Sussex upgraded Lustre to 2.5.3. * ECDF have had success with test middleware to attach Archer SC to grid (ATLAS test queue now setup). * Glasgow investigations of OpenStack progressing. * The Multicore TF accomplished its mission. Its twiki remains as a documentation source. * Good progress seen with VAC/Vcycle functionality. Presetation by Andrew McNab for VAC to be a community service well received in EGI OMB. * Vacuum Platform draft HSF technical note, setting out interfaces between VMs and VM lifecycle managers. |  |  | * Not all SL5 nodes have been decomissioned. EGI is setting a target date of the end of April (UK is ahead of many NGIs in this process!). * Sysadmins starting to note that CentOS7 is very different to SL6! (e.g. Liverpool concerned). * Problem with Manchester VOMS server disk filling up due to logging issues with jetty server (voms admin) * RHUL facing a DPM drain issue. * A WLCG decision was made to freeze glexec deploymenet. This now means sites will need to start investigating alternatives (and we need to do this for DIRAC - pilot jobs). * Some issues seen with APEL summariser in February. * Quite a lot of vulnerabilities had to be responded to this quarter. Updates are becoming a non-negligible task. * Some issues seen with EGI message brokers in January - led to SAM Nagios failures.
Site infrastructure | * Updates to configuration management (e.g. move to Puppet 3). * Faster firewall arrived at Brunel - not yet deployed! * IC LHCONE link also on IPv6 * Test GPU installation now being deployed at QMUL. |  |  | * IPv6 seeing slow progress. (Liverpool awaiting firmware updates; Sheffield want "proper instructions".) * Durham has network connectivity problems following upgrade to JANET links!
Other | * VAC resources increaed to >400 slots at Liverpool. >600 slots at Manchester. * Finalised transition of GridPP website (?) * Several site admins attended HEPiX IPv6 WG meeting at CERN. * QMUL starting power vs effiicency studies. * Sussex have managed to recruit a replacement for Matt RB - ETA 1st April. * DIRAC tutorial on job submission updated to work with the GridPP DIRAC service. |  |  | * VAC installed at Liverpool but noted that few Vos using it yet. * More staff changes: Ewan left Oxford increasing time site takes to respond to issues. * Federico leaving RALPP in April. * Gang leaving Glasgow (for Sussex) in April!
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  | Mitigating Action
The future of EMI is somewhat unclear and there is a growing indication that middleware will need to be more community/site supported. WLCG/sites may not be able to fill the gaps left by EMI ending. The risk reduced a little in Q1-13 with the creation of MEDIA to provide a loose collaboration post-EMI, but EGI indicated that funding from its community was going to reduce and a call for mini-project proposals to set priorities was made. In 2014 we have seen the HEP SW federation develop (especially in Q3) but the grid middleware component is unclear). The impact of this risk is decreasing as our sites have picked up other middleware stacks (e.g. ARC) and now also many provide a cloud offering. Additional adoption of ARC during Q1 & Q2 2015 reduces the risk further. - The ARGUS situation has improved in 2015 with the uptake of support by a group of WLCG sites. - Q3 2015: Risk is reducing as sites are increasingly adopting ARC-CEs and HTC. - Q4 2015 Risk continues to reduce. We should probably retire this risk from the ops report now and replace with one related to Centos7 (the different nature vs SL6 may lead to problems). |  |  | Stay engaged with WLCG discussions - particularly in post-TEG groups and at the GDB. Part of DPM community support. Respond to WLCG post-EMI middleware support proposal and look for ways to contribute (e.g. in tarball creation). Engage with the HEP SW federation. Play an active role in the middleware readiness verification work of WLCG. Support the work of the WLCG middleware readinees TF. ARGUS workshop took place in December with the outcome that a community support effort is being established. Further work has taken place within the ARGUS collaboration and the product looks to be adequately supported.
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  | Ensure/encourage engagement with central IT networking teams. Q414 - Durham continues with issues but has progressed testing
Several sites atill need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Still no glexec tarball - situation continues beyond WLCG MB deadline for glexec enablement. Likely need to move to a workaround approach (i.e. give instructions on how to configure rather than provide an easy to install tarball). |  |  | Keep WLCG MB/GDB aware of concerns and if possible work with WN developers to port a tarball version.
* Sussex has inadequate infrastructure monitoring |  |  | * Share approaches used at other sites
* Lancaster NAT may not cope with federated access demands |  |  | Continue monitoring closely and share potential issues/solutions between sites.
Manpower reduction due to long term sick leave at Durham leaves the site increasingly at risk. |  |  | ScotGrid support.
Bristol unable to fix accounting issue (ARC CE -> JURA -> APEL) - which reports an order of magnitude smaller usage than is known. |  |  | Continue testing.
* A clear need for test resources or a multi-site testbed has been recognised but there are resource concerns. |  |  | State GridPP policy on accounting adjustments where production resources are used for testing and encourage reuse of old hardware (especially Tier-1 hardware).
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  | Due Date |  | Metric/Output/Outcome
One GridPP cloud site in production as part of the EGI FedCloud (Overdue) |  |  | 2014-09-30 |  | IC 'almost' completed integration. Still not completed in Q115. RAL may now join. Q415: No progress. Q116: RAL 'almost' there!?
Additional remaining GridPP4+ resources installed. |  |  | 2015-12-31 |  | Resources deployed and in production. Q415: Not all procurements in place and available.
Encourage additional sites to start looking at IPv6 |  |  | 2016-03-31 |  | At least one more site with IPv6 allocations. >50% of sites to have dual-stack perfSONAR. (IC added IPv6 to their LHCONE link).
Review SL5 status across sites and have plans to meet EGI retirement of SL5 middleware. |  |  | 2016-03-31 |  | Report on SL5 services still available across infrastructure. Documented timeline from sites regarding move away from SL5. Update was collated and presented to EGI. EGIs approach is still unclear - particular in relation to disk servers.
Durham to negotiate for bandwidth allocation after 4Gb/s link commissioned in February 2016 |  |  | 2016-04-01 |  | Allocation agreed.
Additional sites working with VAC (next step in Tier-2 evolution) |  |  | 2016-03-31 |  | At least 2 more sites have working VAC instances.
Additional objectives in Tier-2 evolution JIRA tickets.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  | Due Date |  | Metric/Output
SL5 nodes removed |  |  | 2016-06-30 |  | All monitored nodes >SL5.
Investigate the benefits of ARC-CE/HTCondor for other VO job submissions |  |  | 2016-06-30
Ramp up VAC deployments and VO usage of the resources so managed. |  |  | 2016-06-30 |  | More VAC jobs slots and more jobs running via this approach.
Review IPv6 status and ensure clear documentation is in place. |  |  | 2016-06-30 |  | Experience gained from sites already transitioned to IPv6 to be written up.
Newly procured hardware at Tier-2 sites commissioned and online. |  |  | 2016-06-30 |  | New kit installed (unstable kit removed?)
See Tier-2 reports for site specific objectives (particularly ScotGrid's which includes retiring WMSes at Glasgow and signigicant HPC integration work at ECDF).
Core Ops Task contributions
Name | Area | Successes Q2 2012 |  | Concerns Q2 2012 |  | Successes Q3 2012 | Concerns Q3 2012 | Successes Q4 2012 | Concerns Q4 2012 | Successes Q1 2013 | Concerns Q1 2013 | Successes Q2 2013 | Concerns Q2 2013 | Successes Q3 2013 | Concerns Q3 2013 | Successes Q4 2013 | Concerns Q4 2013 | Successes Q1 2014 | Concerns Q12014 | Successes Q2 2014 | Concerns Q2 2014 | Successes Q3 2014 | Concerns Q3 2014 | Successes Q4 2014 | Concerns Q4 2014 | Successes Q1 2015 | Concerns Q1 2015 | Successes Q2 2015 | Concerns Q2 2015 | Successes Q3 2015 | Concerns Q3 2015 | Successes Q4 2015 | Concerns Q4 2015 | Successes Q1 2016 | Concerns Q1 2016
Daniala Bauer | Staged Rollout | * Setup pages to capture staged rollout status (UK reports) * Created automatic query of site versions * Continued to feed back on and review SR reports * Part of UK ROD team |  |  |  | * Continued to update 'UK status map' * Tracked progress and issues with 3.2 * Updated SR reports and added to SR. * Part of UK ROD team |  | * Continued to update 'UK status map' * Tracked progress and issues with EMI-2 WNs * Contributed to WN tarball testing/config * Part of UK ROD team | * SR contributions mainly London based | * Continued to update 'UK status map' * Tracked progress and issues with EMI-2 WNs * SR and monitoring pages modified for EMI-3 inclusion. * Part of UK ROD team | * SR contributions mainly London based. We need to engage more sites (e.g. T1). | * Part of UK ROD team * Contributing to EMI-3 staged rollout * Overseeing UK contributions to SR |  | * Part of UK ROD team * (Also acting as CMS contact) | * SR future a little unclear - perhaps focus on WLCG middleware readiness. | * Part of UK ROD team * (Also acting as CMS contact) | * Still no clear engagement with middleware readiness team. |  |  | * EMI-3 transition completed (supported monitoring of endpoints) * Followed up on reports to EGI staged rollout | * GridPP needs more involvement in the middleware readiness work. (Currently ECDF is a DPM test site). | * Now taking on responsibility within DIRAC development/deployment area. * UK ROD | * Need more UK involvement in SR. ECDF and QMUL joined the WLCG m/w readiness work. | * Good contribution to DIRAC progress. * UK ROD |  |  |  | * UK ROD * With Simon Fayer made good progress with modules for DIRAC. New DIRAC version installed. |  | * Focus has remained on DIRAC fixes and supporting new Vos. * UK ROD |  | * Continued work on DIRAC * UK ROD work |  | * Continued work on DIRAC * UK ROD work
David Crooks | Monitoring | * Produced a first interation of a ranked set of monitoring links. |  | * Likely to be moving part-time from October |  | * Little progress mainly due to Glasgow site issues. | * Unable to focus on task/going part time | * Developed temperature probe scripts | *Little progress with links due to part time status and lack of clear objectives in monitoring. | * Developed temperature probe scripts. Graphite presentation due to be given at HEPSYSMAN. Investigation into site nagios may also take place. | *Little progress with links due to part time status. | * Graphite presentation given at HEPSYSMAN * Developing more monitoring scripts (for Glasgow but to be shared) | * Need more participation in the WLCG monitoring coordination work. * Overlap with cloud implementations needs checking * Site Nagios report? | * N/b David returning to be full time. * Joined WLCG monitoring consolidatino group work. |  | * Contributing to monitoring consolidation work. * Reporting back on EGI operations meetings |  | * Further work and presentations on graphene dashboard - using graphite. |  | * Collected and contributed UK views to monitoring consolidation task force * Developed ipad monitoring for sites * Presented update * With Raul representing UK at EGI ops meetings | * Still need to look at site Nagios | * Continued in WLCG monitoring consolidation role. * Further monitoring improvements. |  | Comment: David will change his focus to cloud/VM security in 2015. This will be in support of such areas as job traceability. |  |  |  | * Progressed the cloud traceability work and spoke at pre-GDB |  | * Contributing to cloud traceability work in WLCG context.Leading on Security Operations Centre for UK. |  | * Various contributions to GridPP SoC. * Represented GridPP/UK in EGI ops meetings |  | * See below
Matt Doidge | Tickets & helpdesk | * Produces a useful weekly overview of UK GGUS tickets * Now following up on tickets and reviewing topics * Installed backup Nagios hardware at Lancaster |  |  |  | * Continued to conduct weekly review of GGUS tickets * Began updating/prodding tickets in addition to review * Starting involvement with WN tarball creation. |  | * Continued to conduct weekly review of GGUS tickets * Took charge of GridPP contribution to tarball WN | * Tarball work bringing additional support overhead. | * Continued to conduct weekly review of GGUS tickets * Took charge of GridPP contribution to tarball WN + UI.GGUS support unit for the tarball effort created. | * Tarball work bringing additional support overhead. | * Tarball WN integrated into CVMFS * Steady review of tickets | * Tarball WN with glexec support is proving difficult | * Steady review of tickets | * Tarball support for glexec stalled | * Steady review of tickets * Work on EMI-3 WN tarball | * Tarball support for glexec WN remains stalled | Continued maintenance of WN and UI tarballs * Weekly ticket reviews |  | * Continued maintenance of WN and UI tarballs * Weekly ticket reviews |  | * Continued ticket reviews - well received | * glexec tarball not available. | * Tickets reviews remain stready and informative. * Required UI/WN tarball updates produced quickly. | * glexec tarball not available. |  |  | * Participated in MW verification meeting. |  | * Continued to regularly review UK GGUS tickets and VO Nagios results. * Supported some WN tarball updates. * polished up the cvmfs UI in /cvmfs/grid.cern.ch |  | * Ticket updates * Maintained WN and UI updates. |  | * Ticket updates * Maintained WN and UI updates.
Alessandra Forti | Accounting/Security/Monitoring | * Worked on comparision of ATLAS accounting metrics * Forms part of the GridPP security team * Setup and maintained monitoring links page |  |  |  | * ATLAS monthly availability updates * Verified monitoring page accuracy (4 tickets) * Input to SL on accounting metrics * Contributing to GridPP security team * Participates in WLCG ops coordination team * Coordinating ATLAS WMI-2 WN testing for UK |  | * ATLAS monthly availability updates * Helped coordinate EMI-2 WN migration * Contributing to GridPP security team |  | * Helped coordinate EMI-2 WN migration and setup the plans for SL6 * Contributing to GridPP security team * Co-chair of the WLCG operations coordination team. |  | * Contributing to GridPP security team * Co-chair of the WLCG operations coordination team. * Continuing coordination of SL6 migration |  | * Very positive outcome from SL6 TF coordination within WLCG * Contributed to monitoring consolidation work |  | * Co-chair of the multi-core task force within WLCG operations coordination. * Active within ATLAS operations |  | * Significant contributions to the multi-core work in WLCG including leading the TF |  | * Continued lead on multi-core and batch system work. |  | * Guiding WLCG approach to multicore deployment and also now passing parameters to batch systems. * Taking role of security officer on shift. * Attending GridPP security meetings. |  | * Continued contributions to WLCG MC; security shifts and WLCG ops coordination. | Observation: Focus shifting more to ATLAS? |  |  | * Remains active in various WLCG areas. Contributed visibly to the WLCG workshop in Okinawa. |  | * Remains very active in WLCG ops coordination. * Working with ATLAS on several areas. * Lead for LSST work. |  | * Continued active support for LSST * Still active in WLCG ops coordination activities |  | * Support for LSST
Rob Harper | Security | * Contributing to GridPP security team |  |  |  | * Contributing to GridPP security team* |  | * Contributing to GridPP security team* |  | * Contributing to GridPP security team* |  | * Contributing to GridPP security team* | * Leaving in Q3. |  | * Rob left in Q3 and a replacement is not yet in place. Security team activities divided among existing team. * Accounting shared but no push on HEPSPEC06 updates or metrics checks |  | * Replacement being sought |  | * Post now vacant with move to Tier-1? | * Again contributing to the GridPP security team and surrounding activities (such as dashboard feedback). |  | * Taking role of security officer on shift. * Attending GridPP security meetings. |  | * Taking role of security officer on shift. * Attending GridPP security meetings. | [5 empty] | * Contributing to GridPP security team on-duty work. |  |  |  | * Attended security team meetings. Security on duty work.
Stephen Jones | Documentation | * Developed a tool to read VOMS information from ops portal and compare with siteinfo.def configuration * Reviewed wiki for obsolete documents * Set up site templates |  |  |  | * Reviewed GLUE 2.0 documents * Updated VOMSsnooper * Creation of stale documents tracker * Updated various documents |  | * Updated VOMSsnooper * Various document updates | * Stale document review not progressed | * Updated VOMSsnooper and presented via poster at EGI CF (April so Q2!) * Various document updates done * CertWizard concerns fed back and documents updated. * Old/stale document cull started. |  | * Some improvements to documents and associated processes improved. * Refined tools such as VOMSnooper | * Documents and overall dissemination (blogs and keydoc updates) not tended to regularly enough. | * VomsSnooper obeys VomsAdminServer flag * Documentation of process for backup voms adoption * Hardening of process for Approved VOs * Abstracts for VomsSnooper Plans: Docs: Certwizard use case; Adding New Vos document (slipped) * Develop Instant UI for new VOs or users | * GridPP blogs are generally not updated frequently. | * Produced instant UI * Tested several processes and reviewed associated documentation - e.g. VOMS moves | * GridPP blogs are generally not updated frequently. |  | * Lack of blog posts and site admin sharing of interesting solutions and progress. | * Maintenance of Vomssnooper * Various document follow-ups |  | * Support for instant UI at Brunel * Reviewed sections of wiki | [5 empty] | * Updated DrainBoss to new version 'Fallow' * |  | * Proactively tidying up documentation. * On holiday in July but lot of effort put into GridPP35 orginsation in August. |  | * Initiated reviews of GridPP user documentaiton * General document updates |  | * General documentation updates * HTC management control
Raul Lopes | Testing/middleware | * Active in testing EMI middleware releases |  |  |  | * Actively testing and advising on EMI-2 migration |  | * Set up SL6 queues * Working with Vos on SL6 porting tests |  | * Moved Brunel cluster to SL6 * Continuing work with Vos on SL6 porting and testing. |  | * Brunel at forefront of testing and deployment. One of the first sites at EMI-3 SL6. * Good contribution to staged rollout. |  | * Continued contribution to testing activities. |  | * IPv6 and middleware updates indicate still actively involved with deployment. |  | * Middleware testing |  | * Setup SLURM and ARC CE/HT Condor test systems * Continued support of experiment testing (especially CMS) * Looking at map reduce * With Davidl representing UK at EGI ops meetings |  | * Brunel local test cluster development | [5 empty] | * Participated in MW verification meetings. * Continued 'frontier' testing of components. Lookin at machine/job features implementations. |  | * Working with CMS verification team. * Investigating CentOS7 * test CA releases since version 1.68-1. I 've just accepted and installed 1.70-1 https://rt.egi.eu/rt/Ticket/Display.html?id=9911 - test of last two versions of squid frontier. Last one I believe it was in this quarter. - Test of ArcCE releases. In this quarter, ArcCE 5.03 - Test of latest DPM upgrades, including this week's 1.8.10-1 |  | * Further middleware testing * Participating to middleware readiness work. |  | * Further WLCG MW testing work
Ewan MacMahon | Security | * Contributing to GridPP security team * GridPP Nagios responsibilities |  |  |  | * Contributing to GridPP security team |  | * Contributing to GridPP security team * Contributing to xrootd/webdav |  | * Contributing to GridPP security team * Contributing to xrootd/webdav * Taking part in backup VOMS testing. |  | * Contributing to GridPP security team * Contributing to xrootd/webdav |  | * SSC6 review done and documents circulated. |  | * SSC6 review done and documents circulated. |  |  |  | * Contributing to the security team * Testing cloud implementation * Testing ARGUS rollout |  | * Helped debug DPM-ARGUS integration * Took lead on shellshock and perfSONAR follow-up effort in UK. * Deployed more services in IPv6 (e.g. UI) * Taking role of security officer on shift. * Attending GridPP security meetings. |  | * Welcome lead in UK response to several new security vulnerabilities and incident follow-up. * Taking role of security officer on shift. |  |  |  | * Good contributions to security team (leading work on ARGUS testing) |  | * Active member of the GridPP security team. |  | * Contributed to GridPP security team. |  | * Contributed to GridPP security team.
Andrew McNab | Documentation/webserver | * Setup KeyDocs system in wiki * Created secure wiki area * Developing document accuracy measures * Part of UK ROD team |  |  |  | " Created new online GridPP travel form * Keydocs review * Wiki update |  | " Keydocs updates |  | " Keydocs updates * Also now contributing to LHCb cloud testing and development of VAC approach. |  | * Contributing to UK ROD work * Maintaining webserver * Coordinating VAC work with LHCb | * GridPP site in need of update - will be done in conjunction with move to new hardware in September. | * Part of UK ROD team | * GridPP webserver has not yet migrated for SHA-2. Various delaying issues (e.g. with wiki php scripts). | * Part of UK ROD team * Actively working on VAC deployments | * GridPP webserver still not ready for SHA-2 | * Part of UK ROD team | * Migration of GridPP website (to ensure SHA-2 compatibility is ongoing) | * Part of UK ROD team * GridPP website migrated (needed workaround for blog - kept latest posts and archived older ones). * Further enhancement of VAC | * Keydocs tools problems - following website migration. | * Issues with keydocs php script fixed. * Continued rollout/support of VAC/vcycle and presented at several WLCG meetings. * UK ROD |  | * Part of UK ROD team * Worked with Tom on website replacement/upgrade. * Updating VAC tests/DIRAC monitoring |  |  |  | * Continued development of VAC and Vcycle. * Running Vac/Vcycle monitoring. * Support of additional Vos. |  | * Main focus has been on VAC/Vcycle developments (including accounting and monitoring improvements). * UK ROD |  | * Various VAC updates * GridPP website update/migration * UK ROD |  | * Various VAC updates * UK ROD
Mark Mitchell/Glasgow | Core services | * perfSonar planning |  | * Overloaded with non core task work |  |  | * Overloaded with non core task work |  | * Overloaded with non core task work | * Taking lead on Glasgow SL6 (and general testing) cluster. * Attending LHCOPN/LHCONE meetings for GridPP |  | * Attended various network meetings and contributing to HEPiX IPv6 and LHCONE discussions * Testbed work at Glasgow | [6 empty] | *Effort not replaced? |  | * Effort? |  |  | * Gordon Stewart arrived this quarter and will start taking on ScotGrid contribution to ROD in Q115
Kashif Mohammad | Regional tools | * Maintaining GridPP Nagios * Setup backup GridPP Nagios at Lancaster * Active in debugging monitoring issues * Part of UK ROD team * Tested VOMS replication |  |  |  | * Upgraded Nagios instances * Installed backup VOMS * * Part of UK ROD team |  | * Small VO tests brought into infrastructure * Part of UK ROD team |  | * Additional VO test work brought into infrastructure * Follow up of various Nagios issues. * Part of UK ROD team |  | * VO Nagios instances increased * Contributing to UK ROD team * Kept Nagios running |  | * Testing of new VOMS * upgrade of VOMS |  | * Both instances of Sam Nagios were upgraded to update 22. This update required reinstallation of the OS. * A new VO Nagios instance was started to monitor multiple VO's. https://vo-nagios.physics.ox.ac.uk/nagios/ * Currently monitoring five VO's: Gridpp,Pheno,Snoplus.snolab.ca,T2k.org, vo.southgrid.ac.uk * Part of UK ROD work |  | * Part of UK ROD team |  | * Part of UK ROD team * Nagios updates |  | * Added ARC CE tests to GridPP Nagios * Nagios upgrade. * UK ROD | [5 empty] | * UK ROD work * Maintaining nagios |  | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * UK ROD * Maintaining gridppnagios and VO Nagios
Stuart Purdie/ David Crooks/ Raul | Interoperation | * Attends the biweekly EGI ops meeting and reports back * Maintains knowledge of NGI/NGS VO activities * Part of UK ROD team |  |  |  | * Attends the biweekly EGI ops meeting and reports back * Part of UK ROD team |  | * Attends the biweekly EGI ops meeting and reports back * Part of UK ROD team | * Perhaps need more engagement with - DC cloud work - Post EMI engagement - JK took lead on NGS/VOMS changes | * Attended the biweekly EGI ops meeting and continued to feed back information. * Part of UK ROD team | * SP will leave the project in July/August. A plan for a seamless transition to a new staff member is being pursued. | * Attended the biweekly EGI ops meeting and continued to feed back information. * Part of UK ROD team | * Stuart left in June. Ops roles taken by David and Raul. Concern is speed of replacement. * Looking at T1 or other cover for the ROD role. |  | No replacement. However David covers the interoperation with EGI ops. |  | No replacement. However David covers the interoperation with EGI ops. | [10 empty] | * Attended meetings (only a few this quarter) |  | * David/Raul attending EGI meetings but the number has decreased. |  |  |  | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions
Duncan Rand | Perfsonar | * Proactive in interfacing with BNL perfSonar-PS * Investigating/following up network monitoring issues |  |  |  | * Added more perfsonar sites * Continued to create and track networking tickets related to PS results * Creation of CMS cloud in PS. |  | * UK/WLCG mesh testing * Tickets created to track traffic asymmetry problems | * Last sites without perfsonar remain unchanged | * Looked at perfsonar developments. | * Introduction of new mesh instance taking a while. | * Working with perfSONAR developers and dashboard maintainers. * Reviewing and reporting GridPP site issues related to PerfSONAR. |  | * Some follow up of perfSONAR issues * Icreased participation in IPv6 testing |  | * Good progress with IPv6 * Deployment of maddash dashboard |  |  |  | * Significant contributions to IPv6 testing * Follow-up on perfSONAR issues * Rep within LHCONE meeting |  | * Participation in network and metrics WG * Participation in IPv6 testbed | [7 empty] | * some perfSONAR |  |  |  | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE
Chris Walker | Wider Vos | * Created dynamic supported Vos page * Acts as ambassador to smaller VOs * Active in following up on smaller VO issues |  |  |  | * Gathered and presented other VO work at GridPP29 * Provided support for SNO+ and T2K * Pursuing smaller VO ganga integration work |  | * Working with small Vos to understand issues (mainly proxy related) * Warning and liasing with VOs over EMI-2 migration | * Need to develop DIRAC/Ganga submission route. | * Working with small Vos to understand issues (mainly proxy related) * Warning and liasing with VOs over SL6 migration |  | * Continuing to liase with non-LHC Vos. Seeing steady process. |  | * Continued push for adoption of back VOMSes by VOs * Helping (particularly) SNO+, T2K and cern@school with activities * Weekly review and push for smaller VO issue resolution across sites * Pushed wider webDAV use. |  | * Tracking VOMS migration * Championing smaller/other VO issues |  |  |  | * Active on behalf of several smaller Vos. * Undertaking Vos Quarterly Report |  | * Supported SNO+ work * HyperK |  |  | Chris moved to part-time in December 2014 and moves entirely to QMUL HPC in January 2015. A concern is that the valuable work he has done with other Vos will be disrupted as the task is redistributed (to Duncan and Daniela). The risk is somewhat mitigated now that Tom Whyntie is also working with other VOs along with the IC Dirac team.
Federico M | [21 empty] | * Started on Ganglia/Nagios/Observium/Dashing improvements at RALPPD |  | Will share then take over the monitoring tasks from David during Q1 15 |  |  |  | * Updated monitoring pages? |  |  | * "no progress to report about monitoring, and I am actually concerned...". We need to set some clearer tasks in this area if needed or have Frederico focus on something else.
General | General | * Information exchange via bulletin |  |  |  | * Several members now participating in WLCG operations coordination team work | * Some core ops tasks functioning better than others possibly due to more easily defined outputs/objectives. Will refocus in Q113 |  |  | * Core ops areas reviewed at GridPP30 with a generally positive view on progress and directions. | * Ops bulletin format in need of update (plan for summer). | * Some areas currently self-supporting but may need more oversight/direction - e.g. Recommendations for using puppet. * SSC6 write up done. | * Several team members leaving/moving. * Need to strengthen ROD team * DIRAC instance taking a while to commission * LHCb disk accounting changes unclear | * Contributing to various WLCG activities - with good engagement from sites following (e.g. IPv6 and multicore work). * Good UK joint working on puppet - need to find coordination fit? * Friday cloud discussion expanded to be a general "technical meeting". | * ROD team numbers still low. * Team is currently two people down and many people's effort is divided due to other activities | * Gareth Smith from tier-1 trained and joined the ROD work in December. | * Still waiting for team to be re-balanced by new staff. * Batch system issues increasing * | * Steady uptake of ARC-Ces and HT Condor | * Engagement with RIPE on ATLAS probes stalled. | * Sites showing good responsiveness to upgrade requests. * Janusz has enabled more Vos on DIRAC and fed back to developers on improvements/issues. * Good UK contribution to WLCG during quarter despite many upgrades and new resource deployments. | * Oxford identified growing issue with website pages being obsolete. Need to develop an update/replace strategy. * Accounting for clouds not entirely clear | * Some progress with DIRAC this quarter (e.g. with CERN@School usage) |  | * Plan for moving DIRAC to produciton in early 2015 supported. | [6 empty] | * "Ivan Reid is paid by core ops. He works for CMS@Home.". |  |  | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review!

## Narrative Q216
GridPP Quarterly Report
Area | Operations
Year | 2016
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * Additional resources brought online at several sites. * Good overall WLCG Tier-2 A/R results. Timely explanations given. |  |  |  |  | * EFDA-JET has signaled intent to decommission. * Birmingham has struggled with new DPM due to puppet configuration.
Vos | * Microboone jobs now running - e.g. at Lancaster * Dune now configured for Sheffield and set up in EGI portal. * CERN VM users workshop took place at RAL. Led to good (inter-)VO interactions. * Brunel now working on CMS@Home (is this an issue!?) * In May new Approved VOs published to include; icecube and fermilab * May summary of use-cases: CERN@school - LUCID (full workflow with DIRAC) GalDyn (full workflow with DIRAC) PRaVDA (full workflow with DIRAC) LSST (full workflow with Ganga + DIRAC) EUCLID (full workflow at the RAL T1) DiRAC (data storage/transfer) SNO+ (data transfer/networking) |  |  |  |  | * Progress is tracked monthly across the "incubator" Vos and things are progressing slowly.
Middleware/services | * SL7 feasibility tests progressing at several sites with good results (tarball preparation in parallel). For example Brunel is now running containered CentOS7 for CMS and RALPP has a CentOS7 ArcCE. * QMUL contributing to CREAM GPU submission development. Also testing cgroups on SLURM. * UCL VAC now working for ATLAS * *In April Oxford had a scheduled network warning so active nagios instance was moved from Oxford to Lancaster. |  |  |  |  | * Some sites missed SL5 deadline on storage nodes (but low risk). * WLCG diverging from EGI in areas like BDII usage. * perfSONAR issues continue at some sites (e.g. Sheffield awaiting firewall port opening).
Site infrastructure | * Bristol migrated from CREAM-CE WN to ARCE CE. |  |  |  |  | * Sites still in local discussions about IPv6 rollout plans (e.g. Liverpool)
Other | * Utilisation improved across all Tier-2s in this quarter. * Documentation produced on cgroups under Condor. * HEPSYSMAN meeting took place with security training day. * Increased involvement of GridPP staff with the HEPiX batch systems monitoring working group. * "New" EGI accounting portal available and gives improved results. * Averaged between 30 and 40 open tickets during period. * WLCG accounting task force created in May. * Various security advisories received good site responses (e.g. iperf3 in Perfosonar to Nova API for Openstack). * Contributions to new WLCG traceability and isolation working group. |  |  |  |  | * Incomplete Tier-2 reports (Northgrid narratives) * ROD team effort will be reduced as GS (Tier-1 contribution) moves to part-time working. * Some site tickets are put on-hold for long periods.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
The future of EMI is somewhat unclear and there is a growing indication that middleware will need to be more community/site supported. WLCG/sites may not be able to fill the gaps left by EMI ending. The risk reduced a little in Q1-13 with the creation of MEDIA to provide a loose collaboration post-EMI, but EGI indicated that funding from its community was going to reduce and a call for mini-project proposals to set priorities was made. In 2014 we have seen the HEP SW federation develop (especially in Q3) but the grid middleware component is unclear). The impact of this risk is decreasing as our sites have picked up other middleware stacks (e.g. ARC) and now also many provide a cloud offering. Additional adoption of ARC during Q1 & Q2 2015 reduces the risk further. - The ARGUS situation has improved in 2015 with the uptake of support by a group of WLCG sites. - Q3 2015: Risk is reducing as sites are increasingly adopting ARC-CEs and HTC. - Q4 2015 Risk continues to reduce. We should probably retire this risk from the ops report now and replace with one related to Centos7 (the different nature vs SL6 may lead to problems). |  |  |  |  | Stay engaged with WLCG discussions - particularly in post-TEG groups and at the GDB. Part of DPM community support. Respond to WLCG post-EMI middleware support proposal and look for ways to contribute (e.g. in tarball creation). Engage with the HEP SW federation. Play an active role in the middleware readiness verification work of WLCG. Support the work of the WLCG middleware readinees TF. ARGUS workshop took place in December with the outcome that a community support effort is being established. Further work has taken place within the ARGUS collaboration and the product looks to be adequately supported.
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams. Q414 - Durham continues with issues but has progressed testing
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Still no glexec tarball - situation continues beyond WLCG MB deadline for glexec enablement. Likely need to move to a workaround approach (i.e. give instructions on how to configure rather than provide an easy to install tarball). Q216 - Approach will be to provide insturctions for working around issue with tarball rather than providing a fully working install. |  |  |  |  | Keep WLCG MB/GDB aware of concerns and if possible work with WN developers to port a tarball version.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* Lancaster NAT may not cope with federated access demands |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.
Bristol unable to fix accounting issue (ARC CE -> JURA -> APEL) - which reports an order of magnitude smaller usage than is known. |  |  |  |  | Continue testing.
* A clear need for test resources or a multi-site testbed has been recognised but there are resource concerns. |  |  |  |  | State GridPP policy on accounting adjustments where production resources are used for testing and encourage reuse of old hardware (especially Tier-1 hardware).
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
SL5 nodes removed |  |  |  |  | 2016-06-30 |  | All monitored nodes >SL5.
Investigate the benefits of ARC-CE/HTCondor for other VO job submissions |  |  |  |  | 2016-06-30
Ramp up VAC deployments and VO usage of the resources so managed. |  |  |  |  | 2016-06-30 |  | More VAC jobs slots and more jobs running via this approach.
Review IPv6 status and ensure clear documentation is in place. |  |  |  |  | 2016-06-30 |  | Experience gained from sites already transitioned to IPv6 to be written up.
Newly procured hardware at Tier-2 sites commissioned and online. |  |  |  |  | 2016-06-30 |  | New kit installed (unstable kit removed?)
See Tier-2 reports for site specific objectives (e.g. RALPP new DPM headnode deployed, CentOS7 resources deployed, hardware installed...). |  |  |  |  | 2016-06-30
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
Complete testing of SL7/CentOS7 - install nodes (Liverpool/ECDF/Brunel) |  |  |  |  | 31/09/2016 |  | Reports produced for WLCG MWR group and one service node installed.
Review IPv6 status and ensure clear documentation is in place. |  |  |  |  | 2016-06-30 |  | Experience gained from sites already transitioned to IPv6 to be written up.
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken.
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation.
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities.
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed).
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available.

## Narrative Q316
GridPP Quarterly Report
Area | Operations
Year | 2016
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * ECDF now have a route to HPC resources via Openstack. * QMUL deployed GPU nodes. * Oxford progressing ATLAS diskless site option. * RALPPD swapped 2016 disk with older disk and moved from HW RAID to ZFS on JBOD. * Good overall WLCG availability |  |  |  |  | * Glasgow suffered downtimes due to power cuts, flooding and the installation of thermal control hardware not functioning as expected. * Oxford suffered from two air-con incidents. (12th August and 16th August) * ECDF removed their old SL6 cluster due to hardware issues. * ECDF utilisation issues due to SL7 not being fully supported by LHC Vos. * Manchester reported several disk failures in SEs and a WN motherboard.
Vos | * Icecube and LHCb are exploiting a prototype GPU service within grid jobs to run their existing GPU-dependent code at Manchester. * Durham deployed LFC for Pheno usage * Further VO enablements at additional sites - e.g. for vo.moedal.org and icecube. Progress with skatelescope.eu. * RPMs for VO records now available. * Manchester worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs. |  |  |  |  | * Ongoing issues at some sites with LHC Vos running on SL7. * Bristol engagement with SOLID experiment and medicine imaging ongoing but due in July.
Middleware/services | * ECDF use of Openstack resources for ATLAS SL6 analysis jobs. * Various successful tests at Glasgow in relation to MISP, WN via RPM and kubernetes. * Brunel developing IPv6-only WNS for testing in conjunction with LHC Vos (with D Rand) * QMUL supporting CREAM developers with GPU integration: https://wiki.egi.eu/wiki/GPGPU-CREAM * Various fixes to HTC/ARC provided during quarter (but some bugs remain affecting tests) |  |  |  |  | * Durham grid services have shown signs of scaling issues - mitigations implemented including new DPM servers.
Site infrastructure | * Many advances this quarter - Durham (new Vmware virtual host infrastructure; CE2, SLURM and Foreman moved to physical hardware, second SLURM server installed; rebuilt monitoring. * QMUL progressed SLURM deployment (now halfway). * RALPPD has a new top-level router which now allows policy based routing. |  |  |  |  | * Glasgow impacted by various physical events. New infrastructure expected August 2017. * Lancaster has uncovered an asymmetric routing problem. Now with JISC/JANET.
Other | * Site utilisation improved for many sites this quarter, particularly CPU utilisation (though Brunel dropped further?). * Various CHEP 2016 paper submissions and contributions to the event and WLCG workshop. * The EFDA-JET site was decommissioned without incident (though EGI did then flag it as having low availability!). * Old downtime notification system in WLCG/EGI decomissioned. |  |  |  |  | * Several Tier-2 reports were not fully completed and lacked site narratives or clear objectives for coming months. * The UK eScience CA suffered a database corruption in September which impacted certificates being issued over a few days. * GridPP Nagios decommissioned in July (now relying on central ARGO instance) but no VO Nagios replacement in sight.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams. Q414 - Durham continues with issues but has progressed testing
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Still no glexec tarball - situation continues beyond WLCG MB deadline for glexec enablement. Likely need to move to a workaround approach (i.e. give instructions on how to configure rather than provide an easy to install tarball). Q216 - Approach will be to provide insturctions for working around issue with tarball rather than providing a fully working install. |  |  |  |  | Keep WLCG MB/GDB aware of concerns and if possible work with WN developers to port a tarball version.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* VO NAGIOS is not supported beyond SL5 and ARGO development of similar functionality for regional use is not planned. |  |  |  |  | * Escalate concerns to EGI.
* Lancaster NAT may not cope with federated access demands |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.
* A clear need for test resources or a multi-site testbed has been recognised but there are resource concerns. |  |  |  |  | State GridPP policy on accounting adjustments where production resources are used for testing and encourage reuse of old hardware (especially Tier-1 hardware).
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
Investigate the benefits of ARC-CE/HTCondor for other VO job submissions |  |  |  |  | 2016-06-30
Ramp up VAC deployments and VO usage of the resources so managed. |  |  |  |  | 2016-06-30 |  | More VAC jobs slots and more jobs running via this approach.
Review IPv6 status and ensure clear documentation is in place. |  |  |  |  | 2016-06-30 |  | Experience gained from sites already transitioned to IPv6 to be written up. (Q316 - now part of next HEPSYSMAN) Q316 - IPv6 WNs and NAT64 demonstrated at QMUL. Lancaster finished preliminary tests as has Liverpool.
Complete testing of SL7/CentOS7 - install nodes (Liverpool/ECDF/Brunel) |  |  |  |  | 31/09/2016 |  | Reports produced for WLCG MWR group and one service node installed.
See Tier-2 reports for site specific objectives (e.g. Glasgow SOC WG contributions, openstack deployment at ECDF and Durham, IPv6 testing at Liverpool, new hardware deplpyed at various sites (e.g. Bristol and RALPPD), ...). |  |  |  |  | 2016-06-30
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
Continue testing of SL7/CentOS7 - install nodes (Liverpool/ECDF/Brunel) |  |  |  |  | 2016-12-31 |  | Reports produced for WLCG MWR group and one service node installed.Adoption documentation being prepared by Liverpool.
Review IPv6 status and ensure clear documentation is in place. |  |  |  |  | 2016-06-30 |  | Experience gained from sites already transitioned to IPv6 to be written up. Include in programme for sprint 2017 HEPSYSMAN.
Continue WLCG SOC work |  |  |  |  | 2016-12-31 |  | Prepare contribution to be presented at WLCG workshop - October 2016
Integration of DPM within puppet (move away from YAIM) |  |  |  |  | 2016-12-31 |  | Puppet install modules for DPM available.
See Tier-2 reports for site specific objectives (e.g. further tuning in ECDF, MISP for content sharing, ).
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK.
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS?
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7.
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October).

## EVAL
This page structure needs to be improved. Tier-2 reports record their individual contributions.
Q2 2015 + updates
Publications | Date | Notes
GridPP Preparing for Run-II | 2015-05-01 | Jeremy Coles - CHEP talk and paper
Dissemmination events | Date | Notes
GridPP developments and directions | 2015-04-01 | Jeremy Coles - talk at ISGC 2015
EVAL Notes Q1
Publications | Date | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine | 2012-10-15 | Followed from an interview with Pete Gronbech (Project Manager)
CHEP Publications | 2014-01-01 | A contributions from ScotGrid (3 paper from ECDF, 3 papers from Glasgow) accepted for publication
Collaborations | Date | Notes
Landslides |  | Bristol
CAMONT |  | Cambridge/Birmingham?
VoxTox/Accel-RT | starting 09/12 | Cambridge - investigating GRID techniques
CobeBase | Ongoing | Initial steps to collaboration with Startup company in ScotGrid
Neurogrid | Aug-sep 2012 | Completed setup of the VO. Still need to help them start using it.
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs. | 2015-09-01 | Manchester
LSST | Ongoing | Marcus Ebert 50% LUSC DAC Team.
HyperK | Ongoing | ECDF aiding in moving workloads to the Grid.
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST users to adapt their workflow to use grid resources | 2015-09-01 | Manchester
Further Funding (eg external grants) | Date | Notes
Robert Frank salary currently paid by the University of Manchester | 01/09/2012-31/12/2013
Destination of ex staff and recruitment issues | Date | Notes
Santanu Das - Cambridge Sys Admin | 2012-05-24 | Left to work for DataPipe, but then moved to the Financial Times.
Mark Mitchell | 2014-03-31 | Moved to University of Glasgow - Big Data for Urban Studies Institute
Dissemmination events | Date | Notes
Particle Physics Masterclass | 12-13/3/12 | P. Gronbech gave GridPP talk at Oxford
| 18-19/4/13 | P. Gronbech gave GridPP talk at Oxford | Q2?
International Symposium on Grids and Clouds, Taipei | 17-22/3/13 | UK e-Infrastructure talk by Jeremy Coles
Alessandra Forti presentations at: Atlas S&C week, WLCG Ops Planning, | 23/10/2013, 07/11/2013
Alessandra Forti presentations: "Multicore", 13/01/2014, Hepsysman, Birmingham "WLCG Multicore Task Force", 21/01/2014, Multicore Task Force meeting "Multicore Task Force", 11/02/2014, WLCG Ops Coordination F2F, CERN "Moving to BigPanDAmon", 27/02/2014, Atlas S&C week, CERN "ADC Monitoring", 28/02/2014, Atlas S&C week, CERN "Multicore", 25/03/2014, GridPP32 Pilotcry | 13/01/0214, 20/01/2014, 11/02/2014, 27/02/2014, 28/02/2014, 25/03/2014
Andrew McNab presentations: | 24/02/2014, 25/03/2014
“LHCb T2-D Update”, 24 Feb 2014, LHCb National Computing Board, CERN.
"Running real jobs in virtual machines”, 25 Mar 2014, GridPP32, Pitlochry.
Monitoring presentation at UK HEPSYSMAN event | 2014-06-03 | Given by Dave Crooks
Invited talk on HPC at Atlas Software Week | 2014-06-04 | Given by Andrew Washbrook
Invited Talk at WLCG Monitoring Consolidation Meeting | 2014-07-04 | Given by Dave Crooks
OpenMP Tutorial for Atlas Computing | 2014-09-12 | Given by Andrew Washbrook
UKI-LT2-Brunel: GPU 2014 workshop | August 2014 reg | https://agenda.infn.it/conferenceDisplay.py?confId=7534
Invited Talk at Atlas ADC meeting (cgroups) | 2014-11-24 | Gang Qin
Invited Talk at Atlas Jamboree (cgroups) | 2014-12-04 | Gang Qin
HPC(Archer) update at the ATLAS HPC meeting | 2014-12-10 | Andrew Washbrook
DPM Workshop - Naples | 2014-10-09 | Wahid Bhimji
ATLAS S&C week (ADC shifter Feedback) | 2014-12-04 | Wahid Bhimji
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Alessandra is one of the GridPP representatives in the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; SL6 TF leader ends this quarter; Multicore TF leader starts this quarter. | 01/10/2013-31/12/2013; 01/10/2013-31/10/2013; 01/12/2013-31/12/2013 | Joint-Chair WLCG Operations Coordination Team
Pete Gronbech | Current | Chairman HEPSYSMAN
Jeremy Coles | Current | Member - EGI Operations Management Board
Jeremy Coles | Current | UK member - WLCG Grid Deployment Board
WLCG Monitoring Consolidation working Group | Present | Attended by David Crooks
Chair of WLCG Storage Evolution Group W. Bhimji | Present | UK Data Storage
Member of Scientific Programme Comittee and Convenor of the "Data Stores, Data Bases, and Storage Systems" track for CHEP 2013 | Present | CHEP 2013
UK Members of DPM Collaboration | Present | UK Data Storage (W. Bhimji & S. Skipsey)
Active members of Multi-core taskforce (representing Scotgrid distributed Tier 2) | Present | Attended by S. Skipsey
WLCG Traceability & Isolation WG | Present | David Crooks
SOC Working Group | Present | co-lead by David Crooks
UK Members of DPM Collaboration | Present | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group | Present | S. Skipsey
Member of Tier-2 Evolution Working Group | Present | S.Skipsey
ATLAS Software Quality Coordinator | Present | Andrew Washbrook
Andrew McNab is the Deputy LHCb Computing Coordinator. He is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group and leading the GridPP Tier-2 Evolution project. He is leader of the WLCG "Machine Features” task force, and a member of the "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces, and the Grid Deployment Board steering group.
Jeremy Coles | Current | UK NGI Management Board
Other outputs and Knowledge | Date | Notes
Pete Gronbech | 2013-12-06 | GridPP talk at the IATUL Workshop
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG
CentOS7 progress at the ATLAS ADC weekly 14/09/2016 Update on ATLAS benchmark | 2016-08-16 | A Forti.
TO be merged
Publications | Date | Notes
Glasgow EGI (3) | 08/04//2013 | Papers at EGI Community Forum
CHEP |  | Papers to student Societies
Glasgow CHEP (4) | 2013-03-30 | Paper Submission
UKI-LT2-Brunel: GPU 2014 workshop | 2014-12-31 | https://agenda.infn.it/conferenceDisplay.py?confId=7534
ECDF CHEP (2) | 2013-03-30 | Paper Submission
Collaborations | Date | Notes
EMC Data transfer programme | Ongoing | Support for commercial academic FP7 Grant
TechCube installation of a new cluster |  | ScotGrid
ECDF Big data Workshop ECDF | Ongoing
Further Funding (eg external grants) | Date | Notes
Manchester - Extra data server purchased by the University | 2013-06-01
Destination of ex staff and recruitment issues | Date | Notes
Mike Johnson | 2013-12-31 | Moved to William Hill as a systems Admin. Safe bet. :-)
Dissemmination events | Date | Notes
Glasgow Public Outreach (2) | 09/04//2012 | Papers to student Societies
MEW24 | 2013-11-27 | M Mitchell presented on behalf of LAN3 regarding network equipment
Manchester (Alessandra Forti): presentations at: WLCG Monitoring Consolidation; ADC weekly; GDB; ADC weekly; WLCG Monitoring Consolidation | 05/07/2013, 16/07/2013, 11/09/2012, 17/09/2013, 26/09/2013
Andrew: presentations at: pre-GDB, CERN; LHCb National Computing Board meeting, Krakow; EGI Technical Forum, Madrid; GridPP31, Imperia | 09/07/2013, 11/09/2013, 16-20/09/2013, 24/09/2013
Cloud and virtualisation workshop | 2013-07-01
Manchester/NorthGrid: EGI community forum (three posters: VOMS, perfSonar monitoring and LHCb usage of the Tier2). Presentations at the GDB: WLCG Ops Coord summary report, Atlas S&C: SL6 status report, French perfsonar day: WLCG requirements | 08-12/04/2013, 10/6/2013, 11/6/2013, 04/04/2013
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
N/A
Roles held on committees and boards | Date | Notes
HEPIX IPv6 M.Mitchell | Present | Global Network Group
Monitoring consolidation group - David Crooks | Present
LHCONE M.Mitchell | until Q1 2014 | Global Network Group
Member of SQUID Monitoring TF | Present | David Crooks
UK Members of DPM Collaboration | Present | UK Data Storage (W. Bhimji & S. Skipsey)
Active members of Multi-core taskforce (representing Scotgrid distributed Tier 2) | Present | Attended by S. Skipsey
Chair of WLCG Stroage Evolution Group W. Bhimji | Present | UK Data Storage
Alessandra Forti | Current | GridPP representative in the WLCG Ops Coordination, SL6 TF leader, Atlas monitoring coordinator and member of the atlas distributed computing coordination
Alessandra is one of the GridPP representatives in the WLCG Ops Coordination, SL6 TF leader, Atlas monitoring coordinator and member of the atlas distributed computing coordination | 01/07/2013-31/03/2014
Andrew is deputy leader of the GridPP technical group, the LHCb Tier-2 co-ordinator, a Grid Expert On Call member of the LHCb distributed computing team, and a member of the WLCG Machine features task force | 01/07/2013-31/03/2014
Pete Gronbech | Current | Chairman HEPSYSMAN
Jeremy Coles | Current | Member - EGI Operations Management Board
Jeremy Coles | Current | UK member - WLCG Grid Deployment Board
Jeremy Coles | Current | UK NGI Management Board
Member of Scientific Programme Comittee and Convenor of the "Data Stores, Data Bases, and Storage Systems" track for CHEP 2013 | Present | CHEP 2013
Other outputs and Knowledge | Date | Notes
Glasgow Impact | 2013-05-01 | Press Release Completed
Good engagement with High Performance Networking Special Interest Group meeting | 2013-07-01
TO be merged
Collaborations | Date | Notes
Manchester: Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs. | Q415
Dissemmination events | Date | Notes
Alessandra Forti chaired session on opportunistic resources at the ATLAS TIM https://indico.cern.ch/event/437170/timetable/#all.detaile | 2015-12-02
Andrew McNab presentations: “Batch and Cloud overview”, UK-T0 kickoff meeting, 20 Oct 2015. “LHCb infosystem plans” and “Publishing GLUE2 in JSON”, WLCG Information System Task Force meeting, 12 Nov 2015. | 20/10/2015 and 12/11/15
TO be merged
Publications | Date | Notes
Collaborations | Date | Notes
Manchester worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST users to adapt their workflow to use grid resources
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Gang Qin - Sussex University | 2016-04-01 | Gang has moved to Sussex as the Grid admin there.
Dissemmination events | Date | Notes
Alessandra Forti: - Organised Ganga Tutorial and HEPsysman in Manchester 14-15/1/2016 - HEPsysman, WLCG workshop: Info sys, accounting, benchmarking 15/1/2016 - ATLAS Jamboree, chair of the Infrastructure and sites recommendation 27-29/1/2016 - ATLAS Jamboree, "On memory and batch systems", 27/1/2016 - WLCG workshop, chair of the Info sys, accounting, benchmarking session, 1/2/2016 - WLCG workshop, session introduction, 1/2/2016 - WLCG workshop, session Summary, 3/2/2016 - ATLAS S&C week, "WLCG workshop and jamboree summaries", 1/3/2016 | 14-15/01/2016 27-29/01/2016 01/02/2016 03/02/2016 01/03/2016
GDB | 2016-03-07 | David Crooks - Security Operations Centre Update (with Liviu Valsan)
Andrew McNab presentations: “Cloud use by LHCb”, CC-IN2P3 Annual Meeting, Lyon, 9 Feb 2016. “Vacuum platform”, EGI Operations Management Board, 25 Feb 2016. “LHCb Operations Report”, LHCb National Computing Board, 7 Mar 2016. | 09/02/2016 25/02/2016 07/03/2016
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Alessandra is one of the GridPP representatives and one of the co-chairs of the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; Multicore TF co-leader; WLCG workshop 2016 planning committee.
Andrew is the Deputy LHCb Computing Coordinator and LHCb Distributed Computing and Operations Coordinator. He is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group and leading the GridPP Tier-2 Evolution project. He is leader of the WLCG "Machine Features” task force, and a member of the "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces.
Other outputs and Knowledge | Date | Notes