## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Experiment Support |  |  | Close to target
Year | 2017 |  |  | Not OK
Reported by | Pete Gronbech |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Q416 | Q117 | Comment Q116 | Comment Q216 | Comment Q316 | Comment Q416 | Comment Q416
3.4.6 | ATLAS reporting to T1 expt Liaison and resource meetings | Roger Jones | Pete Gronbech | ATLAS support check | yes | [7 empty] | Meeting held 7.12.16 | Meeting held 22.3.17
3.4.7 | CMS reporting to T1 expt Liaison and resource meetings | Dave Colling | Pete Gronbech | CMS support check | yes | [7 empty] | Meeting held 7.12.16 | Meeting held 22.3.17
3.4.8 | LHCb reporting to T1 expt Liaison and resource meetings | Resource Review minutes | Pete Gronbech | 3 out of 4 meetings/ year | yes | [7 empty] | Meeting held 7.12.16 | Meeting held 22.3.17
3.4.9 | Unit testing of code within area of responsibility | Report from Ulrik | Ulrik Egede | Coverage of over 75% of code | OK |  | OK |  |  |  | Continuous testing is now functional. Old release tests are now almost fully migrated. |  | No longer Funded | No longer Funded
3.4.10 | Provide new releases of Ganga | Report from Ulrik | Mark Smith | A new minor release at least every 6 weeks | OK |  | OK |  |  |  | Release manager duties are in the process of transferring from Matt Williams to Mark Smith | Releases are working as expected. | No longer Funded | No longer Funded
3.4.11 | Support provided for new user communities | Report from Ulrik | Rob Currie | Have a turn-around time of less than 1 month for a prototype | OK |  | OK |  |  |  | LSST have a functional prototype now and LZ integration has started. | There has been further work on an LZ prototype that interacts with their production database. | No longer Funded | No longer Funded
3.4.12 | Number of new user groups using the T1/UK Grid | T1 and T2 accounting. Email requests, etc | Pete Gronbech | >1 per year | [5 empty] | Support given to SNO+ to enable data transfers using grid ftp. Support dialogue with SuperNemo established, but now stalled due to lack of time on their part.
3.4.13 | Summary of Work done by support posts | Dan Proropopescu quarterly report | Pete Gronbech | [6 empty] | Not funded this quarter. | Not funded this quarter. | Not funded this quarter. | Not funded this quarter. | Not funded this quarter.
3.4.14 | Summary of Work done by support posts | Janusz Martyniak quarterly report | Pete Gronbech | [6 empty] | Na62 and MICE: moving the file transfer controller to a Centos 6 node, updating the API, ongoing MICE: - work on Configuration DB - Coolingchannel C-API for absorbers (also Java and Python), installation of the new in the Control Room. - work on Detector quality flags implementation for the CDB - ongoing (C, Java, Python) - geometry corrections API, java and Python - ongoing - updates of the raw data mover and a reco mover, maintenance during data taking. | Na62: Finalising the File Transfer Controller for NA62 data transfer. Testing GridPP Dirac asynchronous file transfers. Work on a simple file transfer visualisation. MICE: - work on Configuration DB - cooling channel and absorber C API installed in the Control Room and used during summer data taking. - geometry corrections API - first version ready for testing on the preproduction DB - Work on detector cabling and calibration CDB module - client-side C++ API to facilitate its use in MAUS reconstruction and analysis software. CHEP 2016 oral presentation on CDB - updated the reach mover to use hardware dongle for certificate maintenance - CHEP2016 poster | MICE: - detector geometry API for the CDB released and installed on the DB server - Run Control system which used the C API successfully tested during runs in September, - updated CDB viewer installed - display the cooling channel absorber settings added, - C++ API to be used in MAUS reconstruction software released, - review and retrofit some DB data which were incorrectly stored by the Run Control system. NA62 - maintenance of the data moving system (File Transfer Controller) | MICE: - Another modification of the CDB C-API for the cooling channel and absorber Web Services - Installation of State Machine C-API started - Minor correction to the CDB Viewer (target parameters added) - Work on installation of C++ API in MAUS analysis software - ongoing - work on a new version of the RAW data mover for Feb/March ’17 run. NA62: - maintenance of the data moving system (File Transfer Controller) | MICE: - Completed installation of the CDB C-API for the cooling channel, absorber and state machine Web Services - Minor correction to the CDB Viewer - C++ CDB API released and installed in MAUS analysis software - Work on CDB geometry API update started - CHEP 2016 paper preparation and submission NA62: - maintenance of the data moving system (File Transfer Controller)

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Experiment Support |  |  | Overdue
Quarter | 2017 |  |  | Not yet due
Reported by | Pete Gronbech |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
| Modernise test suite | Rob Currie | 2015-11-01 | 2016-03-01 | The continuous testing is running on all pull requests | There is still a few legacy tests running but they are by now marginal compared to the new test system.
| Migration to Cmake for LHCb | Rob Currie | 2016-01-01 |  |  | Has been delayed by increasing support for other VOs
| Updated authentication system | Matt Williams | 2016-04-01 |  |  | Has been delayed by taking over the milestone for Jenkins and the milestone on updating the lock system.
| Implement new lock system for multi-thereaded operation |  | 2016-04-01 | 2016-03-01 | Much fewer user support issues related to the job monitoring getting into deadlock situations. | Very much a collective responsibility by everybody involved.
| Improve scalability of submissions to Dirac backend | Rob Currie | 2016-06-01 | 2016-06-01 | The submission time of subjobs has gone from about 10s per job to 3 s per job.
| Provide support for IgangaFile objects everywhere in the sytem | Rob Currie | 2016-08-01 |  | This is complete with the 6.2 series of Ganga.
| Prototype of support for production system of LZ | Alex Richards | 2016-09-01 |  | The prototype that is talking to the LZ production database has been completed.
| Prototype for LSST analysis | Rob Currie | 2016-06-01 | 2016-05-01 | The use of this was reported as a success in a report submitted to the UKT0 working group.

## Manpower Q116
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016Q1
Reported by | Pete Gronbech
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards |  |  |  | 0.1 | 0.1 | 0.1
Imperial | Ganga | Ulrik Egede |  |  |  | 0.1 | 0.1 | 0.1
Imperial | Ganga | Rob Currie | 0.5 | 0.5 | 0.5
Imperial | Ganga | Patrick Owen |  |  |  | 0.1 | 0.1 | 0.1
Birmingham | ATLAS Ganga | Mark Slater |  |  |  | 0.2 | 0.2 | 0.2
Birmingham | Ganga | Matt Williams | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak
Liverpool | Ganga | Rob Fay
Total |  |  | 1 | 1 | 1 | 0.5 | 0.5 | 0.5

## Manpower Q216
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Pete Gronbech
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards |  |  |  | 0.1 | 0.1 | 0.2
Imperial | Ganga | Ulrik Egede |  |  |  | 0.1 | 0.1 | 0.1
Imperial | Ganga | Rob Currie | 1 | 1 | 1
Imperial | Ganga | Mark Smith | [5 empty] | 0.2
Glasgow | User Support | Dan Proropopescu | 0 | 0 | 0
Imperial | User Support | Janus Martyniak | 0.5 | 0.5 | 0.5
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0.2 | 0.2 | 0.5

## Manpower Q316
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Pete Gronbech
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards |  |  |  | 0.1 | 0.1 | 0.1
Imperial | Ganga | Ulrik Egede |  |  |  | 0.1 | 0.1 | 0.1
Imperial | Ganga | Rob Currie | 1 | 1 | 1
Imperial | Ganga | Mark Smith |  |  |  | 0.2 | 0.2 | 0.2
Glasgow | User Support | Dan Proropopescu
Imperial | User Support | Janus Martyniak | 0.5 | 0.5 | 0.5
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0.4 | 0.4 | 0.4

## Manpower Q416
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Pete Gronbech
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu
Imperial | User Support | Janus Martyniak | 0.5 | 0.5 | 0.5
Liverpool | Ganga | Rob Fay
Total |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0

## Manpower Q117
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Pete Gronbech
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu
Imperial | User Support | Janus Martyniak | 0.5 | 0.5 | 0.5
Liverpool | Ganga | Rob Fay
Total |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0

## Narrative Q116
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016 Q1
Reported by | Pete Gronbech
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas | Helped make Ganga properly thread safe and significantly more stable. Got pure python usage working. |  | Had significant stability issues due to Ganga not being properly thread safe.
GangaLHCb | Improving of the overall scaling of Ganga to support users with more jobs. |  | The delay of support for the new Cmake type code builds in LHCb is causing some issues for users.
GangaCore | Work on future proofing the code and making it fully Python 3 compliant. New types of use cases are also supported now where ganga is simply imported into an existing python session. |  | The continued quest for making Ganga work faster and scale to ever larger number of jobs revealed some serious limitations in how job objects were locked by different threads. It took quite a while to the button of these problems and a few milestones has been delayed due to this.
Ganga other | Proof of concept of running LSST style jobs on the Grid using Ganga as the user interface to Dirac has been a success. Work has now started on building a prototype that can illustrate the power of a closer integration. In addition discussions are beginning on how LZ can be supported.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Reduced support in the future will lead to code that is not maintained. |  | Implement changes that will reduce the maintenance burden. This will not work though if support team goes below a critical mass.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Make the transition to become a generic tool for submitting all kind of science jobs via the Dirac portal.
ian

## Narrative Q216
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016 Q2
Reported by | Pete Gronbech
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas
GangaLHCb | The improvement in interaction with DIRAC from the Core of Ganga has dramatically improved many issues for LHCb. The LHCb users as the most heavy users have also continued to expose issues related to scalability of the full system. |  | Lack of manpower has limited many developments. The introduction of Mark Smith into the team will improve on this for the next quarter.
GangaCore | Many performance improvements has taken place to support the scalability of Ganga for the future. In particular this has been related to the submission and monitoring of jobs in Dirac.
Ganga other | The support of new teams coming in has been a success. A prototype for LSST was created and subsequently used in anger. For T2K an update of the codebase was integrated. For LZ there is progress on providing a prototype of their web based production system that is using Ganga as a backend for submission to DIRAC.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of Matt Williams from the project at the end of the summer and potentially Rob Currie as well will leave the project more or less dormant in terms of new developments. The support of new communities will also be impossible. |  | Find new manpower.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
ian

## Narrative Q316
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016 Q3
Reported by | Pete Gronbech
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas
GangaLHCb | The transition to the 6.2 releases for LHCb has been smooth. This release supports the new version of the LHCb software framework and thus represents a significant change for users. The solid testing of all code meant that the introduction was very smooth with only a few minor bugs uncovered.
GangaCore | The Ganga core is in a very stable state and most effort has been spent on consolidation as there essentially is no effort to devote to it in the forseeable future. |  | Essentially zero effort available for developing the core in the future. The final trance of developments in the core is the introduction of better support of multiple proxies. This will now be overseen by Mark Smith that was not involved in the development himself and thus represents a minor risk if trouble shows up.
Ganga other | The prototype work to support LZ has continued. Some initial contacts have been established with SKA on possible use of Ganga. |  | With the departure of both Matt Williams and Rob Currie, there is no dedicated effort available to support new experiments. They will have to bring in their own effort now.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
There is no longer any funding for Ganga from GridPP so no longer any objectives/deliverables in that direction.

## Narrative Q416
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016 Q4
Reported by | Pete Gronbech
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
There is no longer any funding for Ganga from GridPP so no longer any objectives/deliverables in that direction.

## Narrative Q117
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2017 Q1
Reported by | Pete Gronbech
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
There is no longer any funding for Ganga from GridPP so no longer any objectives/deliverables in that direction. |  |  |  | New user engaement Officer post may be able to contribute to supporting Ganga at a low level.

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Alex Richards | 2013-04-01 | Went to an STFC core funded computing position at Imperial
Matt Williams | 2016-09-30 | went to Bristol, I *think* on an Research Engineer UK grant with some Computational Biology group
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes