## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | LHCb |  |  | Close to target
Year | 2016 |  |  | Not OK
Reported by | Andrew McNab |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q316 | Q416 | Comment Q316 | Comment Q416
1.7.1 | RAL prod success rate |  | Andrew McNab | 90% | 95.4% | 98.5%
1.7.2 | RAL prod CPU efficiency |  | Andrew McNab | 90% | 95.9% | 95.2%
1.7.3 | RAL user success rate |  | Andrew McNab | 50% | 81.4% | 84.8%
1.7.4 | RAL user CPU efficiency |  | Andrew McNab | 70% | 94.7 | 91.4
1.7.5 | UK Tier-1 work fraction |  | Andrew McNab | 15% | 26.9% | 30%
1.7.6 | UK T1 SE Reliability |  | Andrew McNab | lost files target 0, diskservers down over 8 hours, target < 3 | 20 3 | 0 7 | Noticeable increase in lost files due to crashes of disk servers.
1.7.7 | LHCb No. of sites below WLCG SAM tests uptime target |  |  | <2 | 0 | 0
2.3.1 | Tier-2A : User success rate |  | Andrew McNab | >50% | 85.9 | 83.7
2.3.2 | Tier-2A : User CPU efficiency |  | Andrew McNab | 70% | 90.1 | 88
2.3.3 | All Tier-2: Simulation success rate |  | Andrew McNab | 90% | 92.2% | 91.2%
2.3.4 | All Tier-2: Simulation CPU efficiency |  | Andrew McNab | 90% | 98.2% | 98.0
2.3.5 | UK Tier-2 work fraction |  | Andrew McNab | 15% | 29.5% | 22.2
Note on B19: Imported Author: Where “walltime work” is the walltime recorded by DIRAC, multiplied by the CPU power of the job slot in units of HEPSPEC06 as recorded by DIRAC (either by the DIRAC Benchmark or from the JOBFEATURES mechanism.)
Note on B21: Imported Author: gronbech: how do we measure this

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | LHCb |  |  | Overdue
Quarter | 2016 |  |  | Not yet due
Reported by | Andrew McNab |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.7.7 | Report to PMB on delivery during year | Andrew McNab | 2016-12-31 | 2016-12-01 | oc docs | OC Docs and review SS
1.7.8 | Report to PMB on delivery during year | Andrew McNab | 2017-12-31 |  | oc docs
1.7.9 | Report to PMB on delivery during year | Andrew McNab | 2018-12-31 |  | oc docs
1.7.10 | Report to PMB on delivery during year | Andrew McNab | 2019-12-31 |  | oc docs

## Manpower Q116
GridPP Quarterly Report
Area | LHCb
Quarter | 2016
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Manpower Q216
GridPP Quarterly Report
Area | LHCb
Quarter | 2016
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q316
GridPP Quarterly Report
Area | LHCb
Quarter | 2016
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Manpower Q416
GridPP Quarterly Report
Area | LHCb
Quarter | 2016
Reported by | Andrew McNab
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | LHCb T1/T2 support | Raja Nandakumar | bar: GridPP Funded Month 1 to GridPP Funded Month 3
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0

## Narrative Q116
GridPP Quarterly Report
Area | LHCb
Quarter | Q116
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth running during the stripping campaign and for user analysis jobs.
Tier-2 | User jobs at T2-D sites accessing data placed there. QMUL added as a 4th UK T2-D site for LHCb.
Raja Nadakumar | GEOC shifts and expert LHCb liaison with Tier-1
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only (Ceph-fs) storage technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q216
GridPP Quarterly Report
Area | LHCb
Quarter | Q216
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth running during the stripping campaigns and for user analysis jobs.
Tier-2 | User jobs at T2-D sites accessing data placed there. Liverpool added as a 5th UK T2-D site for LHCb.
Raja Nadakumar | GEOC shifts and expert LHCb liaison with Tier-1
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only (Ceph-fs) storage technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q316
GridPP Quarterly Report
Area | LHCb
Quarter | Q316
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth running during the stripping campaigns and for user analysis jobs.
Tier-2 | User jobs at T2-D sites accessing data placed there. Glasgow added as a 6th UK Tier-2 site with Storage for LHCb.
Raja Nadakumar | GEOC shifts and expert LHCb liaison with Tier-1
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only cloud storage (Echo) technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage. LHCb data management is tracking developments of Echo with other experiments.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q416
GridPP Quarterly Report
Area | LHCb
Quarter | Q416
Reported by | Andrew McNab
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Tier-1 | Smooth running during the stripping campaigns and for user analysis jobs.
Tier-2 | User jobs at T2-D sites accessing data placed there.
Raja Nadakumar | GEOC shifts and expert LHCb liaison with Tier-1. Helping to co-ordinate Castor to Echo transition for LHCb.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Deployment of the disk-only cloud storage (Echo) technology at Tier-1. |  | Production Castor service is continuing support for disk-only storage. LHCb data management has begun testing with Echo and planning how to support it within LHCb DIRAC.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes