## Dissemination Metrics
4.3 | Outreach & Engagement Metrics
Number | Title
4.3.1 | Number of events GridPP attends with stand/posters/talks
Metric | Four per year
Source | Dissemination officer
4.3.2 | Number of GridPP publications
Metric | 10 per year
Source | Dissemination officer
4.3.3 | Number of articles on GridPP web site
Metric | One every 2 weeks
Source | Dissemination officer
4.3.4 | Number of GridPP press releases
Metric | 1 per year
Source | Dissemination officer
4.3.5 | Number of press articles about GridPP
Metric | 5 per year
Source | Dissemination officer
4.3.6 | Number of KE exploration meetings held
Metric | 1 per year
Source | Dissemination officer
4.3.7 | Number of non-GridPP funded Groups who use GridPP hardware
Metric | 10
Source | Dissemination officer
4.3.8 | KE sections of GridPP website updated
Milestone | 31st Dec 2016
Source | Dissemination officer
4.3.9 | KE sections of GridPP website updated
Milestone | 31st Dec 2017
Source | Dissemination officer
4.3.10 | KE sections of GridPP website updated
Milestone | 31st Dec 2018
Source | Dissemination officer
4.3.11 | KE sections of GridPP website updated
Milestone | 31st Dec 2019
Source | Dissemination officer

## 4.3.1
4.3.1 | Number of events GridPP attends with stand/posters/talks
Target | Four per year
Target Per Quarter | 1 | Passed
Q1 2016 | 2 | Yes
Q2 2016 | 2 | Yes
Q3 2016
Q4 2016
Q1 2017
Q2 2017
Q3 2017
Q4 2017
Q1 2018
Q2 2018
Q3 2018
Q4 2018
Q1 2019
Q2 2019
Q3 2019
Q4 2019
Q1 2020
Final Total | 4 | Yes
Count | Event | Date
Q1 - January 2016 to March 2016
1 | Ganga workshop - HEP SYSMAN January 2016 |  | http://indico.cern.ch/event/465558/
1 | WLCG Workshop
Total for this quarter |  | 2
Q2 - April 2016 to June 2016
1 | CernVM Users Workshop, RAL, June 2016 |  | https://indico.cern.ch/event/469775/
1 | HEPSYSMAN with Security training June 2016
Total for this quarter |  | 2
Q3 - July 2016 to September 2016
0
Total for this quarter |  | 0
Q4 - October 2016 to December 2016
1 | HEPSYSMAN at QMUL
Total for this quarter |  | 1

## 4.3.2
4.3.2 | Number of GridPP publications | http://www.gridpp.ac.uk/papers/
Target | 10 per year
Target Per Quarter | 2.5 | Passed
Q1 2016 | 1 | No
Q2 2016 | 1 | No
Q3 2016 | 1 | No
Q4 2016 | 1 | No
Q1 2017 |  | No
Q2 2017 |  | No
Q3 2017 |  | No
Q4 2017 |  | No
Q1 2018 |  | No
Q2 2018 |  | No
Q3 2018 |  | No
Q4 2018 |  | No
Q1 2019 |  | No
Q2 2019 |  | No
Q3 2019 |  | No
Q4 2019 |  | No
Q1 2020
Final Total | 4 | No
Count | Event | Date
Q1 - January 2016 to March 2016
1 | Applications |  | http://dx.doi.org/10.1080/10619127.2015.1104132
Total for this quarter |  | 1
Q2 - April 2016 to June 2016
1 | Applications |  | http://dx.doi.org/10.1016/j.nuclphysbps.2015.09.202
Total for this quarter |  | 1
Q3 - July 2016 to September 2016
1 | Applications |  | https://arxiv.org/abs/1607.01749
1 | Applications |  | http://dx.doi.org/10.1088/1674-1137/40/1/011001
Total for this quarter |  | 1
Q4 - October 2016 to December 2016
1 | Applications (QCD) |  | http://dx.doi.org/10.1007/JHEP11(2016)094
Total for this quarter |  | 1 | Note - CHEP 2016 was late this year, so assuming the proceedings are published in Q1/Q2 targets should be met

## 4.3.3
4.3.3 | Number of articles on GridPP web site | http://www.gridpp.ac.uk/news/?page_id=504 (News Items)
Target | One every 2 weeks
Target Per Quarter | 6 | Passed
Q1 2016 | 2 | No
Q2 2016 | 8 | Yes
Q3 2016 | 4 | No
Q4 2016 | 5 | No
Q1 2017 |  | No
Q2 2017 |  | No
Q3 2017 |  | No
Q4 2017 |  | No
Q1 2018 |  | No
Q2 2018 |  | No
Q3 2018 |  | No
Q4 2018 |  | No
Q1 2019 |  | No
Q2 2019 |  | No
Q3 2019 |  | No
Q4 2019 |  | No
Q1 2020
Final Total | 19 | No
Count | Title | Date
Q1 - January 2016 to March 2016
1 | GridPP at HEP SYSMAN January 2016 |  | https://www.gridpp.ac.uk/news-2016-01-18-hepsysman/
1 | GridPP36 Preview: New directions in GridPP5 |  | https://www.gridpp.ac.uk/news-2016-04-15-gridpp36/
Total for this quarter |  | 2
Q2 - April 2016 to June 2016
1 | GridPP36: New directions in GridPP5 |  | https://www.gridpp.ac.uk/news-2016-04-15-gridpp36/
1 | CernVM Users Workshop - News Item |  | https://www.gridpp.ac.uk/news-2016-06-16-cernvm-workshop/
1 | Case study - LSST |  | https://www.gridpp.ac.uk/users/case-studies/lsst/
1 | Case study - PRaVDA |  | https://www.gridpp.ac.uk/users/case-studies/pravda/
1 | Services - Ganga |  | https://www.gridpp.ac.uk/services/ganga/
1 | Services - GridPP DIRAC |  | https://www.gridpp.ac.uk/services/gridppdirac/
1 | Services - CernVM |  | https://www.gridpp.ac.uk/services/cernvm/
1 | Services - CVMFS |  | https://www.gridpp.ac.uk/services/cvmfs/
Total for this quarter |  | 8
Q3 - July 2016 to September 2016
1 | GridPP37: (R)evolution |  | https://www.gridpp.ac.uk/news-2016-09-05-gridpp37-revolution/
1 | GridPP support for the MoEDAL experiment |  | https://www.gridpp.ac.uk/news-2016-09-12-gridpp-support-for-moedal/
1 | Deploying software the easy way with CVMFS |  | https://www.gridpp.ac.uk/news-2016-09-22-software-deployment-cvmfs/
1 | Queen Mary University of London - site details |  | https://www.gridpp.ac.uk/infrastructure/the-uk-tier-2-sites/qmul/
Total for this quarter |  | 4
Q4 - October 2016 to December 2016
1 | Case study - MoEDAL |  | https://www.gridpp.ac.uk/users/case-studies/moedal/
1 | Case study - HTC for biology |  | https://www.gridpp.ac.uk/users/case-studies/dolphins/
1 | The UserGuide: Now with Ganga! |  | https://www.gridpp.ac.uk/news-2016-11-04-userguide-ganga/
1 | Fifteen years of the Grid |  | https://www.gridpp.ac.uk/news-2016-12-09-fifteen-years-of-the-grid/
1 | UserGuide troublshooting section added |  | https://github.com/gridpp/user-guides/commit/372c267c620ae32785754c420a52b6d9a01fe7f5
Total for this quarter |  | 5

## 4.3.4
4.3.4 | Number of GridPP press releases
Target | 1 per year
Target Per Quarter | 0.25 | Passed
Q1 2016 | 0 | No
Q2 2016 | 0 | No
Q3 2016 | 0 | No
Q4 2016 | 1 | Yes
Q1 2017 |  | No
Q2 2017 |  | No
Q3 2017 |  | No
Q4 2017 |  | No
Q1 2018 |  | No
Q2 2018 |  | No
Q3 2018 |  | No
Q4 2018 |  | No
Q1 2019 |  | No
Q2 2019 |  | No
Q3 2019 |  | No
Q4 2019 |  | No
Q1 2020
Final Total | 1 | Yes
Count | Title | Date
Q1 - January 2016 to March 2016
0 | None
Total for this quarter |  | 0
Q2 - April 2016 to June 2016
0
Total for this quarter |  | 0
Q3 - July 2016 to September 2016
0
Total for this quarter |  | 0
Q4 - October 2016 to December 2016
1 | LSST - "Shear Brilliance" (released via Uni. Manchester Office) |  | http://www.manchester.ac.uk/discover/news/the-dark-universe
Total for this quarter |  | 1

## 4.3.5
4.3.5 | Number of press articles about GridPP
Target | 5 per year
Target Per Quarter | 1.25 | Passed
Q1 2016 | 0 | No
Q2 2016 | 1 | No
Q3 2016 | 0 | No
Q4 2016 | 7 | Yes
Q1 2017 |  | No
Q2 2017 |  | No
Q3 2017 |  | No
Q4 2017 |  | No
Q1 2018 |  | No
Q2 2018 |  | No
Q3 2018 |  | No
Q4 2018 |  | No
Q1 2019 |  | No
Q2 2019 |  | No
Q3 2019 |  | No
Q4 2019 |  | No
Q1 2020
Final Total | 8 | No
Count | Title | Publication | Date | URL (if applicable)
Q1 - January 2016 to March 2016
0 | None
Total for this quarter |  | 0
Q2 - April 2016 to June 2016
1 | Business Insider feature on the LHC |  | 2016-04-03 | http://uk.businessinsider.com/inside-the-lhc-cern-2016-4
Total for this quarter |  | 1
Q3 - July 2016 to September 2016
0
Total for this quarter |  | 0
Q4 - October 2016 to December 2016
1 | LSST - Astronomy Now |  |  | https://astronomynow.com/2016/11/26/grid-computing-to-tackle-the-mystery-of-the-dark-universe/
1 | LSST - phys.org |  |  | http://phys.org/news/2016-11-brilliance-tackles-mystery-dark-universe.html
1 | LSST - NanoWerk |  |  | http://www.nanowerk.com/news2/space/newsid=45181.php
1 | LSST - Scientist Live |  |  | http://www.scientistlive.com/content/shear-brilliance
1 | LSST - Blastr |  |  | http://www.blastr.com/2016-12-8/telescope-will-actually-see-dark-matter
1 | LSST - Italian coverage |  |  | http://www.asi.it/it/news/alla-scoperta-delluniverso-oscuro
1 | LSST - Chinese coverage |  |  | http://tech.qq.com/a/20161128/004260.htm
Total for this quarter |  | 7

## 4.3.6
4.3.6 | Number of KE exploration meetings held
Target | 1 per year
Target Per Quarter | 0.25 | Passed
Q1 2016 | 1 | Yes
Q2 2016 | 0 | No
Q3 2016 |  | No
Q4 2016 |  | No
Q1 2017 |  | No
Q2 2017 |  | No
Q3 2017 |  | No
Q4 2017 |  | No
Q1 2018 |  | No
Q2 2018 |  | No
Q3 2018 |  | No
Q4 2018 |  | No
Q1 2019 |  | No
Q2 2019 |  | No
Q3 2019 |  | No
Q4 2019 |  | No
Q1 2020
Final Total | 1 | No
Count | Description of Meeting | Date
Q1 - January 2016 to March 2016
1 | SeeCycle.cc (at RAL) | 2016-02-22
Total for this quarter |  | 1
Q2 - April 2016 to June 2016
0
Total for this quarter |  | 0
Q3 - July 2016 to September 2016
1 | Satellite Applications Catapult Sataccino Summer BBQ, 6th July 2016 |  | Networking event
1 | Meeting with Stephen Ringler - RAL Space Oxford, 19th July 2016
Total for this quarter |  | 2
Q4 - October 2016 to December 2016
0
Total for this quarter |  | 0

## 4.3.7
4.3.7 | Number of non-GridPP funded Groups who use GridPP hardware | 0
Target | 10 | https://accounting-next.egi.eu | (UK NGI, all VOs) (Non-GridPP
Current Number | 24 |  | funded groups using GridPP hardware)
Count | Group
Q1 - January 2016 to March 2016
1 | biomed
1 | calice
1 | cernatschool.org
1 | comet.j-parc.jp
1 | enmr.eu
1 | fermilab
1 | geant4
1 | gridpp
1 | ilc
1 | lsst
1 | lz
1 | mice
1 | na62
1 | nordugrid
1 | pheno
1 | snoplus.snolab.ca
1 | t2k.org
1 | vo.landslides.mossaic.org
1 | vo.londongrid.ac.uk
1 | vo.northgrid.ac.uk
1 | vo.scotgrid.ac.uk
1 | vo.southgrid.ac.uk
1 | zeus
Totals for this quarter | 23
Q2 - April 2016 to June 2016
1 | biomed
1 | calice
1 | cernatschool.org
1 | comet.j-parc.jp
1 | dune
1 | enmr.eu
1 | esr
1 | geant4
1 | icecube
1 | ilc
1 | lsst
1 | lz
1 | mice
1 | na62.vo.gridpp.ac.uk
1 | pheno
1 | skatelescope.eu
1 | snoplus.snolab.ca
1 | solidexperiment.org
1 | t2k.org
1 | vo.londongrid.ac.uk
1 | vo.northgrid.ac.uk
1 | vo.scotgrid.ac.uk
1 | vo.southgrid.ac.uk
Totals for this quarter | 23
Q3 - July 2016 to September 2016
1 | biomed
1 | cernatschool.org
1 | comet.j-parc.jp
1 | dune
1 | enmr.eu
1 | esr
1 | gridpp
1 | icecube
1 | ilc
1 | lsst
1 | lz
1 | mice
1 | na62.vo.gridpp.ac.uk
1 | pheno
1 | skatelescope.eu
1 | snoplus.snolab.ca
1 | t2k.org
1 | vo.londongrid.ac.uk
1 | vo.moedal.org
1 | vo.northgrid.ac.uk
1 | vo.scotgrid.ac.uk
1 | vo.southgrid.ac.uk
Totals for this quarter | 22
Q4 - October 2016 to December 2016
1 | biomed
1 | cepc
1 | cernatschool.org
1 | comet.j-parc.jp
1 | dune
1 | enmr.eu
1 | fermilab
1 | gridpp
1 | icecube
1 | ilc
1 | lsst
1 | lz
1 | mice
1 | na62.vo.gridpp.ac.uk
1 | pheno
1 | skatelescope.eu
1 | snoplus.snolab.ca
1 | solidexperiment.org
1 | t2k.org
1 | vo.londongrid.ac.uk
1 | vo.moedal.org
1 | vo.northgrid.ac.uk
1 | vo.scotgrid.ac.uk
1 | vo.southgrid.ac.uk
Totals for this quarter | 24

## Milestones
Milestone | Description | Target Completion Date | Date Completed | Comments
4.3.8 | KE sections of GridPP website updated | 31st Dec 2016
4.3.9 | KE sections of GridPP website updated | 31st Dec 2017
4.3.10 | KE sections of GridPP website updated | 31st Dec 2018
4.3.11 | KE sections of GridPP website updated | 31st Dec 2019

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes