## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Security |  |  | Close to target
Year | 2016 |  |  | Not OK
Reported by | Dave Kelsey |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Comment Q116 | Comment Q216 | Comment Q316
3.3.1 | Number of Tier 2 security incidents in the last quarter |  | Dave Kelsey | Green <=1, Amber 2 or 3 and Red >=4 | 1 | 1 | 0 | 1 incident at Imperial College reported to UK NGI Security and EGI on 28 February 2016. [EGI-20160228-01]. | 1 incident at Edinburgh reported on 27 June 2016 - JANET CSIRT #1495611 | None.
3.3.2 | Number of sites responding poorly to a security incident in last quarter |  | Dave Kelsey | Green 0, Amber 1 Red >=2 | 0 | 0 | 0 | Very well handled | Very well handled
Note on B10: gronbech: Green 0, Amber 1, Red >=2

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Security |  |  | Overdue
Year | 2016 |  |  | Not yet due
Reported by | Dave Kelsey |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
3.3.3 | Security Service Challenge | Ian Neilson | 2017-12-31
3.3.4 | UK HEP Sysman Security Training/Workshop | Ian Neilson | 2018-12-31
3.3.5 | Security plans for the future beyond end of GridPP5 | Dave Kelsey | 2019-12-31

## Manpower Q116
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | GridPP Funded Month 1: 0.72; GridPP Funded Month 2: 0.83; GridPP Funded Month 3: 0.97
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.19 | 0.23 | 0.13 | 0.13 | 0.13
RAL | Policy | Dave Kelsey | 0.27 | 0.38 | 0.27 | 0.13 | 0.13 | 0.13
Total |  |  | 1.16 | 1.4 | 1.47 | 0.26 | 0.26 | 0.26

## Manpower Q216
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey | UPDATED 13 Oct 2016
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | GridPP Funded Month 2: 0.36; GridPP Funded Month 3: 0.45
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | GridPP Funded Month 1: 0.91; GridPP Funded Month 2: 0.68; GridPP Funded Month 3: 0.97
RAL | Vulnerabilities | Linda Cornwall | 0.22 | 0.2 | 0.2 | 0.46 | 0.33 | 0.2
RAL | Policy | Dave Kelsey | 0.46 | 0.53 | 0.67 | 0.13
Total |  |  | 1.59 | 1.77 | 2.29 | 0.59 | 0.33 | 0.2

## Manpower Q316
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | GridPP Funded Month 1: 0.44; GridPP Funded Month 2: 0.41
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | GridPP Funded Month 1: 0.98; GridPP Funded Month 2: 0.56; GridPP Funded Month 3: 1
RAL | Vulnerabilities | Linda Cornwall | 0.2 | 0.2 | 0.12 | 0.3 | 0.3 | 0.5
RAL | Policy | Dave Kelsey | 0.57 | 0.52 | 0.15 |  |  | 0.4
Total |  |  | 2.19 | 1.69 | 1.27 | 0.3 | 0.3 | 0.9

## Narrative Q116
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT with regular weekly/monthly meetings. UK NGI security team fortnightly meetings. Ewan has left the UK NGI team and been replaced by David Crooks who is also co-leading a GDB WG on Security Operations Centres. Ian Neilson is following up on Ewan's Argus banning tests and now participates in EGI CSIRT Officer on Duty rota handling incident and monitoring/issuing vulnerability tracking tickets. One UK security incident reported, impacting only the reporting site, from Imperial College involving a poorly configured, user-provided Virtual Machine. Participated at meetings of IGTF, WLCG Collaboration Workshop and security-focussed GDB, Geant TF-CSIRT and EGI CSIRT F2F. Ongoing development work for EGI Cloud Security issues. IPv6 security.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities as reported during the quarter. Complete updated security risk assessment for EGI. Reported status and plans at EGI CSIRT F2F meeting Prague 27-29 Jan.
Policy | Continue to lead EGI SPG and WLCG security policy. Completed work on Revised VM Endorsement and Operations policy and new Data Protection Policy. Attended EUGridPMA meeting Bratislava 18-20 Jan. Chaired EGI CSIRT F2F meeting Prague 27-29 Jan. Attended security workshop, APGridPMA and ISGC2016 conference Taipei 13-18 March. Chaired session on Identity Management and spoke on IPv6 security. Attended WLCG Workshop in Lisbon 1-3 Feb.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2016-04-15 |  | This report describes how security will be taken forward in GridPP5, EGI and WLCG. URL
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 31/12/2013 (new date 30/06/2016) |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson has taken over responsibility for this now Ewan McM has left Oxford and will run a full test at some suitable time in first half of 2016, i.e. this will continue into GridPP5.

## Narrative Q216
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to coordinate EGI CSIRT with monthly meetings and co-chair CSIRT F2F in Amsterdam in April followed by the EGI Conference. Participate in EGI CSIRT duty rota and lead UK NGI security team with fortnightly meetings. Continue work on Argus storage banning tests, to be completed in time for a report at GridPP37. One UK security incident reported, an exposed port mapper at Edinburgh. Participated at meetings of IGTF, WLCG security-focussed GDB, Geant TF-CSIRT. Ongoing development work for EGI Cloud Security issues. IPv6 security. |  | Please note that the security effort being booked to GridPP5 is too large in May and June. The excess is funded by EGI.eu but while the income has been agreed, the project codes in STFC SCD for this have not yet been setup. The costs will balance out over the full financial year.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities (11 in total, including 2 critical and 3 high risk) as reported during the quarter. Reported on updated security risk assessment to EGI OMB. Work on updated procedures for Clouds. Attended EGI Conference Amsterdam in April.
Policy | Continue to lead EGI SPG and WLCG security policy. Continue work on several new policies - Data Protection, VM Endorsement, revised AAI Trust policy. Hosted an EUGridPMA meeting at Coseners House (9-11 May). Member of WISE Steering Committee and lead WISE SCIV2-WG. Proposed new WISE working group on Clouds at TNC16 Conference (Prague 12-16 June). Collaborate with EU H2020 EGI-Engage and AARC activities. Member of UK Jisc AAI working group (meeting 25 April).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q316
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to coordinate EGI CSIRT with monthly meetings and host/co-chair CSIRT F2F in Abingdon in September. Participate in EGI CSIRT duty rota and lead UK NGI security team with fortnightly meetings. Work on Argus storage banning tests completed for a report at GridPP37. Participated at meetings of IGTF, WLCG GDB, Geant TF-CSIRT. Ongoing development work for EGI Cloud Security issues. IPv6 security poster for CHEP. |  | Please note that the security effort being booked to GridPP5 is too large in May to August. The excess is funded by EGI.eu but while the income has been agreed, the project codes in STFC SCD for this were not setup until September. The costs will balance out over the full financial year.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities (several critical) as reported during the quarter. Attended DI4R Conference Krakow in September.
Policy | Continue to lead EGI SPG and WLCG security policy. Four policy documents being updated with newer terminology. Leading SCI Version 2 working group within WISE. Played leading role in WISE meeting in Miami linked to XSEDE conference in July and planned for and co-lead of WISE workshop at DI4R in Krakow in September. Collaborate with EU H2020 EGI-Engage and AARC activities. Member of UK Jisc AAI working group (meeting July).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes