## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Data Group |  |  | Close to target
Year | 2017 |  |  | Not OK
Reported by | Jens Jensen |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Q416 | Q117 | Q217 | Q317 | Comment Q116 | Comment Q216 | Comment Q316 | Comment Q416 | Comment Q117 | Comment Q217 | Comment Q317
3.2.1 | Number of VO requested changes not implemented in a timely fashion across whole infrastructure (1wk for small changes, 3wks for medium size, 6wks for large.) - any GridPP VO |  | Jens Jensen | 0 | [7 empty] | Main change was the ATLAS catalogue upload (make SE contents available at well def'd location) - seems to have completed OK. Mostly slow feedback from ATLAS | No changes | No additional changes requested. | Other than accounting for ATLAS which will need some development, no major changes requested. | No changes | No major changes requested.
3.2.2 | Number of experiments whose data transfer rates from/to RAL to/from T2s do not meet their (realistic) requirements |  | Jens Jensen | 0 |  | See plot | [5 empty] | 350 MB/s overall avg for CMS, LHCb, ATLAS. Also DiRAC got up to 400MB/s. | Transfer and success rates for ATLAs, LHCb, and CMS mostly OK (see plot) | Avg is 82 MB/s into RAL and 110 out. |  | Seems OK; see plot. (However some of the low rates are due to low activity, maybe APEL has better data?) | See plot on RHS. (A bit lo res because it needs to fit on the monitor when I screeshot it. The "J" character is a 3…) | Plot: Oxford and QMUL look a bit dodgy as destinations but fine as source; Sheffield looks a bit low both ways. However, these
3.2.3 | FTS data transfer success rate |  | Jens Jensen | 85% | [7 empty] | CERN FTS plot shows excellent success rates between sites, but one needs to dig into it a bit because in the summary the rates is marred by a large number of failures to the test instances | OK - see plot. Note the slightly dodgy destinations at ECDF, Glasgow, and Oxford are due to the test SEs (e.g. IPv6) being included in the metrics. | Success rate into RAL for main expts is 98%; from RAL is only 81% though. See plot: the failure rates are due to test SEs being included, notably Glasgow and Oxford. (NOTE: this uses the GridPP FTS servers which have done the bulk of the transfers; not the CERN or FNAL ones.) | See plot to the right. Note it includes test transfers - it is difficult to exclude those. | See plot. Again these are only avg rates. | See plot: total is 82% (but including test transfers: we have no reliable way of filtering them out.) | Probably OK in practice, as the 77% include test transfers. Nevertheless, without a way to separate the relevant FTSes?
3.2.4 | Conference paper (CHEP, AHM, or similar (or better)) produced each year describing GridPP developments and innovations in data management and storage area |  | Jens Jensen | 4/Y | [7 empty] | None this quarter except people are preparing stuff for CHEP (for next Q), and for GridPP36 of course | 6-7 abstracts submitted to CHEP for storage group; Marcus' was for a presentation, the others for posters | One or two CHEP submissions were withdrawn, but still met the target: | WLCG workshop https://indico.cern.ch/event/555063/sessions/207257/ and CHEP and HEPiX | Appleyard, Jensen, Gordon: CASTOR acct. (ISGC 2017). Proposed submissions to WLCG in Manchester. We don't seem to have submitted to HEPiX, though, nor to Networkshop | None this quarter; as we focused on the WLCG workshop | None this Q
3.2.5 | Engage with storage and data management experts within WLCG/EGI/EMI/NGS or similar, or industry, to reinforce GridPP's recognised competence in this area (talks given, meetings, virtual meetings) |  | Jens Jensen | 4/Q | [7 empty] | Site report to WLCG early Feb (Sam) ATLAS Jamboree (Brian, Elena) | Sam attended the DPM collaboration meeting in April (https://indico.cern.ch/event/522634/) Good (re)presentation at hepsysman at RAL (June) | Good representation at the pre-GDB on data management; Brian attended to speak on behalf of GridPP. http://indico.cern.ch/event/394833/. Some work on accounting (cf 13 July), also July GDB. GridPP37, of course. Finallly, input from Sam and marcus on DPM-as-a-cache to DPM community. | Data session at CHEP: https://indico.cern.ch/event/555063/sessions/207257/ DPM workshop http://indico.cern.ch/event/559673/ GridPP well represented at the cloud workshop at Crick. Also (less formally) at CIUK '15 (née MEW) | Doesn't seem to have been any relevant meetings this quarter? | Excellent representation at WLCG workshop in Manchester. However, we had nothing at HEPiX. | Engagement with WLCG's storage and reporting task forces, and DPM developers re UK hosting workshop
3.2.6 | Number of incidents not resolved within 1wk after being reported on list |  | Jens Jensen | 0 |  |  |  | 4 |  |  |  | None reported |  | No incidents reported | Not so much "incidents" as issues - biomed (resolved), and truncated xroot/CMS files at Bristol, xroot failing at Edinburgh through cksum failure. Suspcius DPM load spike at Glasgow | sno+ "incindent" seems to be controlled - ie due to growth they need to be persuaded to use space tokens | Only a few incidents but they seem to have resolved fairly quickly . I have less data about RALPP's "interesting" database upgrade for dCache, though, as it was reported only indirectly. | OK
3.2.7 | Number of blog posts |  | Jens Jensen | 5 | 7 | 3 | 6 | 3 | 8 | 8 | 2 | Brian 2, Marcus 2, Jens 2, Daniel 1 | Hmm are we already failing our new lower target? The purdah didn't help though. Marcus wrote all three (excellent) posts | Daniel: 4 excellent posts on Lustre upgrade; Jens 2. | Jens 2 , Marcus 1 | Marcus 3 JohnB 1 Brian 4 | Brian 7 (despite STFC purdah most of the quarter) and, RobC 1 (but a long one…) | Jens 1, Brian 1

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Data Group |  |  | Overdue
Year | 2017 |  |  | Not yet due
Reported by | Jens Jensen |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
3.2.8 | Deploy and test "solution" for T2C storage (e.g. cache+local storage) | Sam Skipsey | 2017-01-31 | 2017-08-31 | Feedback to GDB | Completed
3.2.9 | Present GridPP work at data workshop at CERN | Brian Davies | 2016-09-30 | 2017-08-31 | Presentation | Done.
3.2.10 | Develop GridPP as a "data einfrastructure" in the context of UKT0 | Jens Jensen | 2016-12-31 | 2017-08-31 | Report? | Presented at UKT0 meeting at Milton Park
3.2.11 | Data transfer/management comparison with climate | Jens Jensen | 2016-11-30 | 2017-08-31 | Report, workshop, or publication | Work presented at Cloud workshop hosted by Crick end of Nov. 2016 (on connecting GridPP with cloud and other e-infrastructures)

## Manpower Q212 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q312 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q412 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q113 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q213 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q116
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q216
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q316
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q416
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.5 | 0.5 | 0.5
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 2.7 | 2.7 | 2.7 | 0 | 0 | 0

## Manpower Q117
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q217
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q317
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 0.5 | 0.5 | 0.5
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
|  | Teng Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
Total |  |  | 3 | 3 | 3 | 0.5 | 0.5 | 0.5

## Narrative Q116
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Very interesting work from Marcus on ZFS! (see blog) https://gridpp-storage.blogspot.com/ |  | Very high failure rates on test SEs (particularly the IPv6 ones)
Data Management | GridPP as a data infrastrcuture: good progress with DiRAC at least; LIGO is mostly jobs and LSST not sure what to do. |  | Slow progress with LSST… some issues with integration of communities that already have their own catalogues?
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
High risks associated with future T2 - due to lots of unknowns (interfaces, infrastructure, T2C/T2D, etc.) |  | Engage with WLCG (=GDB) and experiments as much as we can. Needs some planning.
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still problematic - the few test SEs show nothing but failures?! |  | Test with lower level tools?
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Get Leicester moving data for DiRAC |  | 2016-01-31 |  | Leicester got certificates, set up services, customised the Durham script - and then "had no data to back up yet"
Finish ATLAS space token cleanup |  | 2016-03-31 |  | Considered done (by ATLAS).
All sites required to publish catalogues, er, publish catalogues |  | 2016-03-31 |  | GGUS tickets closed
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Input on data einfra to national e-infrastructure project directors' group |  | 2016-05-01
T2C testing: ATLAS hammercloud report |  | 2016-05-15
Status of future T2:summary of current issues and recommendations |  | 2016-06-30 |  | short report (to PMB)

## Narrative Q216
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Loads of good stuff submitted to CHEP |  | Very high failure rates on test SEs (particularly the IPv6 ones) - this is still a problem (see plot for Oxford on the Metrics page)
Data Management
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
High risks associated with future T2 - due to lots of unknowns (interfaces, infrastructure, T2C/T2D, etc.) |  | Update: seems to now be mostly an issue of managing experiments' expectations
Note that as of April 2016 Brian has started doing some work on a H2020 funded climate project (bringing his expertise from GridPP). However, at this momemtn his delivery to T2 support does not seem to have affected.
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still problematic - the few test SEs show nothing but failures?! |  | Test with lower level tools?
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Input on data einfra to national e-infrastructure project directors' group |  | 2016-05-01 |  | Presentation given at event at Milton Hill House
T2C testing: ATLAS hammercloud report |  | 2016-05-15 |  | Still waiting for report from Alastair Dewhurst (delayed).Delay thought to be caused by person in ATLAS HQ who is overloaded with work.
Status of future T2:summary of current issues and recommendations |  | 2016-06-30 |  | Sam's writeup of discussion(s) https://docs.google.com/document/d/1fEJtO0xANVClJrSIh8jeH30fBMtAbLyzLzzrJwTwiog/edit?usp=sharing
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Input to data workshop at CERN in September |  | 2016-09-13 |  | Presentation given on behalf of all of GridPP (by Brian Davies) http://indico.cern.ch/event/394833/
Report on the future of tape storage (Brian Davies) and expected impact on archiving operations at T1 |  | 2016-09-30 |  | Report to GridPP storage

## Narrative Q316
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | GridPP has a Science DMZ. This could be another opportunity to fly the flag. |  | Accounting may need to be looked at again…
Data Management | IPv6 seems to be working OK for (most of) the sites participating in the FTS-at-IC (ie Brunel, Imperial itself, QMUL, RHUL, and Glasgow) |  | Need to separate test traffic from production traffic for this report! (cf last Q's narrative)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Risk of storage interfaces diverging: DPM is getting DAV with "quota tokens", dCache and StoRM supporting Macaroons (=fancy cookies); CASTOR remaining at SRM |  | No mitigating action known. However, if we end up in a mess, we know who to thank…
Risks of information systems being redesigned and the same old wheel being reinvented yet again.(see July GDB); see also https://ggus.eu/?mode=ticket_info&ticket_id=117683 |  | GLUE people (incl GridPP) could work with WLCG/CERN on adopting the GLUE2 JSON schema
Insitute or area specific risks
Risk |  | Mitigating Action
Yet another redefinition of storage accounting will lead to more effort being required. See also https://ggus.eu/?mode=ticket_info&ticket_id=117683 for CASTOR's issue. |  | No mitigating action.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
T2C testing: ATLAS hammercloud report |  | 2016-05-15 |  | Still waiting for report from Alastair Dewhurst (delayed).Delay thought to be caused by person in ATLAS HQ who is overloaded with work.
Input to data workshop at CERN in September |  | 2016-09-13 |  | Presentation given on behalf of all of GridPP (by Brian Davies) http://indico.cern.ch/event/394833/
Report on the future of tape storage (Brian Davies) and expected impact on archiving operations at T1 |  | 2016-09-30 |  | Brian has been to meetings with vendors - Oracle, SpectraLogic, and LTUG (Large Tape User Group). Unfortunately roadmaps are generally under NDA, so we cannot report those to GridPP, but SpectraLogic have promised to send us information we can share.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
GridPP Input to DPM workshop in November (Sam) |  | 23-24 Nov. |  | http://indico.cern.ch/event/559673/
3.2.10. Develop GridPP as a "data einfrastructure" in the context of UKT0 |  | 2016-12-31 |  | Report/proposal
3.2.11. Data transfer/management comparison with climate |  | 2016-11-30 |  | Report or publication

## Narrative Q416
GridPP Quarterly Report
Area | Data Group
Year | 2016
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Good representation at DPM workshop Opportunities to follow up from this quarter, to wave the GridPP flag and do something interesting, such as "data transfer node" writeup; or GLUE in JSON with DESY, or maybe some of the cloud stuff. |  | Rseources not being used correctly through incorrect use of space tokens (particularly biomed@Liverpool). ATLAS problems caused by buggy ATLAS "site mover"
Data Management | Good visibility of our work to : Lydia presenting at JISC end-to-end-workshop (https://www.jisc.ac.uk/events/campus-network-engineering-for-data-intensive-science-workshop-19-oct-2016) and presentations at Crick (https://cloud.ac.uk/workshop-november-2016/ - still not written up as of Jan '17, but see http://storage.esc.rl.ac.uk/weekly/20161217-minutes.txt) - conencting GridPP also to EUDAT, Azure, PRACE, etc. |  | Minor issues on decommissioning VOs. Information in wiki gets stale (even the keydocs are not updated!)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Risk of storage interfaces diverging: DPM is getting DAV with "quota tokens", dCache and StoRM supporting Macaroons (=fancy cookies); CASTOR remaining at SRM (still a risk, cf. biomed at Liverpool) |  | No mitigating action known. However, if we end up in a mess, we know who to thank…
Risks of information systems being redesigned and the same old wheel being reinvented yet again.(see July GDB); see also https://ggus.eu/?mode=ticket_info&ticket_id=117683 |  | GLUE people (incl GridPP) could work with WLCG/CERN on adopting the GLUE2 JSON schema - need to follow up.
Insitute or area specific risks
Risk |  | Mitigating Action
DPM as a cache - needs more testing
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
T2C testing: ATLAS hammercloud report |  | 2016-05-15 |  | Still waiting for report from Alastair Dewhurst (delayed).Delay thought to be caused by person in ATLAS HQ who is overloaded with work.
GridPP Input to DPM workshop in November (Sam) |  | 23-24 Nov. |  | http://indico.cern.ch/event/559673/
3.2.10. Develop GridPP as a "data einfrastructure" in the context of UKT0 |  | 2016-12-31 |  | See "Data Management Successes" above
3.2.11. Data transfer/management comparison with climate |  | 2016-11-30 |  | Brian did some work with non-GridPP funding on data centres for climate;
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Report on ZFS testing (following up from HEPiX): is ZFS a suitable alternative for a Tier 2. Should GridPP expand its expertise (ie not just Marcus) in ZFS? |  | 2017-02-28 |  | Report and updated wiki
Update on GLUE solving the acounting in JSON for ATLAS problem? (See http://storage.esc.rl.ac.uk/weekly/20161116-minutes.txt) |  | 2017-03-31 |  | Report & plan & ideally some sort of working prototype

## Narrative Q117
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Good experiences with ZFS, as can also be seen from the blog, and from the minutes and vidyo chat logs from the meetings |  | Losing most of our ZFS expertise thanks to Brexit (ie Marcus going to Canada) RAL's LHCb SRMs got re-certificated without alternative names, so failed for RAL's FTS (but not CERN's)
Data Management | ARC cache test results at Durham have gone well, would be useful to expand to other site. |  | Accounting is wrong - again. Each implementation - dCache, DPM, CASTOR - seems to have its own problem. Also problems with RUCIO creating empty directories (again) and deletions through WebDAV.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Loss of ZFS expertise leading to problems in the future |  | Other sites need to build expertise, or we need to not use ZFS
Information systems (still a risk) - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Still needs more effort -
Effort - note Brian's back to 80% having left the climate project, but we now lose Marcus |  | Recruitment at Edinburgh
Insitute or area specific risks
Risk |  | Mitigating Action
Storage nodes become unavailable due to their certificates being renewed inadvertently omitting subject altenrative names (happened for LHCb at RAL) (mostly a T1 issue at the moment but could currenlty also hit Imperial, RALPP, and a few other sites). |  | Suggest using hepsysman to review/discuss options
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
T2C testing: ATLAS hammercloud report |  | 2016-05-15 |  | Now finally resolved - tests were done with CMS instead; see http://storage.esc.rl.ac.uk/weekly/20170222-minutes.txt
Report on ZFS testing (following up from HEPiX): is ZFS a suitable alternative for a Tier 2. Should GridPP expand its expertise (ie not just Marcus) in ZFS? |  | 2017-02-28 |  | See extensive blog posts from Marcus (https://gridpp-storage.blogspot.co.uk/) and the minutes of almost every meeting in the quarter (http://storage.esc.rl.ac.uk/weekly/). Short answer is yes, if we can retain the expertise, and need to look out for performance issues.
Update on GLUE solving the acounting in JSON for ATLAS problem? (See http://storage.esc.rl.ac.uk/weekly/20161116-minutes.txt) |  | 2017-03-31 |  | Rob presented work at ISGC in March. However, the task has not progressed as much as we'd like, due to lack of effort - for example, solving CASTOR issues is a higher priority and meant we had less time to work on the accounting.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
We really need to get our wiki docs refreshed, particularly of course the keydocs - lots of storage related docs have been very, very, red for quite some time, despite lots of nagging. |  | 2017-05-31 |  | docs updated - internal review
Proposal for multi-SAN support |  | mid June |  | Discussion/proposal at hepsysman

## Narrative Q217
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Good GridPP (re)presentation at WLCG workshop. While the presentations in GridPP storage were dominated by RAL (and a few of the sought topics were specific to RAL (in GridPP), such as object stores and tape), we contributed to the data and accounting sessions |  | Storage accounting continues to drag behind but was at least revisited at the WLCG workshop. IPv6 is still problematic: even sites with dual stack do not necessarily get good performance, due to site network issues outside of the storage element
Data Management | CVMFS seems to be progressing well and is now proposed used also for experiments' data |  | FTS migration issue (SOAP to ReST). Also, FTS support for non-GridFTP protocols need more testing.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Loss of ZFS expertise leading to problems in the future |  | Other sites need to build expertise, or we need to not use ZFS Mitigation update: RobC seems to have got up to speed, cf his blog post. http://gridpp-storage.blogspot.co.uk/2017/06/hosting-large-web-forum-on-zfs-case.html
Information systems (still a risk) - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Still needs more effort -
Globus toolkit end of support was identified as a major risk during the quarter |  | Hopefully the proposed CERN/OSG support works out, or we will have to think carefully how to proceed with our existing storage systems
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | re-test with "volunteer" (Lancaster) to see if we get better results
Poorly supported non-SRM accounting leading to inaccurate accounting at (SRM-less) T2s |  | Need to test more recent versions of storage elements. (Bristol?)
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
We really need to get our wiki docs refreshed, particularly of course the keydocs - lots of storage related docs have been very, very, red for quite some time, despite lots of nagging. |  | 2017-05-31 |  | Some good progress, but despite fairly persistent nagging since January, not all storage keydocs have been updated. (Note that some just need reviewing, others need re-testing)
Proposal for multi-SAN support (in order to support multi-VO storage endpoints and/or resilient services) |  | mid June |  | Discussion/proposal at hepsysman. Presentation given and discussed. Early trials of system (mostly supporting T1 FTS and Echo) have been sufficintly promising to say it's an improvement.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Present GridPP work at September pre-GDB |  | 2017-09-12 |  | Presentations of work, attendance
Investigate SwordFish (SNIA storage management extension of DMTF's redfish which in turn updates IPMI) |  | 2017-09-12 |  | Presentations of work
If we update the dCache keydoc (testing by Brian) we should test the Google Macaroons as non-certificate access method and report |  | 2017-09-12 |  | Presentation of work

## Narrative Q317
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Storage keydocs are finally green(ish)! Only took over a year! Generally successful migrations from SL6 to CentOS7 and YAIM to Puppet |  | Switching to object stores could cause problems, depending on access patterns and interfaces used.
Data Management | We seem to have made modest progress on the T2 evolution with more clarity from the experiments and a plan for the next steps we can usefully do. |  | Loss of GridFTP (in the longer term) would be a problem unless we can find other ways to do 3rd party copying in parallel streams Request for managing lots (10^6) of small (kB) files for CERN@School. Very slow accounting in DPMs v1.8.X. Needs testing in 1.9 to see whether it improves (sites run it monthly despite being requested to run it daily)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Loss of ZFS expertise leading to problems in the future |  | Situation improving after the loss of Marcus. See talk at GridPP. Also, Teng (at Edinburgh) tasked with gaining expertise. Can probably drop this risk in 17Q4
Information systems - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Ongoing risk. However, following the summer's WLCG workshop, the October pre-GDB has added some clarity (and the December one should add some more…?!)
Globus toolkit end of support was identified as a major risk during the quarter |  | Short to medium term: accept the risk. Do we need to resurrect older ftp implementations? Can we support GridFTP ourselves? Would Globus Connect be sufficient?
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | re-test with "volunteer" (Lancaster) to see if we get better results
Poorly supported non-SRM accounting leading to inaccurate accounting at (SRM-less) T2s |  | Need to test more recent versions of storage elements. (Bristol?)
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
We really need to get our wiki docs refreshed, particularly of course the keydocs - lots of storage related docs have been very, very, red for quite some time, despite lots of nagging. |  | 2017-05-31 |  | Finally they are green… (all the red ones are non-storage ones)
Present GridPP work at September pre-GDB |  | 2017-09-12 |  | Topics in the end were a bit tier1y but GridPP was well represented: https://indico.cern.ch/event/578974/
Investigate SwordFish (SNIA storage management extension of DMTF's redfish which in turn updates IPMI) |  | 2017-09-12 |  | Done, will appear as a blog post in October (hopefully). The basic idea is SwordFish gives us a view of physical resources and their capacity but we still need additional metadata like paths and ownership.
If we update the dCache keydoc (testing by Brian) we should test the Google Macaroons as non-certificate access method and report |  | 2017-09-12 |  | Keydoc has been refreshed. Macaroon doesn't seem to be completed? Or at least it has not been written up.; but the situation has also changed with the SciTokens proposal from the US.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
"xcache" testing: RHUL "volunteered", to be aided by Power Rangers |  | 2017-12-31 |  | report
SciToken/Macaroon (etc) position statement |  | 2017-12-31 |  | feedback to WLCG US
Need a better way to get/filter FTS performance metric (filter out bogus/test data) |  | 2017-12-31 |  | Recipe or reporting tool

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
GridPP as a data infrastructure | 2016-03-31 | All areas of research need data storage and movement even if they don't compute like HEP. Opportunity with MSDC ("UKT0") collaboration.
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Wahid Bhimji went to NERSC | 2015-03-11
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes