## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Security |  |  | Close to target
Year | 2017 |  |  | Not OK
Reported by | Dave Kelsey |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Q416 | Q117 | Q217 | Q317 | Q417 | Comment Q116 | Comment Q216 | Comment Q316 | Comment Q416 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417
3.3.1 | Number of Tier 2 security incidents in the last quarter |  | Dave Kelsey | Green <=1, Amber 2 or 3 and Red >=4 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 incident at Imperial College reported to UK NGI Security and EGI on 28 February 2016. [EGI-20160228-01]. | 1 incident at Edinburgh reported on 27 June 2016 - JANET CSIRT #1495611 | None. | None | 1 incident (10 March) at Glasgow involving an old non-GRID NA62 system. No impact on any GridPP systems [EGI-20170310] | None | None | 1 incident (1 Nov) notified by Janet CSIRT involving the DiRAC cluster at Durham. No impact on any GridPP systems [EGI-20171101]
3.3.2 | Number of sites responding poorly to a security incident in last quarter |  | Dave Kelsey | Green 0, Amber 1 Red >=2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very well handled | Very well handled |  |  | Very well handled |  |  | Very well handled
Note on B10: gronbech: Green 0, Amber 1, Red >=2

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Security |  |  | Overdue
Year | 2017 |  |  | Not yet due
Reported by | Dave Kelsey |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
3.3.3 | Security Service Challenge | Ian Neilson | 2017-12-31 |  |  | Ian Neilson performed a Security Communication Challenge in Q117. Problems with two sites were fixed. Ian's departure in July 2017 put plans for a fuller security challenge on hold. We will perform this once the replacement Security Officer is in post - probably in Q218.
3.3.4 | UK HEP Sysman Security Training/Workshop | Ian Neilson | 2018-12-31 | 2017-06-13 | https://indico.cern.ch/event/592622/ | Milestone 3.3.3 has been delayed, but in the meantime we achieved milestone 3.3.4 early. Ian Neilson organised a one-day security workshop for HEP SYSMAN at RAL concentrating on the topic of IPv6 security
3.3.5 | Security plans for the future beyond end of GridPP5 | Dave Kelsey | 2019-12-31

## Manpower Q117
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.35 | 0.4 | 0.26
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.78 | 0.51 | 0.84
RAL | Vulnerabilities | Linda Cornwall | 0.2 | 0.2 | 0.2 | 0.13 | 0.13 | 0.4
RAL | Policy | Dave Kelsey | 0.18 | 0.16 | 0.2 | 0.39 | 0.21 | 0.23
Total |  |  | 1.51 | 1.27 | 1.5 | 0.52 | 0.34 | 0.63

## Manpower Q217
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.23 | 0.07 | 0.32
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.6 | 0.86 | 0.82
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.17 | 0.17 | 0.25 | 0.28 | 0.4
RAL | Policy | Dave Kelsey | 0.1 | 0.16 | 0.52 | 0.1 | 0.16 | 0.15
Total |  |  | 1.1 | 1.26 | 1.83 | 0.35 | 0.44 | 0.55

## Manpower Q317
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.28 | 0.21 | 0.47
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.78
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.17 | 0.17 | 0.5 | 0.3 | 0.42
RAL | Policy | Dave Kelsey | 0.18 | 0.27 | 0.19 | 0.17 | 0.09 | 0.17
Total |  |  | 1.41 | 0.65 | 0.83 | 0.67 | 0.39 | 0.59

## Manpower Q417
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.51 | 0.51 | 0.15
RAL | Deployment | Dave Kelsey | 0.15 | 0.15 | 0.05
RAL | Deployment | Ian Neilson
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.17 | 0.17 | 0.43 | 0.44 | 0.29
RAL | Policy | Dave Kelsey | 0.15 | 0.19 | 0.09 | 0.26 | 0.25 | 0.09
Total |  |  | 0.98 | 1.02 | 0.46 | 0.69 | 0.69 | 0.38

## Narrative Q116
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to lead EGI CSIRT with regular weekly/monthly meetings. UK NGI security team fortnightly meetings. Ewan has left the UK NGI team and been replaced by David Crooks who is also co-leading a GDB WG on Security Operations Centres. Ian Neilson is following up on Ewan's Argus banning tests and now participates in EGI CSIRT Officer on Duty rota handling incident and monitoring/issuing vulnerability tracking tickets. One UK security incident reported, impacting only the reporting site, from Imperial College involving a poorly configured, user-provided Virtual Machine. Participated at meetings of IGTF, WLCG Collaboration Workshop and security-focussed GDB, Geant TF-CSIRT and EGI CSIRT F2F. Ongoing development work for EGI Cloud Security issues. IPv6 security.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities as reported during the quarter. Complete updated security risk assessment for EGI. Reported status and plans at EGI CSIRT F2F meeting Prague 27-29 Jan.
Policy | Continue to lead EGI SPG and WLCG security policy. Completed work on Revised VM Endorsement and Operations policy and new Data Protection Policy. Attended EUGridPMA meeting Bratislava 18-20 Jan. Chaired EGI CSIRT F2F meeting Prague 27-29 Jan. Attended security workshop, APGridPMA and ISGC2016 conference Taipei 13-18 March. Chaired session on Identity Management and spoke on IPv6 security. Attended WLCG Workshop in Lisbon 1-3 Feb.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.13 Security Plans for the future |  | 2016-04-15 |  | This report describes how security will be taken forward in GridPP5, EGI and WLCG. URL
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
C3.8 Security Service Challenge |  | 31/12/2013 (new date 30/06/2016) |  | The previous SSC was delayed until March 2013 so the UK security team decided it did not make sense to run another so soon after this. We plan to run a banning user challenge once the UK sites have properly configured Argus. Ian Neilson has taken over responsibility for this now Ewan McM has left Oxford and will run a full test at some suitable time in first half of 2016, i.e. this will continue into GridPP5.

## Narrative Q216
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to coordinate EGI CSIRT with monthly meetings and co-chair CSIRT F2F in Amsterdam in April followed by the EGI Conference. Participate in EGI CSIRT duty rota and lead UK NGI security team with fortnightly meetings. Continue work on Argus storage banning tests, to be completed in time for a report at GridPP37. One UK security incident reported, an exposed port mapper at Edinburgh. Participated at meetings of IGTF, WLCG security-focussed GDB, Geant TF-CSIRT. Ongoing development work for EGI Cloud Security issues. IPv6 security. |  | Please note that the security effort being booked to GridPP5 is too large in May and June. The excess is funded by EGI.eu but while the income has been agreed, the project codes in STFC SCD for this have not yet been setup. The costs will balance out over the full financial year.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities (11 in total, including 2 critical and 3 high risk) as reported during the quarter. Reported on updated security risk assessment to EGI OMB. Work on updated procedures for Clouds. Attended EGI Conference Amsterdam in April.
Policy | Continue to lead EGI SPG and WLCG security policy. Continue work on several new policies - Data Protection, VM Endorsement, revised AAI Trust policy. Hosted an EUGridPMA meeting at Coseners House (9-11 May). Member of WISE Steering Committee and lead WISE SCIV2-WG. Proposed new WISE working group on Clouds at TNC16 Conference (Prague 12-16 June). Collaborate with EU H2020 EGI-Engage and AARC activities. Member of UK Jisc AAI working group (meeting 25 April).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q316
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Continue to coordinate EGI CSIRT with monthly meetings and host/co-chair CSIRT F2F in Abingdon in September. Participate in EGI CSIRT duty rota and lead UK NGI security team with fortnightly meetings. Work on Argus storage banning tests completed for a report at GridPP37. Participated at meetings of IGTF, WLCG GDB, Geant TF-CSIRT. Ongoing development work for EGI Cloud Security issues. IPv6 security poster for CHEP. |  | Please note that the security effort being booked to GridPP5 is too large in May to August. The excess is funded by EGI.eu but while the income has been agreed, the project codes in STFC SCD for this were not setup until September. The costs will balance out over the full financial year.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities (several critical) as reported during the quarter. Attended DI4R Conference Krakow in September.
Policy | Continue to lead EGI SPG and WLCG security policy. Four policy documents being updated with newer terminology. Leading SCI Version 2 working group within WISE. Played leading role in WISE meeting in Miami linked to XSEDE conference in July and planned for and co-lead of WISE workshop at DI4R in Krakow in September. Collaborate with EU H2020 EGI-Engage and AARC activities. Member of UK Jisc AAI working group (meeting July).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q416
GridPP Quarterly Report
Area | Security
Year | 2016
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. Matt Doidge joined the security team to replace Ewan. A security communication challenge was successfully carried out for the UKNGI and problems identified were fixed. Played active role in WLCG/EGI operational security. Planning took place for the CSIRT F2F meeting in Prague (Jan 2017). Neilson took his share of weekly duties in EGI IRTF. Several security incidents were handled (not including UK). Patching to fix critical vulnerabilities was coordinated - there were two major campaigns. |  | Please note that the security effort booked to GridPP5 was too large in May to August. The excess was funded by EGI.eu but while the income was agreed, the project codes in STFC SCD for this were not setup until September, from when Cornwall and Kelsey are booking less to GridPP. The costs should balance out over the full financial year!
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handle new vulnerabilities (several critical) as reported during the quarter. 11 new issues were reported during the quarter. This included 1 assessed as 'Critical' risk and 3 'High' risk. Seven advisories were issued on the public wiki. Minor updates were made to the Advisory template, including context section describing that the risk is the opinion of SVG in the context of the EGI deployment.
Policy | An SPG F2F meeting was held in Nikhef (2/3 Nov). SPG, in collaboration with EGI-Engage, at this meeting produced several updated policy documents, including a new top-level overall Security Policy. These were successfully passed through the formal approval procedures. EGI was represented at a GEANT/EGI/EUDAT/SURFnet security meeting in Cambridge (8/9 Dec). Started work on IPv6 Security paper for submission to the CHEP2016 proceedings (based on the poster presented at the conference). Plans for the EU H2020 EINFRA-12 proposal were prepared and submitted (Nov).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q117
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. Another security communication challenge was successfully carried out for the UKNGI and problems with two sites were identified were fixed. Played active role in WLCG/EGI operational security. We attended the CSIRT F2F meeting in Prague (Jan 2017). Neilson took his share of weekly duties in EGI IRTF. Several security incidents were handled (not including UK). Patching to fix critical vulnerabilities was coordinated - there was one major campaign (VOMS Admin). |  | Please note that the security effort booked to GridPP5 was too large in May to August. The excess was funded by EGI.eu but while the income was agreed, the project codes in STFC SCD for this were not setup until September, from when Cornwall and Kelsey are booking less to GridPP. The costs have indeed balanced out over the full financial year - 1.5 FTE effort used.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. Eight advisories were issued on the public wiki. Work on security risk assessment with continued active participation in SIG-ISM and the WISE RAW group.
Policy | Work continued on revising EGI/WLCG security policies in collaboration with EGI-Engage. Three new policies formally adopted during the quarter (top-level policy, Data Protection and Acceptable Authentication). Prepared for and delivered security workshop at the ISGC2017 conference in Taipei (March). Completed and submitted the CHEP2016 paper on IPv6 Security. Attended EUGridPMA meeting in Florence (Jan). Lots of work on the WISE SCIv2-WG including a full-day workshop at the Nikhef WISE meeting in Amsterdam (March). New EGI continuation E_INFRA12 proposal was prepared and submitted (now called EOSC-Hub).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q217
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. Played active role in WLCG/EGI operational security. We attended the CSIRT F2F meeting in Lisbon (May 2017). Neilson took his share of weekly duties in EGI IRTF. Several security incidents were handled (not including UK). Patching to fix critical vulnerabilities was coordinated. We attended and presented at the EGI Conference in Catania (May 2017). Organised an IPv6 Security Workshop at RAL as part of UK HEP SYSMAN (June 2017). Continue work on new EGI CSIRT web.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. Eight advisories were issued on the public wiki (4 of which were HIGH). Published WISE security risk assessment template. Leading new SIG-ISM working group 1 on Inventory for Security Officers. Working on updates to SVG strategy and procedures. Continue work on EGI security risk assessment.
Policy | Work continued on revising EGI/WLCG security policies in collaboration with EGI-Engage and AARC2. Two draft Community/VO security policies worked on. Chaired EGI SPG meeting in Karlsruhe (June). Attended EUGridPMA meeting in Ljubljana (May). Finalised and published WISE SCI version 2. SCI version 2 was endorsed on 1st June by many Infrastructures in a ceremony at TNC17. Attended TAGPMA meeting in Washington DC as part of Internet2 Global Summit (April).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q317
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. Ian Neilson went on leave of absence at end of July. UK NGI Security team takes over after he leaves - still run by STFC (David K and Linda C). Played active role in WLCG/EGI operational security. Neilson took his share of weekly duties in EGI IRTF (July only). Patching to fix critical vulnerabilities was coordinated. New EGI CSIRT web was released. EGI report on CSIRT was worked on and then published by EGI Communications. Attended UK IPv6 Security one-day workshop in London. |  | Ian Neilson (on leave of absence from start of August) has resigned from the post of GridPP security officer. STFC has to recruit to replace - in progress. In the meantime other STFC staff (Kelsey and Cornwall) will do some of the work, and spend some of the effort funds.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter.8 advisories were issued on the public wiki (1 of which was CRITICAL and 2 HIGH). Presented updated SVG strategy at the July EGI OMB meeting. Continue to lead GEANT SIG-ISM working group on Inventory for Security Officers; prepare for October meeting.
Policy | Work continued on revising EGI/WLCG security policies in collaboration with EGI-Engage and AARC2. Two draft Community/VO security policies were finalised and distributed for wider comment. Chaired EGI SPG meeting in Amsterdam (July). Organised and co-chaired a one-day WISE workshop as part of the NSF Cybersecurity summit in Arlington VA. Attended and co-organised EUGridPMA/IGTF All Hands meeting in Manchester (Sep). Organised and co-chaired two-day FIM4R meeting at McGill University, Montreal. Talk at WLCG GDB in Sep on Security policies.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q417
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. During absence of GridPP security officer, the UK NGI Security team continues to cover - still run by STFC (David K and Linda C). Played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. Represented WLCG and EGI at APGridPMA meeting in Japan (15 Oct) before HEPiX. DPK member of WLCG AuthZ working group including full pre-GDB meeting 7 Nov. Co-chaired EGI CSIRT F2F meeting Helsinki 15-17 Nov. Much of this planning for start of EOSC-hub in Jan 2018 |  | STFC still has to recruit to replace Ian Neilson - in progress. In the meantime other STFC staff (Kelsey and Cornwall) will do some of the work, and spend some of the effort funds.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter.7 advisories were issued on the public wiki (2 of which were CRITICAL and 1 HIGH). Updated SVG strategy now approved by EGI OMB. Continue to lead GEANT SIG-ISM working group on Inventory for Security Officers; attended 5-6 October meeting in Brussels.
Policy | Work continued on revised EGI/WLCG security policies in collaboration with AARC2. Two draft Community/VO security policies were finalised and sent for final approval. Chaired EGI SPG Vidyo meetings. Attended DI4R conference in Brussels (end of Nov). Lots of planning for EOSC-hub era in 2018.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes