## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Tier-1 |  |  | Close to target
Quarter | Q317 |  |  | Not OK
Reported by | Gareth Smith |  |  | Not yet able to be measured
Suspended
GridPP no. | Tier-1 no. | Description | Source | Owner | Target | Q116 | Q216 | Q316 | Q416 | Q117 | Q217 | Q317 | Comment Q116 | Comment Q216 | Comment Q316 | Comment Q416 | Comment Q117 | Comment Q217 | Comment Q317
1.1.1 | 1.2.7 | Fraction of WLCG MoU commitment for CPU 100 % |  | Andrew Lahiff | 100% | 117.7% | 104.7% | 143.3% | 132% | 142.7% |  | 107%
1.1.2 | 1.6.3 | % met of GRIDPP T1-RB allocation for CPU 100 % |  | Andrew Lahiff | 100% | 127% | 115% | 124.3% | 128.3% | 144.3% | 106.7% | 105.3%
1.1.3 |  | Availability of CE service 99 % |  | Catalin Condurache | 99% | 99.58% | 99.62% | [7 empty] | Problem getting this figure for one of months.
1.1.4 |  | Number of Security Incidents 2 per year |  | Gareth Smith | 2 | 0 | 0 | 0 |  | 0 | 0 | 0
1.1.5 |  | # level 3 incidents(newly entered or active) in disaster management system 0 |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Escalated problem LHCb had with Castor while running stipping/merging campain. Led to reverting LHCb Castor SRM upgrade.
1.1.6 |  | # level 4 incidents (newly entered or active) in disaster management system 0 |  | Andrew Sansum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.7 |  | Percentage of GRIDPP4 Staff in Post 93 % |  | Andrew Sansum | 93% | 94% | 97% | 100% | 90% | 90%
1.2.1 | 1.2.8 | Fraction of WLCG MoU commitment for Disk 100 % |  | Andrew Lahiff | 100% | 168% | 125% | 125% | 125% | 202.7% |  | 140%
1.2.2 | 1.2.9 | Fraction of WLCG MoU commitment for Tape 100 % |  | Andrew Lahiff | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2.3 | 1.6.1 | % met of GRIDPP T1RB Allocation for Tape 100 % |  | Andrew Lahiff | 100% | 100% | 100% | 100% | 110% | 104% | 100% | 100%
1.2.4 | 1.6.2 | % met of GRIDPP T1RB Allocation for Disk 100 % |  | Andrew Lahiff | 100% | 132% | 98.67% | 101% | 108% | 113.7% |  | 115%
1.2.5 | 7.1.3 | # Storage node failures leading to filesystem loss or damage |  | Kashif Hafeez | 2 | 0.66667 | 0 | 0 | 0.33333 | 0 | 0 | 0.33333
1.2.6 | 7.1.4 | % Lost disk server hours due to hardware problems over deployed base |  | Kashif Hafeez | 1% | 0.23% | 0.3267% | 0.1867% | 0.3% | 0.29% | 0.3% | 0.1533%
1.2.7 | 7.3.1 | Damaged tapes/month, leading to data loss |  | Tim Folkes | 1 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0.33333
1.2.8 | 5.1.2 | CASTOR SAM tests: ATLAS VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 96.33% | 99.67% | 100% | 100% | 92.33% | 92.33% | 98% | Poor availability in Jan. Problem with OPN link caused incoming tests to fail. |  |  |  | There were several spells of poor test results for Talas. The first (early Feb) coincided with a tape recall exercise and tests time out. There were then two further spells of test failures (late Feb, early March). We identified that the Atlas Test was not specifying a space token on write and then (depending on what else was going on) the file was not found in later stages of the SRM test. | There was a problem around to 30th April/1st May when one of the Atlas disks filled up and we failed tests consistently. There were also intermittent test failures before the Castor Atlas 2.1.16 upgrade which was done on the 25th May. | In first part of quarter there were problems that appeared in the SRMs that were thought to be due to Castor performance issues. The merging of the small AtlasScratchDisk pool into a larger disk pool alleviated these. (See Narrative).
1.2.9 | 5.1.1 | CASTOR SAM tests: ALICE VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 100% | 100% | 99.67% | 100% | 95.67% | 100% | 100% |  |  |  |  | Missing ALICE-specific xroot component after Castor 2.1.15 upgrade led to several days of test failure (inlcuing a weekend).
1.2.10 | 5.1.3 | CASTOR SAM tests: CMS VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 96.67% | 99.33% | 99.33% | 96.67% | 97.67% | 89.67% | 94% | Poor availability in Jan. Problem with OPN link caused incoming tests to fail. Plus tests run against CMSTape area in Castor which was under high load for a couple of days. |  |  |  | There have been sporadic failures of the CMS SAM tests against the SRMs (timeouts) throught this period. Effort was directed at Castor upgrades (SRM and then Castor itself to improve this). | During this period we had a high level of failure of the CMS SRM SAM tests with timeout errors. There was also some specific test failures on top of this: 9/10/11th April - Problems with CMS Castor (transfermanager); 3rd May: glexec problem; 14/15 May - problems writing into Castor CMS. 24/25 June - test ailing with CMSDisk full. | At the start of the quarter there was a high rate of SRM tests failures (timeouts) but in the middle of the quarter this improved - although we do not know why. (See narrative). The September figure was brought down by CMSDisk becoming full causing a very high rate of SRM test failures for a couple fo days.
1.2.11 | 5.1.4 | CASTOR SAM tests: LHCb VO | Metric calculation changed in 12Q1 Now harder | Rob Appleyard | 99% | 98.33% | 99% | 99.67% | 99.67% | 97.33% | 97% | 95.67% | Poor availability in Jan. Problem with OPN link caused incoming tests to fail. |  |  |  | Sporadic SRM test failures through the quarter. Some specific problems with the SRM led to more test failures on one or two days. | Test failures dominated by problems in first part of quarter The causes are as detailed in the narrative section. (These led to the reversion of a previous SRM update and a problem with TURLs returned after the Castor upgrade.) | Figure dominated by September availability at 88%. Problem with two disk servers added into Castor gave problems for SAM tests although LHCb did did not report problems. Also noted in Narrative section.
1.2.12 | 7.3.4 | Reliability of tape robot 99 % |  | Tim Folkes | 99% | 100% | 92.33% | 100% | 100% | 100% | 100% | 99.72% | Significant problems with the tape library in May and June. Initially hardware then stability of control software.
1.3.1 | 1.2.2 | WLCG Service Availability Target (set lower by WLCG than MoU, taken from OPS availability) 97 % |  | Gareth Smith | 97% | 99.33% | 99% | 100% | 100% | 99.67% | 98.67% | 99.57%
1.3.2 | 1.2.11 | WLCG Service Availability for Alice 97 % |  | Gareth Smith | 97% | 100% | 100% | 99.67% | 100% | 95.67% | 100% | 100% |  |  |  |  | See comment for metric 1.2.9.
1.3.3 | 1.2.12 | WLCG Service Availability for ATLAS 97 % |  | Gareth Smith | 97% | 98% | 100% | 100% | 100% | 92.33% | 92.33% | 98% |  |  |  |  | See comment for metric 1.2.8. | See comment for metric 1.2.8. | See comment for metric 1.2.8.
1.3.4 | 1.2.13 | WLCG Service Availability for CMS 97 % |  | Gareth Smith | 97% | 97% | 99% | 99.33% | 96.67% | 97.67% | 89.67% | 94% | Q116 CMS tests poor in January. There was a problem on the network bypass' that affected all VOs. For CMS the SRM tests run agains CMSTape which was under high load and saw problems during January. |  |  |  | See comment for metric 1.2.10 above. Plus in March CMS CE tests suffered from aa problem with argus plus another when a Hyperviosor failed affecting a number of virtual machines. This in turn affected CMS CE tests. | See comment for metric 1.2.10 | See comment for metric 1.2.10
1.3.5 | 1.2.14 | WLCG Service Availability for LHCB 97 % |  | Gareth Smith | 97% | 98.33% | 99.33% | 99.67% | 99.67% | 97.33% | 97% | 95.67% |  |  |  |  | See comment for metric 1.2.11. | See comment for metric 1.2.11 | See comment for metric 1.2.11
1.3.6 | 1.2.4 & 1.2.5 | Respond to pager within 2 hours 95 % |  | Gareth Smith | 95% | 100% | 95% | 100% | 100% | 100% | 100% | 100% | Failed for one out of hours callout in May. There were low statistics with only a total of 5 callouts out of hours in the month.
1.3.7 | 4.1.2 | Number of GGUS Tickets not responded to within two hours . |  | Gareth Smith | 3 per month | 0.66667 | 0 | 0.33333 | 1.3333 | 0.33333 | 0.33333 | 2.3333
1.3.8 | 1.6.4 | Job Efficiency (CPU/Wall) 70 % |  | Andrew Lahiff | 70% | 83.67% | 86% | 89.33% | 0.83333 | 0.78333 | 0.77333 | 87.33%
1.3.9 | 1.6.5 | Farm Occupancy 70 % |  | Andrew Lahiff | 70% | 88.67% | 92% | 92% | 0.94667 | 0.94333 | 0.95 | 90.67%
1.3.10 | 1.6.6 | Percentage of available T1 Disk 1 used in quarter 20 % |  | Andrew Lahiff | 20% | 78.33% | 77.33% | 79% | 0.76667 | 0.77333 |  | 46.67%
1.3.11 | 7.3.5 | Used tape capacity (TB) |  | Tim Folkes | 5416 | 15744.6667 | 17233.3333 | 19006.6667 | 21726.6667 | 22450 | 23400 | 26433.3333
NGI
3.4.1 |  | UK CPU and storage delivered to EGI |  | Ian Collier
3.4.2 |  | Monthly timesheets complete by 10th of each month |  | Ian Collier
3.4.3 |  | GridPP staff PM delivered as required |  | Ian Collier
3.4.4 |  | GOCDB Availability |  | Ian Collier | >99% |  | (98.96, 100, 100) == 99.53 | (100,100,100) ==100 | (99.97, 99.61, 100) ==99.86 |  |  | 100% |  |  |  |  | Waiting on EGI to publish their stats. A quick look at Nagios over the quarter shows no availability issues.
3.4.5 |  | APEL Availability |  | Ian Collier | >99% |  | 99.92 | 100 |  | 100 | 99.96 | 100

## Milestones
GridPP Quarterly Report |  |  |  | Complete |  | Proposed to be Rescheduled
Area | Tier-1 |  |  | Overdue |  | Likely to be late
Quarter | Q317 |  |  | Not yet due |  | Proposed Milestone change
Reported by | Gareth Smith |  |  | Suspended |  | Query
Based on Milestones 1.3d-2
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.4.1 | Produce the purchasing plan | Andrew Sansum | 2016-06-01 |  |  | A purchasing plan swas produced but changes in the amount of money available require the plan to be re-visited.
1.4.2 | FY16 Capacity order placed | Andrew Sansum | 2016-11-01 | 2017-02-01 |  | Order for CPU & disk storage received by vendor mid-Feb.
1.4.3 | FY16 Purchase in production | Andrew Sansum | 2017-04-01 |  |  | CPU in use. Storage awaiting further work in Echo.
1.4.4 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2017-05-01 |  |  | As shown in metrics.
1.4.5 | Produce the purchasing plan | Andrew Sansum | 2017-06-01 |  |  | Planning completed so that tenders could be issued.
1.4.6 | FY17 Capacity order placed | Andrew Sansum | 2017-11-01 |  |  | Tenders issued at end of November.
1.4.7 | FY17 Purchase in production | Andrew Sansum | 2018-04-01 |  |  | It may take a while to get the disk servers into Echo.
1.4.8 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2018-05-01
1.4.9 | Produce the purchasing plan | Andrew Sansum | 2018-06-01
1.4.10 | FY18 Capacity order placed | Andrew Sansum | 2018-11-01
1.4.11 | FY18 Purchase in production | Andrew Sansum | 2019-04-01
1.4.12 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2019-05-01
1.4.13 | Produce the purchasing plan | Andrew Sansum | 2019-06-01
1.4.14 | FY19 Capacity order placed | Andrew Sansum | 2019-11-01
1.4.15 | FY19 Purchase in production | Andrew Sansum | 2020-04-01
1.4.16 | Tier-1 WLCG MoU commitments met | Andrew Sansum | 2020-05-01

## Manpower Q116
GridPP Quarterly Report
Area | Tier-1
Quarter | Q116
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia | 3.8 | 3.8 | 3.8 |  |  |  |  | 11.4 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 4.55 | 4.55 | 4.55 |  |  |  | reduction as increased cost sharing with ISIS | 13.65 | 0
Tier-1 | CASTOR/Tape | Canning , De Witt, Folkes, Prosser, Davies,Appleyard, Johnson | 4.6 | 4.6 | 4.6 |  |  |  | A temporary increase of 1 FTE over previous quarter - code developer effort for CEPH xrootd/gridftp plug in. | 13.8 | 0
Tier-1 | Database | Sierra, Smirnov, Packer | 1.1 | 1.1 | 1.1 |  |  |  |  | 3.3
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | Load sharing of T1 Manager role amongst several staff. But not sustainable long term | 0.6 | 0
Tier-1 | Operations | Norris, Patel, Sheppard, Knightley | 0.4 | 0.4 | 0.4 | 0.9 | 0.9 | 0.9 |  | 1.2 | 2.7
Tier-1 | Network |  |  |  |  | 0.5 | 0.5 | 0.5 |  | 0 | 1.5
Tier-1 | Production | Smith, Idiculla, Kelly | 2.8 | 2.8 | 2.8 |  |  |  |  | 8.4 | 0
Total |  |  | 17.45 | 17.45 | 17.45 | 1.4 | 1.4 | 1.4

## Manpower Q216
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia | 3.8 | 3.8 | 3.8 |  |  |  | 11.4 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 4.13 | 4.13 | 4.13 |  |  |  | 12.39 | 0
Tier-1 | CASTOR/Tape | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | 3.8 | 3.8 | 3.8 |  |  |  | 11.4 | 0
Tier-1 | Database | Smirnov, Packer | 0.85 | 0.85 | 0.85 |  |  |  | 2.55
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | 0.6 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | 2.8 | 2.8 | 2.8 |  |  |  | 8.4 | 0
Total |  |  | 15.58 | 15.58 | 15.58 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5

## Manpower Q316
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia, Chambers, Masaitis, Gale | 4.5 | 4.5 | 5.9 |  |  |  | 14.9 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 4.6297 | 4.07 | 4.07 |  |  |  | 12.7697 | 0
Tier-1 | CASTOR/Tape | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | 4.4 | 4.4 | 4.4 |  |  |  | 13.2 | 0
Tier-1 | Database | Smirnov, Packer, Contractor | 0.85 | 1.35 | 1.35 |  |  |  | 3.55 | 0
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | 0.6 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | 2.8 | 2.8 | 2.2054 |  |  |  | 7.8054 | 0
Total |  |  | 17.3797 | 17.32 | 18.1254 | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL |  | 0.7 | 0.7 | 0.7 |  |  |  | 2.1 | 0
Tier-1 | GOCDB |  | 0.29 | 0.29 | 0.278 |  |  |  | 0.858 | 0
Total |  |  | 0.99 | 0.99 | 0.978 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE
Note on B22: gronbech: Expect 0.3FTE

## Manpower Q416
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia, Chambers, Masaitis, Gale | 5.2 | 4.5 | 4.5 |  |  |  | 14.2 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 3.07 | 3.07 | 3.07 |  |  |  | 9.21 | 0
Tier-1 | CASTOR/Tape/CEPH | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | 4.5 | 4.5 | 3.9 |  |  |  | 12.9 | 0
Tier-1 | Database | Smirnov, Packer, Contractor | 1.35 | 1.35 | 1.8 |  |  |  | 4.5 | 0
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | 0.6 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | 2.0054 | 2.0054 | 2.0054 |  |  |  | 6.0162 | 0
Total |  |  | 16.3254 | 15.6254 | 15.4754 | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL | Coveney, Corbett | 0.38 | 0 | 0.28 |  |  |  | 0.66 | 0
Tier-1 | GOCDB | Ryall, Meredith | 0.29 | 0.29 | 0.278 |  |  |  | 0.858 | 0
Total |  |  | 0.67 | 0.29 | 0.558 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE
Note on B22: gronbech: Expect 0.3FTE

## Manpower Q117
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317 | [7 empty] | 16.3254 | 15.6254 | 15.4754 | 16.1054 | 15.6054 | 15.6054
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded | [5 empty] | 0.90231
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia, Chambers, Masaitis, Gale | 4.5 | 4.5 | 4.5 |  |  |  | 13.5 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 3.7 | 3.7 | 3.7 |  |  |  | 11.1 | 0
Tier-1 | CASTOR/Tape/CEPH | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | 3.9 | 3.9 | 3.9 |  |  |  | 11.7 | 0 |  |  |  |  | 15.7721
Tier-1 | Database | Smirnov, Packer, | 1.8 | 1.3 | 1.3 |  |  |  | 4.4 | 0
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | 0.6 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | 2.0054 | 2.0054 | 2.0054 |  |  |  | 6.0162 | 0
Total |  |  | 16.1054 | 15.6054 | 15.6054 | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL | Coveney, Corbett | 0.37 | 0.37 | 0.37 |  |  |  | 1.11 | 0
Tier-1 | GOCDB | Ryall, Meredith | 0.29 | 0.29 | 0.278 |  |  |  | 0.858 | 0
Total |  |  | 0.66 | 0.66 | 0.648 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE
Note on B22: gronbech: Expect 0.3FTE

## Manpower Q217
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317 | [7 empty] | 16.3254 | 15.6254 | 15.4754 | 16.1054 | 15.6054 | 15.6054
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded | [5 empty] | 0.90231
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia, Chambers, Masaitis, Gale | [6 empty] | 0 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | [6 empty] | 0 | 0
Tier-1 | CASTOR/Tape/CEPH | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | [6 empty] | 0 | 0 |  |  |  |  | 0
Tier-1 | Database | Smirnov, Packer, | [6 empty] | 0 | 0
Tier-1 | Management | Sansum | [6 empty] | 0 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | [6 empty] | 0 | 0
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL | Coveney, Corbett | [6 empty] | 0 | 0
Tier-1 | GOCDB | Ryall, Meredith | 0 | 0 | 0 |  |  |  | 0 | 0
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE
Note on B22: gronbech: Expect 0.3FTE

## Manpower Q317
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317 | [7 empty] | 16.3254 | 15.6254 | 15.4754 | 16.1054 | 15.6054 | 15.6054
Reported by | Andrew Sansum
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded | [5 empty] | 0.90231
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | Fabric | Bly, Hafeez, Harper, Walia, Chambers, Masaitis, Gale | 3.8 | 4 | 4 |  |  |  | 11.8 | 0
Tier-1 | Grid | Condurache, Adams, Collier, Ryall, Dibbo, Williams | 3.7297 | 3.7297 | 3.5297 |  |  |  | 10.9892 | 0
Tier-1 | CASTOR/Tape/CEPH | Canning , Folkes, Prosser, Appleyard, Johnson,Vasilakakos ,Patargias , Packer | 4.1 | 4.1 | 3.5 |  |  |  | 11.7 | 0 |  |  |  |  | 14.5064
Tier-1 | Database | Smirnov, Packer, | 1.3 | 1.3 | 1.3 |  |  |  | 3.9 | 0
Tier-1 | Management | Sansum | 0.2 | 0.2 | 0.2 |  |  |  | 0.6 | 0
Tier-1 | Production | Smith, Idiculla, Kelly | 1.31 | 1.31 | 1.91 |  |  |  | 4.53 | 0
Total |  |  | 14.4397 | 14.6397 | 14.4397 | 0 | 0 | 0
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | GRIDPP Funded Name(s) | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Tier-1 | APEL | Coveney, Corbett | 0.7 | 0.7 | 0.7 |  |  |  | 2.1 | 0
Tier-1 | GOCDB | Ryall | 0 | 0 | 0 |  |  |  | 0 | 0
Total |  |  | 0.7 | 0.7 | 0.7 | 0 | 0 | 0
Machine room operations are now fully funded by SCD in GridPP5
Site networking is not funded by either SCD or GridPP in GridPP5
Note on B21: gronbech: expect 0.7FTE
Note on B22: gronbech: Expect 0.3FTE

## Narrative Q116
GridPP Quarterly Report
Area | Tier-1
Quarter | q116
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General |  |  | Two members of staff left at the end of this quarter: Shaun De Witt (Castor Team) Juan Sierra (Database Team)
Management | The Tier1 manager role is being filled by 20% of Andrew.
CPU | Capacity Purchases received by end of quarter.
Disk | Capacity Purchase received by end of quarter. Eight Disk servers, with a total capacity of almost 900TB added to Atlas Castor. |  | There have been problems with one of the older batches of disk servers (CV'11) used in the tape caches. Action has been taken to mitigate this (firmware updates, using spare disks from a different manufacturer that were in a decommissioned batch of servers). Some new disk servers are being purchased to go into the disk caches so that the older servers can be retired.
CASTOR |  |  | The Castor 2.1.15 update has not been rolled out. Early tests showed load problems on the Oracle Database. Tests have been hidered by problems within the test database system which has had to be rebuilt.
Grid Deployment
Core Services
Production Team
Network | We have seen increased use of the OPN link for part of this quarter. |  | There have been a few network problems: Twice during the quarter there were problems with one of the four links between the 'UKLight' router and the Tier1 core network. Also there was a site networking problem at the end of March. The Tier1 router pair didn't failover owing to a configuraion error.
Machine Room Operations
Database team |  |  | Following the deoparture of Juan Sierra the Database Team is down to one person - which is below the critical threshold. The use of a contractor and the recruitment of more DB Admins are being followed up as a matter of urgency.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project.
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
The Tier-1 project to replace (remove) the old UKLight router has been delayed owing to Tier-1 team staff departures and operational problems. Network bandwidth limitations on the Tier-1 links to JANET. STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set. Following a review of the UKLight router replacement a simpler course of action (as compared to that previously proposed) was agreed. Progress towards this replacement is being tracked by the Tier1 Production Manager.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
A4.5 Tier-1 WLCG MoU commitments met |  | 2016-03-31 |  | MOU commitments have been met. Capacity order received.
A4.1 Internal strategic and technology review |  | 2016-03-01 |  | Propose Re-scheduling: Was awaiting completion of GridPP5 bid. Partly dependent on appointment of new Tier1 manager.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
A4.2 Produce the purchasing plan |  | Jun '16
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
A1.16 External review of operation |  | 2015-10-01 |  | propose autumn-2016 | A review has been requested by the PMB for this timescale.
A1.17 Strategic and operations plan agreed |  | 2015-06-01 |  | propose 01/Sep/2016 | This will need to take into account the GridPP5 bid and may depend on when a new Tier1 Manager is recruited.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output
Capacity Procurements Started |  | 2016-07-01
Capacity Order Placed |  | 2016-10-01 |  | Order placed.
Note on H49: Unable to set until new LHC schedule and revised experiment resource requirements
Note on H50: Unable to set until new LHC schedule and revised experiment resource requirements

## Narrative Q216
GridPP Quarterly Report
Area | Tier-1
Quarter | q216
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General
Management | The Tier1 manager role continues to be covered by 20% of Andrew.
CPU | One of the two batches of capacity CPU purchases (that from XMA) was put into production at the end of May. We have sufficient capacity in place to meet MOU requirements. |  | Deployment to production of the second of the batches of capacity CPU purchases (that from HPE) has not yet taken place owing ting to various problems post delivery. However, MOU commitments already met.
Disk | Capacity procurement of disk delivered and readied for putting into ECHO CEPH cluster.
CASTOR | Castor "GEN Scratch" storage atrea was decommissioned slightly simplifying the Castor set-up. |  | The Castor 2.1.15 update has still not been rolled out. The test database system has been rebuilt. However work has not progressd as fast as we would like owing to the limited manpower available.
Grid Deployment | HAProxy load balancers introduced in front of the production and test FTS3 services. One of the three production WMS systems was decommissioned simplifying the service. Machine Job Features rolled out across batch farm.
Core Services | The migration of the Atlas data from 'C' to 'D' tapes was stared in this period. By end June it was around 50% complete. |  | During May and into June there were significant problems with the tape library leading to periods when it was not available. This was caused by three separate issues: - Significant hardware problem with the fix confused by a spare board failing soon after installation. - Faulty replacement handbot within the library led to safety concern. - Problem with library control software hanging.
Production Team
Network |  |  | We are seeing increased usage of the OPN link to/from CERN with the inbound traffic saturating the 10Gbit link for increasingly long periods. There was a problem with the RAL core networkin mid-April, strating late on a Friday and continuing until the Saturday afternoon. We experienced four significant breaks in connectivity during this period. A fifteen hour outage was been declared in the GOC DB.
Machine Room Operations |  |  | There was a failure of the air conditioning to the machine room early in May. Both chillers and pumps stopped. After around 30 minutes the air conditioning (pumps & chillers) was restarted and temperatures fell back down. See blog post at: http://www.gridpp.rl.ac.uk/blog/2016/05/10/r89-water-pump-outage/
Database team |  |  | During the quarter we had only one person in the Database Team - which is below the critical threshold. Work on finding a contractor and the recruitment of more DB Admins were actvely followed up.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
The Tier-1 project to replace (remove) the old UKLight router has been delayed owing to Tier-1 team staff departures and operational problems. Network bandwidth limitations on the Tier-1 links to JANET. STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set. Following a review of the UKLight router replacement a simpler course of action (as compared to that previously proposed) was agreed. Progress towards this replacement is being tracked by the Tier1 Production Manager.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
A4.2 Produce the purchasing plan |  | Jun '16 |  | Taking this as the purchasing plan for spendind within the 2016/17 FY. Plan has been produced but not yet disseminated.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
Capacity procurements started |  | July '16
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
A1.16 External review of operation |  | 2015-10-01 |  | propose autumn-2016 | A review has been requested by the PMB for this timescale.
A1.17 Strategic and operations plan agreed |  | 2015-06-01 |  | propose 01/Sep/2016 | This will need to take into account the GridPP5 bid and may depend on when a new Tier1 Manager is recruited.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output
Capacity Procurements Started |  | 2016-07-01
Capacity Order Placed |  | 2016-10-01 |  | Order placed.
Tier-1 WLCG MoU commitments met |  | 2017-03-01
Note on H49: Unable to set until new LHC schedule and revised experiment resource requirements
Note on H50: Unable to set until new LHC schedule and revised experiment resource requirements

## Narrative Q316
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General | Contractor (Phani Yeluri) started to work in Database Team in early July. |  | One members of staff left at the end of this quarter: Tiju Idiculla (Productio Team) In addition one person reduced their hours (to around 45%) at the end of August: Gareth Smith (Production Team)
Management | The Tier1 manager role continues to be covered by 20% of Andrew.
CPU | We have sufficient capacity in place to meet MOU requirements. The LSST VO was enabled on the batch farm at the end of July. |  | The second of the batches of capacity CPU purchases (that from HPE) is not yet in full production. It is being used to set-up and test a new configuration of worker nodes for use with CEPH. (These will run SL7 with an xroot gateway with the "worker node" in a SL6 container.)
Disk | Three disk servers each of 57TB capacity have been deployed into each of the following tape caches: AtlasTape, cmsTape, lhcbRawRdst. (I.e. a total of nine servers) at the end of July.
CASTOR
Grid Deployment | The database behind the LFC was moved to new hardware at the start of August. During September services running on the Microsoft Hyper-V 2008 infrastructure were moved to the Hyper-V 2012 infrastrcucture.
Core Services | Problems reported in last quarter on the tape libraries were resolved early in July. Since then these have operated stably. The migration of the Atlas data from 'C' to 'D' tapes was completed in August. Additional 'D' drives have been ordered (and at the time of this report delivered) to provide additional capacity ahead of migrating the LHCb data.
Production Team |  |  | Significant loss in effort in Production Team.
Network | Following saturation of the single 'primary' 10Gbit OPN link at the start of this quarter the OPN connection was reconfigured to use both 10Gbit links at the start of August. On Wednesday 5th October (just after period of report) the UKLight Router was replaced. This has also enabled a a 40 GBit connection to the RAL border routers (i.e. giving a datapath of up to 40Gbit for the bypass connection.) We have seen a significant increase in traffic over the bypass route since this change - well exceeding the previous 10Gbit limit. |  | At the end of August there was a problem with packet loss seen across a part of the Tier1 network. Finally traced to a faulty transceiver which was replaced.
Machine Room Operations | A brief power dip affected parts of the RAL site on Wedesday afternoon, 14th Sep. The R89 machine room was OK. However, it was seen by equipment in the Atlas building. This had no affect on our services.
Database team
APEL | No major problems encountered. Service ran smoothly during this period. Response time for GGUS tickets well within OLA. Improved engagement with GridPP through attendance at GridPP37 |  | Period saw reduced staff numbers due to leave. However, only three days had no core APEL staff available and some limited cover was provided by colleagues.
GOCDB | Deployed v5.7 onto gocdb-test instance to include cursor-based paging and replace offset-based paging. Work with EGI + WLCG InfoSysTF to agree on new extensions for new write API and ServiceEndpoint extensions (longer term aim of reducing WLCG dependency on BDII)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
Changes to purchasing plan may add delays and lead to purchasing items earlier at less favourable prices/performance. |  | Purchasing against the revised plan will be prioritsied to expedite the processing and examined thoroughly.
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
1.4.2 FY16 Capacity order placed |  | Nov '16 |  | Needs the plan to be finalised.
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
1.4.1 Produce the purchasing plan |  | Jun '16 |  | Propose Oct/Nov '16 | Taking this as the purchasing plan for spendind within the 2016/17 FY. A plan was produced but has had to be changed as some spend originally earmarked for Tier2s is being moved to the Tier1.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q416
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General | In response to Security announcement CVE-2016-5195 a number of services were stopped. In essence we stopped the batch system on Monday (24th Oct). Storage (Castor) was able to continue running. These services were resumed two days later after a patch had been received and applied. In November test data was received from a second Dirac site (Leicester).
Management | The Tier1 manager role continues to be covered by 20% of Andrew.
CPU | The second tranche of worker nodes (from HPE) were reinstalled with SL6 put into service at the start of December. This followed a period of testing with another configuration in readiness for CEPH deployment. |  | In early October it was realized we had been running for a long time with a limit on the number of CMS batch jobs that was well below pledge. This limit was then quickly raised. A post mortem carried out to understand how that had arisen.
Disk | In November additional disk servers were added to Castor: For Alice 5 extra servers, each 100TB. For LHCb 12 additional servers, each 120TB. This will enable both an increase in capacity and the withdrawal of some older (smaller capacity) disk servers. In December firmware updates on one batch of older disk servers. (Work continued in next quarter on another batch).
CASTOR | Early December the small LhcbUser disk pool was merged into the larger LhcbDst pool. This eased performance issues seen with small disk pools.
Grid Deployment
Core Services | In November started writing LHCb data to the 'D' tapes and migrating their data onto these.
Production Team | During this time Production Team effort was significantly reduced with one full time member of staff (who was away for some of the time) plus less than 50% of the Team leader. An apprentice, at RAL for 3 days per week, started working in the team at teh start of a 6-month placement.
Network | On the 5th October the UKLight Router was replaced. As part of this the 'bypass' route for Tier1 data to non-OPN nodes was increased from 10 to 40Gbit. |  | A long running problem of low-level packet loss was resolved when the old UKLight router was replaced.
Machine Room Operations | In early December there was a problem overnight with one of the Power Distribution Units to a rack in the UPS room which affected two network switches - which in turn affected some core services (including the TopBDII). The same PDU again showed this problem on the 23rd December and was swapped out ahead of the Christmas break.
Database team | Use of a contactor continued during this time as the database team was down to one member of staff. (When did Miguel start??)
APEL
GOCDB | GOCDB v5.7 was released into production, which inclues: a new write API for custom properties (as requested by WLCG InfoSys TF); optional cursor paging of API methods; and new attributes for some entities to enable ARGO monitoring to move away from relying on the BDII. A number of new service types have been added which have been contributed to GLUE2. No OLA violations for availability/reliablity and response times. |  | No major issues
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
Changes to purchasing plan may add delays and lead to purchasing items earlier at less favourable prices/performance. |  | Purchasing against the revised plan will be prioritsied to expedite the processing and examined thoroughly.
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
1.4.2 FY16 Capacity order placed |  | Nov '16 |  | Needs the plan to be finalised.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
1.4.1 Produce the purchasing plan |  | Jun '16 |  | Propose Oct/Nov '16 | Taking this as the purchasing plan for spendind within the 2016/17 FY. A plan was produced but has had to be changed as some spend originally earmarked for Tier2s is being moved to the Tier1.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q117
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General
Management | The Tier1 manager role continues to be covered by 20% of Andrew. Database team now up to strength with two members of staff. |  | Production team running well below staff complement. The plavcement of an apprentice in the team for siix months (Oct '16 - Mar '17) is helping.
CPU
Disk | At the start of the year firmware updates were made to RAID cards in the Viglen '13 batch of disk servers. Some of the 100TB ’14 generation disk servershave been delpoyed in Castor. (These servers were originally used to test CEPH).
CASTOR | Castor was updated to version 2.1.15 during January/February. At the end of the quarter a start was made on upgrading the SRMs to version 2.1.16 (and to run on SL6) although performance problems were subsequently encountered. |  | Following the upgrade of the GEN instance to 2.1.15 there was a problem with ALICE access as a special version of the xroot component is needed which we did not have available. This caused a significant loss of availability for ALICE (failed between the 26th and 30th January) There were a number of instances of problems with Castor access during this quarter.
ECHO | In February ECHO was upgraded to the kraken version of CEPH. Resiliency tests have also been carried out. Two additional 'MON' boxes are being set-up bringing the total to five. The existing three can cope with normal activity but the additional ones would speed up recoveries and starts. Two additional gateway nodes are also being set-up (also bringing the total to five) which will improve bandwidth. Out of hours cover by the ECHO team is being piloted. |  | CEPH ECHO: There was a problem with one 'placement group' that resulted in a loss of data (2000 Atlas files). This has been followed up and understood - in conjunction with the CEPH developers and was presented in a CEPH forum. The understanding gained means that should this recur there would be no data loss.
Grid Deployment | The site and Top BDIIs were put behind load balancers. A review of WMS usage shows ongoing interest in this service.
Core Services | Migration of LHCb data from 'C' to 'D' tapes has been completed. All Tier1 data is now on T10KD tapes. Migration of services off SL5 as it has reached end of life. |  | There were two problems when a hypervisor in the Hyper-V virtual infrastructure crashing. The VMs were recovered but there was an effect on services while this happened.
Production Team
Network | IPv6 has been enabled on the various routers and in early March was available through to the Tier1 production network. Ahead of that IPv6 was disabled on systems (via quattor) and will be re-enabled on a case-by-case basis. The perfsonar nodes on the production Tier1 network now also run tests over IPv6.
Machine Room Operations | Two of the chillers were replaced. One of those replaced had partly failed.
Database team
APEL | No major problems encountered. Service ran smoothly during this period. Response time for GGUS tickets well within OLA. Most machines migrated off SL5. |  | Delayed hardware has meant that one machine is yet to be migrated off SL5. John Gordon retired in this period, but still in touch and helping occasionally.
GOCDB | EGI Ops Tools Advisory Group to prioritise GOCDB roadmap until the end of EGI-Engage: https://indico.egi.eu/indico/event/3296/ Roadmap updated: https://wiki.egi.eu/wiki/EGI-Engage:TASK_JRA1.4_Operations_Tools#GOCDB Work started on write API extensions. Work to virtualise the GOCDB failover instance under way. Downtime classification changes for Scheduled/Unscheduled downtimes presented to EGI, no resolution yet, ongoing. |  | Reduced developer effort during Q117 (GR ~1mth leave, DM reduced effort). No major issues.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
Changes to purchasing plan may add delays and lead to purchasing items earlier at less favourable prices/performance. |  | Purchasing against the revised plan will be prioritsied to expedite the processing and examined thoroughly.
2017 Capacity produrement may be impacted by delays introduced by SBS procurement process. |  | STFC recognises that delays in the SBS procurement process are a risk to the whole organisation. STFC has introduced its own oversight of this process. The Tier1 will need to commence its procurements significantly earlier than last year in order to meet its deadlines. The purcahsing of the FY16 equipment was done at the very last minute (and equipment received just before the end of the FY). Use as made of an existing Framework agreement to achieve this.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
CERN will stop support for Castor. |  | CERN have announces a replacement for Castor (for tape). An evaluation of the best way forward for future tape storage is being made.
CEPH ECHO will not deliver storage reliably or be able to deliver the necessary access bandwidth. |  | Tight management of the ECHO project is carefuly monitoring progress. A detailed risk register for ECHO has been produced.
Oracle withdraw support for existing Tape infrastucture. |  | Oracle have indicated that the next generation of tape drives/mdeia will not be produced. Track Oracle timeline for tape/media/librray support and be aware of the directions being taken by other sites.
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
STFC has been unable to prioritise IPV6 developments necessary to allow the Tier-1 to to meet its WLCG milestone of Perfsonar access over IPV6. |  | Tier-1 is setting up a new network management meeting that will include members of site networking group to oversee tier-1 network projects. Tier-1 service manager has been invited to attend the STFC NetTDA where site network development priorities are set.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
1.4.2 FY16 Capacity order placed |  | Nov '16 |  | The orders were placed and equipment received by the end of the FY.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
1.4.3. FY16 Purchase in production |  | April '17 |  | Equipment delivered but time needed for cabling and testing. Will be late.
1.4.4. Tier-1 WLCG MoU commitments met |  | May '17
1.4.5. Produce the purchasing plan |  | June '17
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
1.4.1 Produce the purchasing plan |  | Jun '16 |  | Propose Oct/Nov '16 | Taking this as the purchasing plan for spendind within the 2016/17 FY. A plan was produced but has had to be changed as some spend originally earmarked for Tier2s is being moved to the Tier1.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q217
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General
Management | The Tier1 manager role continues to be covered by 20% of Andrew. |  | Production team running well below staff complement.
CPU | During the quarter a start was made on installing xrootd gateways on worker nodes.
Disk |  |  | We started seeing a high rate of cases where the RAID cards in one batch of disk servers (OCF '14) were flagging problems in disk drives but the vendor was finding no fault with the returned drives. In response during June a the firmware in all the RAID cards in this batch were updated to the latest version.
CASTOR | Castor and the SRMs were upgraded to version 2.1.16-13. This put us on a version similar to that running at CERN. The upgrade of the SRMs (both a Castor update and OS update to SL6) meant we no longer had and external facining systems running SL5. |  | There were significant problems with Castor for LHCb that led to the previous SRM update (on 23rd March) being reverted. This gave significant improvement. There were some Castor problems following the upgrade to version 2.1.16-13 in May. Notably a problem for LHCB when a TURL returned by the SRM did not always work when used for xroot access. Also, Atlas encountered a problem where double-slashes ("//") in the incoming request filenames caused problems. These issues were resolved and led to more stable Castor operations. There was a steady rate of CMS SAM test failures affecting availabilities.
ECHO | During April Out of Hours cover for the Echo service started to be piloted. During May the GridFTP / XRootD plugins on the Echo gateways were successfully updated - changing the way checksums are stored. During May CMS successfully tested AAA access to ECHO over xrootd. By the end of May atlas were storing 2Petabytes of data in Echo. Following this Atlas carried out a successful deletion test - as regular deletions (as well as creations) are needed for normal operations. During June an internal (transparent) change was successfully made to the Echo CMS pool to increase the number of placement groups. This improves the distribution of data and was being done ahead of adding more hardware capacity. |  | Echo has seen a number of issues arise as usage ramped up - and these have been successfully tackled: During May problems were seen on the Echo xroot gateways. A xrootd proxy cache was then installed on these gateways and this resolved the issue. In June Echo saw an internal problem where the "Level DB"s on some OSDs (disk managers) had grown very large causing latency problems. The cause was understood and worked around by the introduction of the XRoot proxies. It was then possible to reduce the sizes of these databases. Also during June there were problems with the Echo gateways that coincided with a large increase in requests. In response the xrootd gateway was stopped for a few days and a concurrent connection limit applied to the GridFTP gateways. High memory usage was also observed and steps taken to reduce that.
Grid Deployment | During May batch access was enabled for LIGO and the MICE pilot role. Also during May the Edinburgh Dirac site started transferring data in production - initiall around 2 to 4TB per day. Then during June data startedshipping from the Leicester Dirac site.
Core Services | During May load balancers were set-up in front of the Argus service and the CEs configured to use these. This eliminated a single-point of a failure for the batch system.
Production Team
Network | In April The IPv6 addressing scheme was agreed and put in place. This was an enabler for IPv6 services. Also during Aril the Perfsonar nodes were set-up to work over IPv6 on the production Tier1 network. Towards the end of June: - The paired network link between R89 and R26 was switched from 2*10Gb/s to 2*40Gb/s. - The OPN link to CERN was increased from 2*10Gb/s to 3*10Gb/s. |  | In May a problem with the site firewall was revealed. Initially being looked at owing to videoconferencing problems it became clear this has a significant effect on some of our data flows. Although much of our data flow bypasses the firewall this is a significant problem (e.g. for data flows to/from worker nodes) and is caused by a weakness in the current firewall. (The problem has not been resolved).
Machine Room Operations | The two chillers replaced in the last quarter are working OK. They look like they will give will give a return on investment (in electricity costs) in around 5 years. |  | At the end of April there was a failure of the UPS in building R89 when internal capacitors overheated. Following this there was no UPS (or diesel) backup to the machine room in R89. A replacement UPS was installed and commissioned during May.
Database team
APEL | No major problems encountered. Service ran smoothly during this period. Response time for GGUS tickets well within OLA. |  | New hardware did arrive at last, but due to problems with sys admin availability, only now starting to work up a detailed schedule and plan for migration.
GOCDB | Handover from DM to GR completed. Work on extending write API continuing |  | No Major Issues. DM to move to other projects.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
Changes to purchasing plan may add delays and lead to purchasing items earlier at less favourable prices/performance. |  | Purchasing against the revised plan will be prioritsied to expedite the processing and examined thoroughly.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
CERN will stop support for Castor. |  | CERN have announces a replacement for Castor (for tape). An evaluation of the best way forward for future tape storage is being made.
CEPH ECHO will not deliver storage reliably or be able to deliver the necessary access bandwidth. |  | Tight management of the ECHO project is carefuly monitoring progress. A detailed risk register for ECHO has been produced. Staff are gaining operational experience with Echo now storing Atlas data.
Oracle withdraw support for existing Tape infrastucture. |  | Oracle have indicated that the next generation of tape drives/mdeia will not be produced. Track Oracle timeline for tape/media/librray support and be aware of the directions being taken by other sites.
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
1.4.3 FY16 Purchase in production |  | Apr '17 |  | Equipment delivered but further time needed for testing before going into production.
1.4.4 Tier-1 WLCG MoU commitments met |  | May '17 |  | New equipment not in use. However, CPU commitment met and Echo storage coming onstream. Note that this report missing key metrics here.
1.4.5. Produce the purchasing plan |  | June '17 |  | Planning underway. However, plean will not be finalised until much later than this.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
No milestones in next quarter.
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
1.4.5. Produce the purchasing plan |  | June '17 |  | Oct '17 | Finalising the purchasing requires many discussions and usually cannot (or does not) start earlier.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q317
GridPP Quarterly Report
Area | Tier-1
Quarter | Q317
Reported by | Gareth Smith
Progress over last Quarter
Work area | Successes |  | Problems/Issues
General | In mid-July data started to be received from the Dirac Leicester site. By the end of this quarter we had a total of about 2PBytes of data from a total of 4 of the Dirac sites.
Management | The Tier1 manager role continues to be covered by 20% of Andrew. |  | Production team running well below staff complement.
CPU
Disk | The RAID card firmware was updated on one batch of disk servers (OCF '14) in July. Also during July the wide area network tuning parameters were updated on Castor disk servers. (This had previously been applied to some of the servers - this completed the roll-out.) During this quarter 6 additional disk servers have been deployed into each of AtlasTape, CMSTape and lhcbRawRdst (All D0T1 areas) in Castor. |  | The (2015) disk servers added into Echo gave problems owing to a higher-than-expected rate of disk errors. The servers had been put into a Ceph test area and exercised. However, this was clearly insufficient to shake out enough of the disk problems and the process will be re-visited. The error rates seen on the disks drives used in Echo are requiring careful management which is taking more effort than anticipated.
CASTOR | In July and August there were some problems with Atlas Castor. One was specifically accessing the Atlas Scratch Disk, another affected the SRMs. During August small AtlasScratchDisk was merged into the larger AtlasDataDisk pool in Castor. This had the effect of removing the bottleneck caused by the small AtlasScratchDisk pool which affected the rate at which files could be transferred in/out. Enabled access to Castor for the SOLID experiment. |  | A couple of instances during the quarter where CMSDisk became full. This affected the SAM SRM tests and hence CMS availability. At the start of the quarter we were still seeing a high rate of failures of the CMS SAM tests against the SRM which affected the (CMS) availabilities. However, around the middle of the quarter the test success rate improved markedly although we do not understand why. In August four files were reported lost to CMS from a tape. During a CMS mass recall the monitoring noted that one tape was generating errors and causing tape drives to go down. The tape was put into repack. After various attempts at repacking and reading files direct from tape, four files were left unreadable. In September six disk servers from 2012 batches were deployed into the LHCb tape buffer. Some problems were encountered with SAM tests failing - ultimately traced to configuration problems on a couple of these additional disk servers. LHCb did not report operational problems resulting from this.
ECHO | In July a test gateway to Echo was made dual stack and test transfers have been shown to work over IPv6 to/from CERN. At the start of the quarter the number of placement groups in the Echo CEPH Atlas pool was steadily increased in preparation for the increase in storage capacity when new hardware was added. This was completed early August, and then by mid-August all the 2015 capacity storage had been put into Echo giving around 13.4Petabytes of space raw or approximately 10PBytes of usable space. Work then started to re-balance the existing data across all the storage. In early September there was a successful test transfer of CMS data into Echo using PhEDEx. |  | Media errors that were flushed out as Atlas data was moved (rebalanced) onto the newly-added hardware (the rest of the 2015 batch) led to problems within CEPH. At the end of August there was a loss of around 22,000 Atlas files (of which 3285 files were unique). One CEPH "placement group" was lost. This problem was understood - and a bug in CEPH identified. Media errors in the hardware that has been added into Echo exposed a bug in the CEPH Erasure Coding when back-filling. Careful management of disk errors as the data was moved onto new servers was necessary. The rebalancing proceeded much more slowly than anticipated and was still ongoing at the end of the quarter. The above problem aslo uncovered a separate problem (subsequently solved) with the Echo gateways (including those on the worker nodes) which created many threads - blocking activity. Post mortem for data loss at: https://www.gridpp.ac.uk/wiki/RAL_Tier1_Incident_20170818_first_Echo_data_loss
Grid Deployment
Core Services | In July access to FTS via the SOAP interface was stopped. This enabled the FTS service to be subsequently upgraded to a newer version. By early August all squid nodes have been enabled with IPv4/IPv6 dual stack and in mid-August the CVMFS Stratum-1 service also had IPv4/6 dual stack enabled. The moving of VMs off our old Windows HyperV2008 infrastructure to hypervisors running HyperV2012 was largely complete at the end of the quarter. |  | There was a problem with the test FTS3 service (used by Atlas) at the end of July. The system hit a limit of having done 2 billion file transfers. An emergency update was applied.
Production Team
Network | During August one of the three links that make up the OPN connection was moved to a new circuit that uses a different route - improving resilience of the overall OPN link. |  | There is an ongoing problem on the site firewall which is causing problems for some specific data flows that pass through the firewall. There was a site networking problem overnight at the end of July. One of the RAL core network stacks stopped working correctly in the early hours one morning. The Tier1 router pair flipped between the connections to the core networkj stacks several times. However, the one failing stack was in a bad shape and even when nominally up was not working correctly leading to the flipping. The faulty stack was stopped in the morning restoring network connectivity. Following the above there was a further problem on the 2nd August. After the previous problem we had set our router pair (the Extreme X670s) to not flip back to use the link to the (then) failing stack. However, during work to resolve the problem on the failed core stack our second link to another core stack went down - it appears our routers thought there was a network loop. This caused the Extreme x670 router pair to try switching back to the other connection. The upshot was a complete break in Tier1 connectivity to the core for around an hour. There was some delay in re-establishing IPv6 connectivity after this event.
Machine Room Operations | Power work was carried out in building R26 (the Atlas building) over the weekend of 29/30 July. This had no impact on our operational services. There was a successful UPS/Generator load test on 9th August. These are done quarterly and this was the first regular test since the building UPS was replaced. (It had been tested shortly after installation).
Database team
APEL | New hardware finally up and running. Summary processing rate much increased by this change. No major problems encountered. Service ran smoothly during this period. Response time for GGUS tickets well within OLA. |  | A couple of days had no cover by core APEL staff due to coincident leave.
GOCDB | Others starting to gain knowledge to gain resiliency of service. |  | Availability of effort.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The GridPP5 proposal requires the Tier1 to transition to supplying a more diverse community and that economies (in this context as seen by GridPP) can be found by providing a shared resource. |  | Ongoing discussions with other communities. Some initial success with DiRAC.
Insitute or area specific risks
Risk |  | Mitigating Action
Changes to purchasing plan may add delays and lead to purchasing items earlier at less favourable prices/performance. |  | Purchasing against the revised plan will be prioritsied to expedite the processing and examined thoroughly.
Experiment data access models are evolving. CASTOR is looking increasingly limited by transaction rate - particularly during hardware draining and meta-data operations such as ATLAS renaming. It is increasingly clear that CASTOR will not provide all required functionality to meet future experiment requirements. However recent discussion at PMB F2F concluded that no indication yet that CASTOR would prove inadaquate. |  | Continue work on the CEPH disk storage project (ECHO)
CERN will stop support for Castor. |  | CERN have announces a replacement for Castor (for tape). An evaluation of the best way forward for future tape storage is being made.
CEPH ECHO will not deliver storage reliably or be able to deliver the necessary access bandwidth. |  | Tight management of the ECHO project is carefuly monitoring progress. There has been one notable data loss incident. However, experience so far corroborates that expected from the risk register. As experience is being gained this risk is diminishing.
Oracle withdraw support for existing Tape infrastucture. |  | Oracle have indicated that the next generation of tape drives/mdeia will not be produced. Track Oracle timeline for tape/media/librray support and be aware of the directions being taken by other sites.
Staffing recruitment and retention remains problematic. |  | Recruitment and retention is considered a significant risk to STFC. A number of initiatives are underway in order to mitigate this. It would be possible to further mitigate against this risk if the Tier1 were able to recruit staff above agreed average staffing level.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
1.4.3 FY16 Purchase in production |  | Apr '17 |  | CPU in use. Storage awaiting further work in Echo.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Summary of Comments
1.4.6 FY17 Capacity order placed |  | Nov '17 |  | Tenders issued at end of November.
Objectives and Deliverables needing Rescheduling
Objective/Deliverable |  | Old Due Date |  | New Due Date | Reason
1.4.5. Produce the purchasing plan |  | June '17 |  | Oct '17 | Finalising the purchasing requires many discussions and usually cannot (or does not) start earlier.
New Objectives and Deliverables
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes