## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | CMS |  |  | Close to target
Year | 2018 |  |  | Not OK
Reported by | Dave Colling |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q117 | Q217 | Q317 | Q417 | Q118 | Q218 | Q318 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417 | Comment Q118 | Comment Q218 | Comments Q318
1.6.1 | Data Transfer quality | PhEDEx | Dave Colling | As needed by CMS | OK | OK | OK | OK | OK | OK | OK
1.6.2 | Timely and efficient availability and use of resources at RAL T1 |  | Dave Colling |  | Not ideal – worst cpu effeciency of any T1 in CMS. Best is ~90% whereas RAL is below 70%. Work in progress | Not ideal, worst CPU efficiency (~65%) of any CMS T1 (other than T1-RU-JINR and we don’t in their league) | Not ideal, CPU efficiency ~65%, however two other T1s were in the same region this quarter. | Third worst T1 efficiency from CMS. RAL was 69% cv 92% CNAF and 79% for FNAL (only KIT, which has had problems, and JINR are worse) | Worse CPU efficiency for any other T1 except CNAF which is recovering from a flood. | 3rd est CPU eficiencyn T1s although still low | Most efficient T1 in CMS this quarter (74%) | There are investigations in place as to why the CMS use of the T1 has not been as efficient as at other T1 centres. Previously this was put down to multicore pilot jobs and one particular workflow. However further scratching has shown that these are only a small part of the effect and so searches are being carried out. | See comments in main report. | See comments earlier | No new comments
1.6.3 | Data Loss at Tier-1 |  | Dave Colling |  | OK | OK | OK | OK | oOK | OK
1.6.4 | Site availability at the Tier-1 | 90% | Dave Colling | 97% | 90% for April, which is below 97% target, but still OK. | Not ideal, worst reliability and availabilty of all CMS T1s (around 90% averaged over the quarter) | Not Iideal, around 93% for both availability and reliability for this quarter. Worst in CMS, only by a few percent but consistently every month. Target is 97% | Slight dip in October but otherwise OK | Good 99% or 100% each month | OK | ~90% |  | See comments in main report. | See comments earlier |  |  |  | Understood because of the week long Echo outage in August
1.6.5 | Data availability via AAA |  | Dave Colling |  | OK | OK | Being investigated. Big difference between resident locally and remotely | Being investigated. Big difference between resident locally and remotely | Being investigated. Big difference between resident locally and remotely | Still known probems | ~78% uptime |  |  | See comments earlier
1.6.6 | CMS Fraction of Tier-1 work carried out at RAL |  | Dave Colling | 8% | 7.9% | 8.2% | 9% | 6% | 6.9% | 6% | 9%
2.2.1 | Transfer rates to the UK Tier 2s |  | Dave Colling |  | OK | OK | OK | OK | OK | OK | OK
2.2.2 | Site availability at the Tier-2s |  | Dave Colling | 80% | Bristol 93%, RALPP78%, Brunel 98%, Imperial 100% | Bristol 96%, RALPP 87%, Brunel 99%, Imperial 100% | OK at over target for all sites (apart from slight dip in August just below for RALPP and Bristol). Typicall 100% or high 90%. | ALL OK (close to 100% throughout) | Bristol dipped to 67% in March from 92% in Feb. No other site below 97%for any month. | Generaly OK, slgh dipb Bistol in May to 74% | OK. Bristol had a couple of months (July and September) in the 80% range but still always above target. All other sites clearly OK. |  | These numbers are a by eye average over 3 monthly reports
2.2.3 | Site readiness at the Tier-2s |  | Dave Colling | 80% | Bristol 93%, RALPP78%, Brunel 98%, Imperial 100% | Bristol 96%, RALPP 87%, Brunel 99%, Imperial 100% | All over target | ALL OK (close to 100% throughout) | Exactly the same as availability – Bristol dipped to 67% in March from 92% in Feb. No other site below 97%for any month. | As with avalability | OK. Bristol had a couple of months (July and September) in the 80% range but still always above target. All other sites clearly OK. (Very similar to above). |  | These numbers are a by eye average over 3 monthly reports
2.2.4 | Unique data loss at Tier-2s |  | Dave Colling |  | OK | OK | OK | OK | OK |  | OK
2.2.5 | Failed analysis jobs |  | Dave Colling | <30% | 30% | 38% | 46% !!! Worse than the rest of CMS! I haven’t looked by site yet. | 32% Only just 30% target. | 38% so 8% outside of target% Bristol ~75% failed | 34% fail so 4% over target% | 36% (6% above target) |  |  | See comments earlier
2.2.6 | Failed production jobs |  | Dave Colling |  | 11% | 8% | 14%, slightly worse than CMS average of 12% (which is why this is orange as I have no specific targets set) | 31% (only China, Taiwan and India worse) | 34% failed (Bristol ~75% failed) | 12% failure (usng WC) but Bristol~40% | 15% |  |  | See comments earlier
2.2.7 | T2 sites provide an appropriate level of resource to CMS |  | Dave Colling |  |  | 4.5% | 3.6% Low | 4.8% | 3.9% a little low | 3.95% which a little low | 4.14% |  | Actually 4.5% | See comments earlier
2.2.8 | AAA data transfer performance |  | Dave Colling |  | OK | Good | Good… being investigated as part of CPU task force. | Good… being investigated as part of CPU task force. | OK | Good | OK |  | Have linked all UK data and installed UK re-director

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | CMS |  |  | Overdue
Year | 2018 |  |  | Not yet due
Reported by | Dave Colling |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
1.6.9 | Report to PMB on delivery during the year | Dave Colling | 2016-12-01 | 2016-12-01 | OC Docs | OC Docs plus experiment review SS
1.6.10 | Report to PMB on delivery during the year | Dave Colling | 2017-12-01 | 2018-02-01 | OC Docs | OC Docs plus experiment review SS
1.6.11 | Report to PMB on delivery during the year | Dave Colling | 2018-12-01 |  | OC Docs
1.6.12 | Report to PMB on delivery during the year | Dave Colling | 2019-12-01 |  | OC Docs

## Manpower Q3 2017
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Manpower Q4 2017
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Nobody
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Manpower Q1 2018
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Chris Brew | GridPP Funded Month 1: 0.3; GridPP Funded Month 2: 0.3; GridPP Funded Month 3: 0.3
Total |  |  | 0.3 | 0.3 | 0.3 | 0 | 0 | 0

## Manpower Q2 2018
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Chris Brew | GridPP Funded Month 1: 0.25; GridPP Funded Month 2: 0.25; GridPP Funded Month 3: 0.25
Total |  |  | 0.25 | 0.25 | 0.25 | 0 | 0 | 0

## Manpower Q3 2018
GridPP Quarterly Report
Area | CMS
Quarter | 2016
Reported by | Dave Colling
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | CMS | Chris Brew | GridPP Funded Month 1: 25%.; GridPP Funded Month 2: 0.25; GridPP Funded Month 3: 0.25
RAL | CMS | Katy Ellis | bar: GridPP Funded Month 3
Total |  |  | 0 | 0.25 | 1.25 | 0 | 0 | 0

## Narrative Q4 2016
GridPP Quarterly Report
Area | CMS
Year | 2016
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Andrew was very effective this quarter, especially interesting was his work running CMSjobs on different cloud infrastructures.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q1 2017
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | Andrew left CMS (although still contributes(. A replacement is being sought.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q2 2017
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q3 2017
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | We interviewed for Andrew’s replacement.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q4 2017
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Andrew Lahiff | People we interviewed for Andrew’s replacement turned us down.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: gronbech:Bullet point summary of this quarters work
Note on B11: gronbech:Bullet point highlights of this quarters work.

## Narrative Q1 2018
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
CMS Post | Chris Brew covering at 30%
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: Peter Gronbech: Bullet point list of work done during the quarter

## Narrative Q2 2018
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
CMS Post
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: Peter Gronbech: Bullet point list of work done during the quarter

## Narrative Q3 2018
GridPP Quarterly Report
Area | CMS
Year | 2017
Reported by | Dave Colling
Progress over last Quarter
Work area | Successes |  | Problems/Issues
CMS Post
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Note on B10: Peter Gronbech: Bullet point list of work done during the quarter