## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Data Group |  |  | Close to target
Year | 2018 |  |  | Not OK
Reported by | Jens Jensen |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q117 | Q217 | Q317 | Q417 | Q118 | Q218 | Q318 | Q418 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417 | Comment Q118 | Comment Q218 | Comment Q318 | Comment Q418
3.2.1 | Number of VO requested changes not implemented in a timely fashion across whole infrastructure (1wk for small changes, 3wks for medium size, 6wks for large.) - any GridPP VO |  | Jens Jensen | 0 | [8 empty] | No changes | No major changes requested. |  | Incidents under our control resolved quickly - within 1wk (space report at Shef., CA signature change, default perms in DPM) | No major changes requested | OK: No changes seem to have been requested. | No major changes requested; no new VOs onboarded this quarter. | No requested changes if we don't count the Birmingham EOS-only SE
3.2.2 | Number of experiments whose data transfer rates from/to RAL to/from T2s do not meet their (realistic) requirements |  | Jens Jensen | 0 |  |  |  | ?? | ?? |  |  |  | Seems OK; see plot. (However some of the low rates are due to low activity, maybe APEL has better data?) | See plot on RHS. (A bit lo res because it needs to fit on the monitor when I screeshot it. The "J" character is a 3…) | Plot: Oxford and QMUL look a bit dodgy as destinations but fine as source; Sheffield looks a bit low both ways. However, these | It is much harder to get the data now that CERN only offers the grafana interface - it is very pretty but harder to find the infromation Over the quarter, RAL transferred 608.9 TB to the T2s for the three WLCG expts., which is an avg of 76.6 MB/s. (compare with 1.65 PB RAL-RAL over FTS) From T2s to RAL we get about 470TB.which averages 59 MB/s | Same as last quarter. I have been in touch with CERN about the lack of accounting data. |  | NO DATA | NO DATA
3.2.3 | FTS data transfer success rate |  | Jens Jensen | 85% |  |  |  | ?? | ?? |  |  |  | See plot. Again these are only avg rates. | See plot: total is 82% (but including test transfers: we have no reliable way of filtering them out.) | Probably OK in practice, as the 77% include test transfers. Nevertheless, without a way to separate the relevant FTSes? |  |  |  | NO DATA | NO DATA and it;'s getting worse; ATLAS are replacing their good moniroting with prettier but useless monitoring
3.2.4 | Conference paper (CHEP, AHM, or similar (or better)) produced each year describing GridPP developments and innovations in data management and storage area |  | Jens Jensen | 4/Y | [8 empty] | Appleyard, Jensen, Gordon: CASTOR acct. (ISGC 2017). Proposed submissions to WLCG in Manchester. We don't seem to have submitted to HEPiX, though, nor to Networkshop | None this quarter; as we focused on the WLCG workshop | None this Q | We should have some submissions to CHEP but the submission deadline was extended into Jan. | GridPP presented at the WLCG workshop but we don't seem to have any submissions from storage and data management |  | CHEP submission (Sam, with input from Everyone™) | 0
3.2.5 | Engage with storage and data management experts within WLCG/EGI/EMI/NGS or similar, or industry, to reinforce GridPP's recognised competence in this area (talks given, meetings, virtual meetings) |  | Jens Jensen | 4/Q | [8 empty] | Doesn't seem to have been any relevant meetings this quarter? | Excellent representation at WLCG workshop in Manchester. However, we had nothing at HEPiX. | Engagement with WLCG's storage and reporting task forces, and DPM developers re UK hosting workshop | Representation at the december pre-gdb (on authorisation - David Crooks). Liasiing with DPM team on workshop organisation (now postponed to May 18) | Attendance at WLCG workshop (Brian Davies, David Crooks) https://indico.cern.ch/event/658060/ see http://storage.esc.rl.ac.uk/weekly/20180404.txt LHCOPN (Duncan, Brian); see http://storage.esc.rl.ac.uk/weekly/20180314.txt | Main event was DPM workshop (see narrative) 0 for HEPiX, apparently. Hepsysman had good input from GridPP but less storage related stuff | DOMA WG has resurrected itself and we are contributing to it. Also obviously GridPP41 and the associated hackday. Contributions to DPM "community" | Good interactions with DOMA WGs Also IRIS counts, trial of new VOs using GridPP
3.2.6 | Number of incidents not resolved within 1wk after being reported on list |  | Jens Jensen | 0 | [8 empty] | sno+ "incindent" seems to be controlled - ie due to growth they need to be persuaded to use space tokens | Only a few incidents but they seem to have resolved fairly quickly . I have less data about RALPP's "interesting" database upgrade for dCache, though, as it was reported only indirectly. | OK |  |  | OK | Incidents were ATLAS data cleanup requiring manual intervention; corrupted files reported at Bristol; minor issue at Manchester; insufficiently tested DPM (devops issue).All resolved on satisfactory timescale | 0
3.2.7 | Number of blog posts |  | Jens Jensen | 5 | 8 | 8 | 2 | 2 | 6 | 5 | 4 | 0 | Marcus 3 JohnB 1 Brian 4 | Brian 7 (despite STFC purdah most of the quarter) and, RobC 1 (but a long one…) | Jens 1, Brian 1 | As previous quarter: Jens 1, Brian 1 | Brian 4, Matt 1, Rob 1 | Brian 3, Dan 1, Sam 1 | 4 (Brian 3, Rob 1) | 0

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Data Group |  |  | Overdue
Year | 2018 |  |  | Not yet due
Reported by | Jens Jensen |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
3.2.8 | Deploy and test "solution" for T2C storage (e.g. cache+local storage) | Sam Skipsey | 2017-01-31 | 2017-08-31 | Feedback to GDB | Completed
3.2.9 | Present GridPP work at data workshop at CERN | Brian Davies | 2016-09-30 | 2017-08-31 | Presentation | Done.
3.2.10 | Develop GridPP as a "data einfrastructure" in the context of UKT0 | Jens Jensen | 2016-12-31 | 2017-08-31 | Report? | Presented at UKT0 meeting at Milton Park
3.2.11 | Data transfer/management comparison with climate | Jens Jensen | 2016-11-30 | 2017-08-31 | Report, workshop, or publication | Work presented at Cloud workshop hosted by Crick end of Nov. 2016 (on connecting GridPP with cloud and other e-infrastructures)
3.2.12 | All major T2s dual stacked | Jens Jensen | 2018-04-30 |  | Test with IPv6 FTS

## Manpower Q212 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q312 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q412 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q113 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q213 (hidden)
GridPP Quarterly Report
Area | Data Group
Year | 2013
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Wahid Bhimji | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q117
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Marcus Ebert | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q217
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 1 | 1 | 1
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
Total |  |  | 3 | 3 | 3 | 0 | 0 | 0

## Manpower Q317
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 0.5 | 0.5 | 0.5
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
|  | Teng Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
Total |  |  | 3 | 3 | 3 | 0.5 | 0.5 | 0.5

## Manpower Q417
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 0.5 | 0.5 | 0.5
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
|  | Teng Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
Total |  |  | 3 | 3 | 3 | 0.5 | 0.5 | 0.5

## Manpower Q118
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 0.5 | 0.5 | 0.5
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
|  | Teng Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
Total |  |  | 3 | 3 | 3 | 0.5 | 0.5 | 0.5

## Manpower Q218
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 0.5 | 0.5 | 0.5
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
|  | Teng Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
Total |  |  | 3 | 3 | 3 | 0.5 | 0.5 | 0.5

## Manpower Q318
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
|  | Teng Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
Total |  |  | 3 | 3 | 3 | 1 | 1 | 1

## Manpower Q418
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  | Jens Jensen | 0.2 | 0.2 | 0.2
|  | Rob Currie | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
|  | Brian Davies | 0.8 | 0.8 | 0.8
|  | Sam Skipsey | 1 | 1 | 1
|  | Teng Li | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | (LSST)
Total |  |  | 3 | 3 | 3 | 1 | 1 | 1

## Narrative Q117
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Good experiences with ZFS, as can also be seen from the blog, and from the minutes and vidyo chat logs from the meetings |  | Losing most of our ZFS expertise thanks to Brexit (ie Marcus going to Canada) RAL's LHCb SRMs got re-certificated without alternative names, so failed for RAL's FTS (but not CERN's)
Data Management | ARC cache test results at Durham have gone well, would be useful to expand to other site. |  | Accounting is wrong - again. Each implementation - dCache, DPM, CASTOR - seems to have its own problem. Also problems with RUCIO creating empty directories (again) and deletions through WebDAV.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Loss of ZFS expertise leading to problems in the future |  | Other sites need to build expertise, or we need to not use ZFS
Information systems (still a risk) - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Still needs more effort -
Effort - note Brian's back to 80% having left the climate project, but we now lose Marcus |  | Recruitment at Edinburgh
Insitute or area specific risks
Risk |  | Mitigating Action
Storage nodes become unavailable due to their certificates being renewed inadvertently omitting subject altenrative names (happened for LHCb at RAL) (mostly a T1 issue at the moment but could currenlty also hit Imperial, RALPP, and a few other sites). |  | Suggest using hepsysman to review/discuss options
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
T2C testing: ATLAS hammercloud report |  | 2016-05-15 |  | Now finally resolved - tests were done with CMS instead; see http://storage.esc.rl.ac.uk/weekly/20170222-minutes.txt
Report on ZFS testing (following up from HEPiX): is ZFS a suitable alternative for a Tier 2. Should GridPP expand its expertise (ie not just Marcus) in ZFS? |  | 2017-02-28 |  | See extensive blog posts from Marcus (https://gridpp-storage.blogspot.co.uk/) and the minutes of almost every meeting in the quarter (http://storage.esc.rl.ac.uk/weekly/). Short answer is yes, if we can retain the expertise, and need to look out for performance issues.
Update on GLUE solving the acounting in JSON for ATLAS problem? (See http://storage.esc.rl.ac.uk/weekly/20161116-minutes.txt) |  | 2017-03-31 |  | Rob presented work at ISGC in March. However, the task has not progressed as much as we'd like, due to lack of effort - for example, solving CASTOR issues is a higher priority and meant we had less time to work on the accounting.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
We really need to get our wiki docs refreshed, particularly of course the keydocs - lots of storage related docs have been very, very, red for quite some time, despite lots of nagging. |  | 2017-05-31 |  | docs updated - internal review
Proposal for multi-SAN support |  | mid June |  | Discussion/proposal at hepsysman

## Narrative Q217
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Good GridPP (re)presentation at WLCG workshop. While the presentations in GridPP storage were dominated by RAL (and a few of the sought topics were specific to RAL (in GridPP), such as object stores and tape), we contributed to the data and accounting sessions |  | Storage accounting continues to drag behind but was at least revisited at the WLCG workshop. IPv6 is still problematic: even sites with dual stack do not necessarily get good performance, due to site network issues outside of the storage element
Data Management | CVMFS seems to be progressing well and is now proposed used also for experiments' data |  | FTS migration issue (SOAP to ReST). Also, FTS support for non-GridFTP protocols need more testing.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Loss of ZFS expertise leading to problems in the future |  | Other sites need to build expertise, or we need to not use ZFS Mitigation update: RobC seems to have got up to speed, cf his blog post. http://gridpp-storage.blogspot.co.uk/2017/06/hosting-large-web-forum-on-zfs-case.html
Information systems (still a risk) - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Still needs more effort -
Globus toolkit end of support was identified as a major risk during the quarter |  | Hopefully the proposed CERN/OSG support works out, or we will have to think carefully how to proceed with our existing storage systems
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | re-test with "volunteer" (Lancaster) to see if we get better results
Poorly supported non-SRM accounting leading to inaccurate accounting at (SRM-less) T2s |  | Need to test more recent versions of storage elements. (Bristol?)
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
We really need to get our wiki docs refreshed, particularly of course the keydocs - lots of storage related docs have been very, very, red for quite some time, despite lots of nagging. |  | 2017-05-31 |  | Some good progress, but despite fairly persistent nagging since January, not all storage keydocs have been updated. (Note that some just need reviewing, others need re-testing)
Proposal for multi-SAN support (in order to support multi-VO storage endpoints and/or resilient services) |  | mid June |  | Discussion/proposal at hepsysman. Presentation given and discussed. Early trials of system (mostly supporting T1 FTS and Echo) have been sufficintly promising to say it's an improvement.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Present GridPP work at September pre-GDB |  | 2017-09-12 |  | Presentations of work, attendance
Investigate SwordFish (SNIA storage management extension of DMTF's redfish which in turn updates IPMI) |  | 2017-09-12 |  | Presentations of work
If we update the dCache keydoc (testing by Brian) we should test the Google Macaroons as non-certificate access method and report |  | 2017-09-12 |  | Presentation of work

## Narrative Q317
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Storage keydocs are finally green(ish)! Only took over a year! Generally successful migrations from SL6 to CentOS7 and YAIM to Puppet |  | Switching to object stores could cause problems, depending on access patterns and interfaces used.
Data Management | We seem to have made modest progress on the T2 evolution with more clarity from the experiments and a plan for the next steps we can usefully do. |  | Loss of GridFTP (in the longer term) would be a problem unless we can find other ways to do 3rd party copying in parallel streams Request for managing lots (10^6) of small (kB) files for CERN@School. Very slow accounting in DPMs v1.8.X. Needs testing in 1.9 to see whether it improves (sites run it monthly despite being requested to run it daily)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Loss of ZFS expertise leading to problems in the future |  | Situation improving after the loss of Marcus. See talk at GridPP. Also, Teng (at Edinburgh) tasked with gaining expertise. Can probably drop this risk in 17Q4
Information systems - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Ongoing risk. However, following the summer's WLCG workshop, the October pre-GDB has added some clarity (and the December one should add some more…?!)
Globus toolkit end of support was identified as a major risk during the quarter |  | Short to medium term: accept the risk. Do we need to resurrect older ftp implementations? Can we support GridFTP ourselves? Would Globus Connect be sufficient?
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | re-test with "volunteer" (Lancaster) to see if we get better results
Poorly supported non-SRM accounting leading to inaccurate accounting at (SRM-less) T2s |  | Need to test more recent versions of storage elements. (Bristol?)
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
We really need to get our wiki docs refreshed, particularly of course the keydocs - lots of storage related docs have been very, very, red for quite some time, despite lots of nagging. |  | 2017-05-31 |  | Finally they are green… (all the red ones are non-storage ones)
Present GridPP work at September pre-GDB |  | 2017-09-12 |  | Topics in the end were a bit tier1y but GridPP was well represented: https://indico.cern.ch/event/578974/
Investigate SwordFish (SNIA storage management extension of DMTF's redfish which in turn updates IPMI) |  | 2017-09-12 |  | Done, will appear as a blog post in October (hopefully). The basic idea is SwordFish gives us a view of physical resources and their capacity but we still need additional metadata like paths and ownership.
If we update the dCache keydoc (testing by Brian) we should test the Google Macaroons as non-certificate access method and report |  | 2017-09-12 |  | Keydoc has been refreshed. Macaroon doesn't seem to be completed? Or at least it has not been written up.; but the situation has also changed with the SciTokens proposal from the US.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
"xcache" testing: RHUL "volunteered", to be aided by Power Rangers |  | 2017-12-31 |  | report
SciToken/Macaroon (etc) position statement |  | 2017-12-31 |  | feedback to WLCG US
Need a better way to get/filter FTS performance metric (filter out bogus/test data) |  | 2017-12-31 |  | Recipe or reporting tool

## Narrative Q417
GridPP Quarterly Report
Area | Data Group
Year | 2017
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Storage keydocs are now much greener! ZFS expertise (or lack of) no longer considered a risk (having imrpoved over the previous two quarters); there may still be things we can't solve but we have more expertise in-house now Also progress on IPv6 towards the end of the quarter, it seemed to have gained momentum
Data Management | Good progress with xroot proxy cache at RAL PP, and other sites exploring it. However, the results also show the limitations, as a full cache use can thrash the disks even for local jobs only. |  | Information systems clearer with the ATLAS JSON formatted version; need to check all implementations can generate it. Implement an automated checking tool?
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Upgrades from SL6 to XXX7 (SL7, CentOS7) causing problems for sites |  | Carefully "pilot" upgardes and share experiences between sites. Make use of the Power Rangers?
Information systems - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Ongoing risk. Some clarity; we should set a goal of harmonising our information across GridPP (see below)
Globus toolkit end of support was identified as a major risk during the quarter |  | Short to medium term: accept the risk. Do we need to resurrect older ftp implementations? Can we support GridFTP ourselves? Would Globus Connect be sufficient? (See also Scitoken discussion below)
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | Lancaster testing finally progressing; see hepsysmna 16 Jan. However, much more still needs to be done if we are to meet the deadline for 2x stacking larger T2s
Still lots of old DPMs out there; have got behind the baseline |  | Ticket sites to upgrade.
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
If we update the dCache keydoc (testing by Brian) we should test the Google Macaroons as non-certificate access method and report |  | 2017-09-12 |  | Summary of Macaroons discussion now sent to list (albeit somewhat late). See also item below. In contrast, the authorisation pre-gdb didn't cover this topic at a sufficiently detailed level; it was more high-level overview
"xcache" testing: RHUL "volunteered", to be aided by Power Rangers |  | 2017-12-31 |  | For the writeup of the test - now done by RALPP instead of RHUL; RHUL still ongoing - see http://storage.esc.rl.ac.uk/weekly/20171108-minutes.txt
SciToken/Macaroon (etc) position statement |  | 2017-12-31 |  | http://storage.esc.rl.ac.uk/weekly/20171018-minutes.txt See also mail to list (26 Jan). Not clear yet whether we should try to influence the direcitons of development; would depend on the uptake of SciTokens
Need a better way to get/filter FTS performance metric (filter out bogus/test data) |  | 2017-12-31 |  | Sadly, this task is now needs to be redone (or may be impossible!?) thanks to the new portal being deployed by CERN. It is much harder to distinguish the failures from the successful transfers as they are summarised independently of each other.
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Organise storage workshop (Glasgow) |  | 2018-01-31 |  | Writeup
IPv6 at larger T2s (dual-stacked) |  | 2018-03-31 |  | Works with IPv6-only FTS
For my £0.02, it is worth having a stab at harmonising storage accounting between T1 and T2s, although not strictly a T2-only task See https://twiki.cern.ch/twiki/bin/view/LCG/AccountingTaskForce |  | 2018-03-31 |  | Data available in harmonised format across of all of GridPP: DPM, dCache, StoRM, CASTOR

## Narrative Q118
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Glasgow hosted storage day in connection with hepsysman; see http://storage.esc.rl.ac.uk/weekly/20180124-minutes.txt for writeup and topics |  | Still niggling issues with CentOS7 upgrades and IPv6
Data Management | Update on adding RAL to LHCONE suggests easier T1-T1 transfers |  | Two sets of GFAL upgrade issues, one for non-LHC switching (or rather having to switch) from lcg-utils and the other a compatibility issue with FTS
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Upgrades from SL6 to XXX7 (SL7, CentOS7) causing problems for sites |  | Carefully "pilot" upgardes and share experiences between sites. Make use of the Power Rangers?
Information systems - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Ongoing risk. Some clarity; we should set a goal of harmonising our information across GridPP (see below)
Globus toolkit end of support was identified as a major risk during the quarter |  | Short to medium term: accept the risk. Do we need to resurrect older ftp implementations? Can we support GridFTP ourselves? Would Globus Connect be sufficient? (See also Scitoken discussed (briefly) at GridPP40)
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | Lancaster testing finally progressing; see hepsysmna 16 Jan. However, much more still needs to be done if we are to meet the deadline for 2x stacking larger T2s
Still lots of old DPMs out there; have got behind the baseline |  | Need to maintain https://www.gridpp.ac.uk/wiki/Storage_site_status
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Organise storage workshop (Glasgow) |  | 2018-01-31 |  | Writeup; see summary given at hepsysman https://indico.cern.ch/event/686369/ and/or http://storage.esc.rl.ac.uk/weekly/20180124-minutes.txt
IPv6 at larger T2s (dual-stacked) |  | 2018-03-31 |  | See Lancaster reports at GridPP40 https://indico.cern.ch/event/684659/contributions/2963507/ (as of this writing Matt needs to be reminded to upload his slides!) Finally, see Matt's blog post https://gridpp-storage.blogspot.co.uk/2018/01/dual-stacking-lancasters-sl6-dpm.html
For my £0.02, it is worth having a stab at harmonising storage accounting between T1 and T2s, although not strictly a T2-only task See https://twiki.cern.ch/twiki/bin/view/LCG/AccountingTaskForce |  | 2018-03-31 |  | Had discussions with CERN. Unfortunately, they resulted in work for us (= T1) to do to report consistently with other tape sites.
Need a better way to get/filter FTS performance metric - we used to get irrelevant data from test FTSes but after CERN's "upgrade" to Grafana we now get no useful data at all. But it _is_ very pretty! |  | 2017-12-31 |  | Issue has been raised with CERN
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
GridPP submission/input/presentation at DPM workshop https://indico.cern.ch/event/699602/ |  | End of May 2018 |  | Presentation, post-meeting report
Storage session at GridPP40: prepare agenda and talks |  | GridPP40 |  | Presentations given and uploaded
If we are to use GOCDB for information like Andrew McNab suggests, what do we need to change? How many formats are there? OGF GLUE2, WLCG accounting JSON, OSG, OGF StAR, etc. CERN's wlcg-tape-archive group and accounting group expecting different formats?! |  | 2018-06-01 |  | Action plan…!

## Narrative Q218
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Good representation at DPM workshop https://indico.cern.ch/event/699602/ |  | DPM sites will need to migrate to DOME. The planned hack day at GridPP41 may help.
Data Management | Lots of good work on [xroot] proxy caches, including submissions to CHEP (for Q3) |  | Still uncertainty about transfer protocols - for GridFTP, the future, for xroot the breadth of support and standardisation, for HTTP, the many options for token-based authorisation
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insufficient effort to make progress with many of the non-urgent technical issues |  | ??
Information systems - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Ongoing risk. Less clarity than before…
Globus toolkit end of support was identified as a major risk during the quarter |  | Short to medium term: accept the risk. Do we need to resurrect older ftp implementations? Can we support GridFTP ourselves? Would Globus Connect be sufficient? (See also Scitoken discussed (briefly) at GridPP40)
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | Lancaster testing finally progressing; see hepsysmna 16 Jan. However, much more still needs to be done if we are to meet the deadline for 2x stacking larger T2s
Token-based access creating problems for GridPP sites: there are at least four different technologies: scitokens, OAuth2 (RFC6749), JWT (RFC7519), and Macaroons [scitokens are derived from JWT] |  | ??
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
GridPP submission/input/presentation at DPM workshop |  | End of May 2018 |  | https://indico.cern.ch/event/699602/ See also Sam's report https://gridpp-storage.blogspot.com/2018/06/dpm-workshop-2018-report.html
Storage session at GridPP40: prepare agenda and talks |  | GridPP40 |  | https://indico.cern.ch/event/684659/timetable/
If we are to use GOCDB for information like Andrew McNab suggests, what do we need to change? How many formats are there? OGF GLUE2, WLCG accounting JSON, OSG, OGF StAR, etc. CERN's wlcg-tape-archive group and accounting group expecting different formats?! |  | 2018-06-01 |  | Incomplete: apart from meetings with the CERN-led accounting WG, we have not made enough progress on this. In fact the situation is even more muddled than at the start of the quarter, with less certainty about the future of infomration systems,so we should decide whether to wait for the dust to settle first or whether to try to influence the process
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
GridPP 6 forward look from storage and data management perspective |  | ?? |  | Document
CHEP submissions representing GridPP storage |  | CHEP deadline |  | Submissions from GridPP
Organise DOME hack day (for DPM admins) at GridPP41 |  | GridPP41 |  | report from attendees

## Narrative Q318
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | DOME tests and SL7 upgrade tests of DPM caught problems before wider rollout - which is precisely what they're meant to do. |  | Tests prove cache inefficient for some workflows - this would be a serious problem for eggs in the T2C basket
Data Management | Not perhaps a success (yet) but more an opportunity: Rucio is getting features to support metadata, and more experiments, new and old, express an interest in Rucio: CMS, SKA, DUNE, ICECUBE... |  | Still protocol issues: no single protocol satisifies all the requirements identified in forward look document (link below)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insufficient effort to make progress with many of the non-urgent technical issues |  | ??
Information systems - information not trusted, or doesn't match experiment requirements, or differs between experiments and/or implemementations |  | Ongoing risk. Less clarity than before…
Globus toolkit end of support was identified as a major risk during the quarter |  | Short to medium term: accept the risk. Do we need to resurrect older ftp implementations? Can we support GridFTP ourselves? Would Globus Connect be sufficient? (See also Scitoken discussed (briefly) at GridPP40)
Insitute or area specific risks
Risk |  | Mitigating Action
IPv6 still a risk, mainly due to need to work with site networking and tests at Glasgow have shown poor performance |  | Lancaster testing finally progressing; see hepsysmna 16 Jan. However, much more still needs to be done if we are to meet the deadline for 2x stacking larger T2s
Token-based access creating problems for GridPP sites: there are at least four different technologies: scitokens, OAuth2 (RFC6749), JWT (RFC7519), and Macaroons [scitokens are derived from JWT] |  | ??
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
GridPP 6 forward look from storage and data management perspective |  | ?? (finished 23 Oct.) |  | https://docs.google.com/document/d/1zH-R9si2JUhrjHqk7rWKqWSp_BVDV61ql1KvZUj1wbM/edit?usp=sharing
CHEP submissions representing GridPP storage |  | CHEP deadline |  | https://indico.cern.ch/event/587955/contributions/2936863/
Organise DOME hack day (for DPM admins) at GridPP41 |  | GridPP41 |  | http://storage.esc.rl.ac.uk/weekly/20180905-minutes.txt
If we are to use GOCDB for information like Andrew McNab suggests, what do we need to change? How many formats are there? OGF GLUE2, WLCG accounting JSON, OSG, OGF StAR, etc. CERN's wlcg-tape-archive group and accounting group expecting different formats?! |  | 2018-06-01 |  | Incomplete: apart from meetings with the CERN-led accounting WG, we have not made enough progress on this. In fact the situation is even more muddled than at the start of the quarter, with less certainty about the future of infomration systems,so we should decide whether to wait for the dust to settle first or whether to try to influence the process
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
GridPP DPM sites contributions to DPM community - DOME testing (see hackday above), e.g. 3rd party copying specifically needs to work |  | 2018-10-31 |  | Results of functional tests; report to DPM
EOS evaluation (Glasgow, Edinburgh) - is EOS an alternative SE and backend (as opposed to Birmingham which primarily serves ALICE which is different) |  | 2018-12-31 |  | Evaluation, report
Towards Rucio/cache integration - report from Teng on testing (at Durham?) - the idea is that by making Rucio cache-aware, better efficiency can be reached, instead of caching files that are accessed only once (as ATLAS do) |  | 2018-12-31 |  | feasibility - report

## Narrative Q418
GridPP Quarterly Report
Area | Data Group
Year | 2018
Reported by | Jens Jensen
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Storage | Finally successful DOME testing (Lancaster); we are now not recommending that sites not upgrade. More storage (pledge) on IPv6 than before; 100% of CMS's (for 2018) and 80% of ATLAS's. |  | DUNE unable to make use of storage allocation at RAL because their files are bigger (8GB) than S3 can handle, and the RAL storage only provides S3. Imperial and Lancaster offer xroot but only for a few TB storage. The shock-consternation-uproar associated with Bham becoming EOS-only
Data Management | GridPP forward look (finally) finished. |  | Remote access is crucial to the new "flavoured" T2 model - storage and cache; yet the EOS tests reveal problems with remote access (in this case BHAM->MAN)
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insufficient effort to make progress with many of the non-urgent technical issues |  | ??
Insufficnet support from site central IT to resolve IPv6 issues |  | Ensure that we can continue to work with IPv4 as a fallback plan
Insitute or area specific risks
Risk |  | Mitigating Action
Token-based access creating problems for GridPP sites: there are at least four different technologies: scitokens, OAuth2 (RFC6749), JWT (RFC7519), and Macaroons [scitokens are derived from JWT] |  | ??
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
GridPP DPM sites contributions to DPM community - DOME testing (see hackday above), e.g. 3rd party copying specifically needs to work |  | 2018-10-31 |  | Completed at Lancaster http://storage.esc.rl.ac.uk/weekly/20181121-minutes.txt
EOS evaluation (Glasgow, Edinburgh) - is EOS an alternative SE and backend (as opposed to Birmingham which primarily serves ALICE which is different) |  | 2018-12-31 |  | This does not seem to have completed in time; unlike the BHAM evaluation of EOS, Glasgow were aiming to run EOS on top of ZFS. Edinburgh, too, behind schedule due to the need to allocate new servers. Testing CERN's data lake stalled due to permissions problems (only Brian seems to be able to use it, as a member of ATLAS)
Towards Rucio/cache integration - report from Teng on testing (at Durham?) - the idea is that by making Rucio cache-aware, better efficiency can be reached, instead of caching files that are accessed only once (as ATLAS do) |  | 2018-12-31 |  | Some progress,.see http://storage.esc.rl.ac.uk/weekly/20181107.txt (item 4)
Objectives and Deliverables for Next Quarter
|  | Due Date |  | Metric/Output
Apart from finishing last quarter's tasks(!) it would make sense to have a Rucio related task Start a tutorial for data management with Rucio in GridPP/IRIS |  | 2019-03-31 |  | Updated Wiki

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
GridPP as a data infrastructure | 2016-03-31 | All areas of research need data storage and movement even if they don't compute like HEP. Opportunity with MSDC ("UKT0") collaboration.
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Wahid Bhimji went to NERSC | 2015-03-11
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes