## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Operations |  |  | Close to target
Year | 2018 |  |  | Not OK
Reported by | Jeremy Coles |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q117 | Q217 | Q317 | Q417 | Q118 | Q218 | Q318 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417 | Comment Q118 | Comment Q218 | Comment Q318
3.1.1 | Fraction of UK sites in Production | Manual - Information available from GOCDB | Jeremy Coles | Number of GridPP sites in certified status. Require 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3.1.2 | Number of supported VOs | Manual - Tier-2 quarterly reports and Tier-1 | Jeremy Coles | Sum of unique VOs supported across GridPP sites - target 4 LHC + 5 other | 48 | 49 | 49 | 49 | 49 | 49 | 49 |  | DUNE VO added at several sites. |  |  | No reported changes but probably we should start looking at only active Vos as this figure is not useful. |  | This metric is really obsolete.
3.1.3 | Fraction of HEPSPEC06 used | From APEL accounting | Jeremy Coles | HEPSPEC06 used/ HEPSPEC06 available - 80% | 71% | 73% | 75% | 76% | 70% | 74% | 76% | 80% for wall eff. | TBC |  |  | Using wall time is 80%
3.1.4 | GridPP HEPSPEC06 Available | Manual sum over entries in quarterly reports | Jeremy Coles | Total GridPP HEPSPEC06 nominally available at the end of the last quarter. Target WLCG pledge | 700150 | 786900 | 781000 |  | 743000 | 860900 | 839400
3.1.5 | GridPP disk storage available | Manual sum over entries in quarterly reports | Jeremy Coles | Total TB of disk storage nominally available from GridPP at the end of the last quarter. Target WLCG pledge | 46000 | 53300 | 54500 |  | 62900 | 64000 | 64900
3.1.6 | UK contribution to LHC experiments | Manual sum over data provided by accounting portal | Jeremy Coles | Percentage of jobs run by LHC V0s processed in UK in last quarter. Target is as pledged shares (11%?) | 13.5% | 12.1% | 10.18% | 9.5% | 8.82% | 8.36% | 10.8% | Figure TBC as accounting portal changed | Figure TBC as accounting portal changed | Difficult getting a consistent figure. APEL main portal was having problems with SQL connections so this quarter came via accounting-devel.egi.eu. Figures in that portal look low for earlier quarters too. |  | Figures taking from the development portal of APEL. Concern with falling share. http://accounting-devel.egi.eu/country.php?query=normcpu&startYear=2018&startMonth=1&endYear=2018&endMonth=3&yrange=COUNTRY&xrange=VO&groupVO=lhc&chart=GRBAR&scale=LIN&localJobs=onlygridjobs
3.1.7 | GridPP site response to tickets |  | Jeremy Coles | Number of flagged tickets <3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.8 | Scotgrid % of promised (by that time) disk available to GridPP |  | Jeremy Coles | 100% | 205% | 254% | 207% | 207% | 207% | 200% | 207% |  |  | Q-1 numbers inconsistent | Q-1 numbers inconsistent
3.1.9 | Scotgrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 501% | 655% | 256% | 256% | 256% | 256% | 256%
3.1.10 | Scotgrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 89% | 99% | 97% | 97% | 98% | 91% | 96% | Glasgow low availabilty due to power cut leading to issues with cooling and corrupt DPM database |  |  |  |  | Apparently not work payloads. Duham had a low availability due to packages not updated (misflagged by a test).
3.1.11 | Scotgrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 90% | 99% | 97% | 97% | 98% | 91% | 96%
3.1.12 | Scotgrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 83% | 78% | 92% | 77% | 77% | 84% | 91% | Overall increases in efficiency this quarter. | Report now claims Q-1 is 68%?
3.1.13 | Scotgrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 75% | 70% | 93% | 62% | 63% | 73% | 77% |  | Q-1 given as 59%?
3.1.14 | Southgrid % of promised (by that time) disk available to GridPP |  | Jeremy Coles | 100% | 184% | 146% | 146% | 146% | 146% | 169% | 169%
3.1.15 | Southgrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 331% | 300% | 302% | 304% | 314% | 241% | 241%
3.1.16 | Southgrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 95% | 83% | 94% | 95% | 95% | 96% | 96%
3.1.17 | Southgrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 95% | 84% | 95% | 96% | 96% | 97% | 97%
3.1.18 | Southgrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 75% | 74% | 73% | 75% | 67% | 58% | 67%
3.1.19 | Southgrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 58% | 54% | 54% | 55% | 53% | 52% | 51% | [6 empty] | Why did this decrease when walltime utilisation increased a lot?
3.1.20 | Londongrid % of promised (by that time) disk available |  | Jeremy Coles | 100% | 233% | 233% | 233% | 272% | 305% | 300% | 300%
3.1.21 | Londongrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 339% | 339% | 339% | 339% | 339% | 364% | 364%
3.1.22 | Londongrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 98% | 100% | 100% | 96% | 96% | 97% | 96% |  |  |  | QMUL down |  |  | QMUL low
3.1.23 | Londongrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 98% | 100% | 100% | 96% | 96% | 98% | 98% |  |  |  | QMUL down |  | QMUL & RHUL low | QMUL low
3.1.24 | Londongrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 72% | 71% | 84% | 85% | 109% | 77% | 88% | [6 empty] | High with RHUL
3.1.25 | Londongrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 61% | 62% | 75% | 72% | 69% | 68% | 58%
3.1.26 | Northgrid % of promised (by that time) disk available to GridPP |  | Jeremy Coles | 100% | 183% | 188% | 200% | 200% | 200% | 200% | 226%
3.1.27 | Northgrid % of promised (by that time) CPU available |  | Jeremy Coles | 100% | 347% | 346% | 206% | 204% | 200% | 200% | 234%
3.1.28 | Northgrid Average SAM (SLL page) availability |  | Jeremy Coles | 95% | 97% | 90% | 90% | 92% | 94% | 98% | 92%
3.1.29 | Northgrid Average SAM (SLL page) reliability |  | Jeremy Coles | 95% | 98% | 90% | 95% | 93% | 95% | 98% | 92%
3.1.30 | Northgrid CPU utilisation (wall clock time) |  | Jeremy Coles | 50% | 85% | 79% | 83% | 102% | 93% | 116% | 105%
3.1.31 | Northgrid CPU utilisation (CPU time) |  | Jeremy Coles | 50% | 75% | 70% | 73% | 91% | 82% | 98% | 89%

## Manpower Q117
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and Operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q217
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and Operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
| London | I still do not see any contribution from Ivan Reid.
Daniela and Simon largely on DIRAC
| NorthGrid | Alessandra increasingly on ATLAS activities.
|  |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| 0 | R. Long | 1 | 1 | 1
|  | M. Doidge | 1 | 1 | 1
|  | P. Love |  |  |  | 0.3 | 0.3 | 0.3
| 0 | S. Jones | 1 | 1 | 1
|  | R. Fay |  |  |  | 0.5 | 0.5 | 0.5
|  | J. Bland |  |  |  | 0.5 | 0.5 | 0.5
| 0 | A. Forti | 1 | 1 | 1
|  | R. Frank | 1 | 1 | 1
|  | A. McNab |  |  |  | 0.5 | 0.5 | 0.5
| 0 | E. Korolkova | 0.5 | 0.5 | 0.5
|  | M. Robinson |  |  |  | 0.1 | 0.1 | 0.1
| Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  |  | EGI Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| Manchester | A. McNab | 0.5 | 0.5 | 0.5
| Manchester | A. Forti |  |  |  | 1 | 1 | 1
|  |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| * https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx | Raul Lopes | 0.85 | 0.85 | 0.85 | 0.15 | 0.15 | 0.15
|  | Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
|  | P. Hobson |  |  |  | 0.1 | 0.1 | 0.1
|  | P. Kyberd |  |  |  | 0.05 | 0.05 | 0.05
| 0 | Simon Fayer | 1 | 1 | 1
|  | Daniela Bauer | 1 | 1 | 1
|  | Ray Beuselinck |  |  |  | 1 | 1 | 1
|  | Duncan Rand | 0.5 | 0.5 | 0.5
|  | David Colling |  |  |  | 0.1 | 0.1 | 0.1
| 0 | Terry Froy | 1 | 1 | 1
|  | Dan Traynor | 1 | 1 | 1
|  | local site assistance |  |  |  | 0.1 | 0.1 | 0.1
| 0 | Govind Songara | 1 | 1 | 1
|  | B.Green/Tom |  |  |  | 0.1 | 0.1 | 0.1
| 0 | Ben Waugh |  |  |  | 0.05 | 0.05 | 0.05
| Total |  | 6.9 | 6.9 | 6.9 | 1.85 | 1.85 | 1.85
|  |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| 0 | Mark Slater | 1 | 1 | 1
Matt Williams
| 0 | Winnie Lacesso |  |  |  | 0.2 | 0.2 | 0.2
Luke Kreczko
0
|  | John Hill |  |  |  | 0.5 | 0.5 | 0.5
0
|  | Vip Davda | 0.5 | 0.5 | 0.5
|  | Kashif Mohammad | 0.5 | 0.5 | 0.5
| 0 | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
|  | Chris Brew | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3
Sussex
|  | J Maris |  |  |  | 0.1 | 0.1 | 0.1
|  | Leo Rojas |  |  |  | 0.3 | 0.3 | 0.3
| Total |  | 2.6 | 2.6 | 2.6 | 1.8 | 1.8 | 1.8
EGI Funded Posts (FTE)
|  |  | EGI Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| Durham | Oliver Smith | 0 | 0 | 0 | 0 | 0 | 0
| Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
| Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
| Edinburgh | R. Currie | 0 | 0.5 | 0.5 | 0 | 0 | 0
| Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
| Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
| Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
| Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
| Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
| Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
| Total |  | 3 | 3.5 | 3.5 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  |  | EGI Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q317
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and Operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
| London | I still do not see any contribution from Ivan Reid.
As Q2: Daniela and Simon largely on DIRAC
| NorthGrid | No figures given in report.
| SouthGrid | Not seeing much of Mark S at ops meetings.
| ScotGrid | Oliver removed from Durham
| Q2 figures are… |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| 0 | R. Long | 1 | 1 | 1
|  | M. Doidge | 1 | 1 | 1
|  | P. Love |  |  |  | 0.3 | 0.3 | 0.3
| 0 | S. Jones | 1 | 1 | 1
|  | R. Fay |  |  |  | 0.5 | 0.5 | 0.5
|  | J. Bland |  |  |  | 0.5 | 0.5 | 0.5
| 0 | A. Forti | 1 | 1 | 1
|  | R. Frank | 1 | 1 | 1
|  | A. McNab |  |  |  | 0.5 | 0.5 | 0.5
| 0 | E. Korolkova | 0.5 | 0.5 | 0.5
|  | M. Robinson |  |  |  | 0.1 | 0.1 | 0.1
| Total |  | 5.5 | 5.5 | 5.5 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  |  | EGI Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| Manchester | A. McNab | 0.5 | 0.5 | 0.5
| Manchester | A. Forti |  |  |  | 1 | 1 | 1
|  |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| * https://archive.gridpp.ac.uk/deployment/status/reports/GridPP4+-Tier-2%20Pledge%20levels-Aug2015.xlsx | Raul Lopes | 0.85 | 0.85 | 0.85 | 0.15 | 0.15 | 0.15
|  | Ivan Reid | 0.55 | 0.55 | 0.55 | 0.2 | 0.2 | 0.2
|  | P. Hobson |  |  |  | 0.1 | 0.1 | 0.1
|  | P. Kyberd |  |  |  | 0.05 | 0.05 | 0.05
| 0 | Simon Fayer | 1 | 1 | 1
|  | Daniela Bauer | 1 | 1 | 1
|  | Ray Beuselinck |  |  |  | 1 | 1 | 1
|  | Duncan Rand | 0.5 | 0.5 | 0.5
|  | David Colling |  |  |  | 0.1 | 0.1 | 0.1
| 0 | Terry Froy | 1 | 1 | 1
|  | Dan Traynor | 1 | 1 | 1
|  | local site assistance |  |  |  | 0.1 | 0.1 | 0.1
| 0 | Govind Songara | 1 | 1 | 1
|  | B.Green/Tom |  |  |  | 0.1 | 0.1 | 0.1
| 0 | Ben Waugh |  |  |  | 0.05 | 0.05 | 0.05
| Total |  | 6.9 | 6.9 | 6.9 | 1.85 | 1.85 | 1.85
|  |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| 0 | Mark Slater | 0.5 | 0.5 | 0.5
Matt Williams
| 0 | Winnie Lacesso |  |  |  | 0.2 | 0.2 | 0.2
Luke Kreczko
0
|  | John Hill |  |  |  | 0.5 | 0.5 | 0.5
0
|  | Vip Davda | 0.5 | 0.5 | 0.5
|  | Kashif Mohammad | 0.5 | 0.5 | 0.5
| 0 | Ian Loader | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
|  | Chris Brew | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3
Sussex
|  | J Maris |  |  |  | 0.1 | 0.1 | 0.1
|  | Leo Rojas |  |  |  | 0.4 | 0.4 | 0.4
| Total |  | 2.1 | 2.1 | 2.1 | 1.9 | 1.9 | 1.9
EGI Funded Posts (FTE)
|  |  | EGI Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
|  |  | GridPP Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
| Durham | Adam Boutcher | 0 | 0 | 0 | 0 | 0 | 0
| Edinburgh | A Washbrook | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3
| Edinburgh | R. Currie | 0 | 0.5 | 0.5 | 0 | 0 | 0
| Edinburgh | ECDF Systems Team | 0 | 0 | 0 | 0.2 | 0.2 | 0.2
| Glasgow | D Crooks | 1 | 1 | 1 | 0 | 0 | 0
| Glasgow | S Skipsey | 0 | 0 | 0 | 0 | 0 | 0
| Glasgow | G Roy | 1 | 1 | 1 | 0 | 0 | 0
| Glasgow | G. Stewart | 0.2 | 0.2 | 0.2 | 0 | 0 | 0
| Glasgow/NA62 | D. Protopopescu | 0.3 | 0.3 | 0.3 | 0 | 0 | 0
| Total |  | 3 | 3.5 | 3.5 | 0.5 | 0.5 | 0.5
EGI Funded Posts (FTE)
|  |  | EGI Funded |  |  | Unfunded
| Site | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q417
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and Operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q118
GridPP Quarterly Report
Area | Operations
Year | 2018
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and Operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q218
GridPP Quarterly Report
Area | Operations
Year | 2018
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and Operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Manpower Q318
GridPP Quarterly Report
Area | Operations
Year | 2018
Reported by | Jeremy Coles
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Cambridge | Deployment and operations | Jeremy Coles | 0.5 | 0.5 | 0.5
Oxford | Deployment and Operations | Pete Gronbech | 0.5 | 0.5 | 0.5
Total |  |  | 1 | 1 | 1 | 0 | 0 | 0
Comments on Tier-2 manpower (in Tier-2 reports)
Comment
| SouthGrid | Mark Slater | Less visible in recent months but funded at 0.5.
| LondonGrid | Antonio Perez Fernandez | New contributor at RHUL. Not ops visible.
Note on D8: rMBP: Is this supposed to record the actual effort given or as the column title suggests what is "funded"? If funded then 1.0 should appear here.

## Narrative Q117
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * Good overal availability this quarter. No issues raised by EGI (targets met). WLCG performance similar to normal.
Vos | [5 empty] | * During quarter some sites affected by ATLAS jobs filling cream sandbox with large log files.
Middleware/services | * Universal DIRAC VMs deployed to production for GridPP and LHCb in July. |  |  |  |  | * Issues with LFC at RAL Tier-1 in September due to database corruption.
Site infrastructure | * Steady progress with IPv6 deployment |  |  |  |  | * Despite progress on IPv6 some sites report central IT lack of priority.
Other | [5 empty] | * Some VidyoConnect teething issues in August.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise. Q416: SL5 no longer an issue. Testing on CentOS7 coming along well.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
Hardware reaching end-of-life without spares available - leading to reductions in capacity |  |  |  |  | Ensure H/W grants appropriately distributed and timely to allow replacements. (Note many sites are well over capacity so the risk is about maintaining resource levels not yet meeting pledges).
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams. Q414 - Durham continues with issues but has progressed testing
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Still no glexec tarball - situation continues beyond WLCG MB deadline for glexec enablement. Likely need to move to a workaround approach (i.e. give instructions on how to configure rather than provide an easy to install tarball). Q216 - Approach will be to provide insturctions for working around issue with tarball rather than providing a fully working install. |  |  |  |  | Keep WLCG MB/GDB aware of concerns and if possible work with WN developers to port a tarball version.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* VO NAGIOS is not supported beyond SL5 and ARGO development of similar functionality for regional use is not planned. Q416 - this will soon be an issue. There is no regional option being made available. |  |  |  |  | * Escalate concerns to EGI. * Perhaps trial on SL6!
* Lancaster NAT may not cope with federated access demands * Lancaster headnode out of warranty and may fail |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.
Glasgow: Air Condition/power issues leading to damaged equipment |  |  |  |  | Site admins working with estates to supply new data facility, now scheduled for Aug 2017
* A clear need for test resources or a multi-site testbed has been recognised but there are resource concerns. |  |  |  |  | State GridPP policy on accounting adjustments where production resources are used for testing and encourage reuse of old hardware (especially Tier-1 hardware).
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
Continue testing of SL7/CentOS7 - install nodes (Liverpool/ECDF/Brunel) |  |  |  |  | 2016-12-31 |  | Reports produced for WLCG MWR group and one service node installed.Adoption documentation being prepared by Liverpool.
Review IPv6 status and ensure clear documentation is in place. |  |  |  |  | 2016-06-30 |  | Experience gained from sites already transitioned to IPv6 to be written up. Include in programme for sprint 2017 HEPSYSMAN.
Continue WLCG SOC work |  |  |  |  | 2016-12-31 |  | Prepare contribution to be presented at WLCG workshop - October 2016
See Tier-2 reports for site specific objectives (e.g.Lancaster setting up CentOS7 mini-cluster and Bro SOC instance, further use of multi-core VAC (liverpool); ECDF openstack migration |  |  |  |  | 2017-03-31 |  | See reports
Proceed with required hardware purchases / Commission newly procured hardware (various sites) |  |  |  |  | 2017-03-31 |  | Hardware configured and online.
Continued adoption of IPv6 |  |  |  |  | 2017-03-31 |  | IPv6 status understood for all sites.
Additional site with legacy batch system begins migration to newer batch system (e.g. ARC-CE/HTCondor) |  |  |  |  | 2017-03-31 |  | At least one additional test cluster installed.
Progress to phasing out YAIM |  |  |  |  | 2017-03-31 |  | Clarity on plans to remove YAIM.
Investigate use of pakiti for UK NGI security team |  |  |  |  | 2017-03-31 |  | Test report
Integration of DPM within puppet (move away from YAIM) |  |  |  |  | 2016-12-31 |  | Puppet install modules for DPM available.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
UK pakiti instance available for initial tests |  |  |  |  | 2017-06-30 |  | Tests run
IPv6-only WN tests completed for LHC Vos |  |  |  |  | 2017-06-30 |  | Tests on IPv6 WN (at Brunel in first instance) completed
Further progress on CentOS07 deployments |  |  |  |  | 2017-06-30 |  | CentOS7 instances tested and functioning
2017-06-30
See Tier-2 reports for site specific objectives (e.g. MISP for content sharing, further work on tarball WN, setting up pakiti, maintain patching levels, update configuration managers (e.g. to Puppet 3)). |  |  |  |  | Various |  | Various
Update the GridPP users guide (created by Tom Whyntie) |  |  |  |  | 2017-06-30 |  | User guide updated.
New hardware (currently in test) in production during the quarter. |  |  |  |  | 2017-06-30 |  | Hardware in production
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016 | Successes Q4 2016 | Concerns Q4 2016 | Successes Q1 2017 | Concerns Q1 2017
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus. Not much detail reported but DIRAC did run into limitations recently. Contributing to ROD.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK.
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete. |  | Steady contributions. Some work on tarball.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS? |  |  | Focus elsewhere.
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes. |  | Useful contributions to documentation and following up on procedures.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7. |  | * Good WLCG & experiment feedback on tests being undertaken with CentOS7.
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD |  | * VAC/Vcycle improvements and rollout. * Good support of SKA VO. * ROD
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD |  | * GridPP Nagios & ROD
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh. |  | * Occasional attendance at ops meeting to discuss perfSONAR mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October). |  | * Good engagement with other Vos but reporting could be improved. | * Fresh look at ops tasks needed. Fewer people in team and changing priorities (plus split with evolution group) means things less well managed. | * Business as usual for most of the above areas. | Loss of VO Nagios gives less visibility for core ops team to be proactive spotting smaller VO problems.

## Narrative Q217
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * Additional hardware installed - Bristol, Durham, Glasgow, IC, Lancaster, Sheffield…. * Sussex doubled logical CPU number. * Good EGI availablility and reliability for NGI UK this quarter. |  |  |  |  | * Machine room/rack space - is noted as an issue at some times (e.g. Durham) * Bristol site outages due to HPC power problems (25 hours in total in two days). * Sites reporting storage going EOL (e.g. Bristol and Lancaster headnode).
Vos | * First steps for CMS cache testing started (e.g. Oxford installed xrootd server). * Increased participation in "other communities" collaborating discussions (e.g. pre-GDB in June) |  |  |  |  | * Small data loss at Durham (hardware failure) * Storage accounting issue at Sheffield for ATLAS
Middleware/services | * Moved to cvmfs repo for the GridPP VO * Continured migration of services and WNs to SL7/CentOS7 (Durham, Glasgow, Britol, Cambridge… ) Strong theme for this quarter. * Singularity deployed/tested at IC, Bristol and other sites * Proxmox Vmhost working for QMUL * RHUL moved to UMD * Birmingham VAC migration going well. * Various version updates applied (dCache, DPM, HTC...) * UMD4 SL6 and CentOS7 tarballs updated * ZFS usage increasing * Increasing use and development of GridPP DIRAC (several updates to GridPP DIRAC VMs). * Moved to perfSONAR 4. |  |  |  |  | * There was an RHEL/SL 6.9 openssl issue in April that affected many sites * VAC accounting distorted at Glasgow due to error/bug in multi-core HS06 values. * Sussex site capacity incorrectly published.
Site infrastructure | * New NAT gateway at Brunel. * Refurbishment of Liverpool server room (c/o facilities) |  |  |  |  | * Sites still in local discussions about IPv6 rollout plans (e.g. Liverpool) * perfSONAR nodes now out of warranty. Queries about replacements! * IPv6 roadblock at Sheffield due to support issues from University provider. * Some RIPE ATLAS probes reported as having hardware issues.
Other | * New data management staff member at ECDF. * IPv6 training contributions at WLCG workshop * GOCDB information review completed. * GPU price/performance tests underway at QMUL * Kernel updates applied in timely fashion across most sites. * Good engagement in CHEP reviews * Good attendance at the WLCG workshop hosted in Manchester in June * Culled obsolete ops documents. |  |  |  |  | * Some Tier-2 reports have minimal content. * Bristol reports a severe shortage of staff * Queue structure at Sussex led to ops tests failures until single dedicated queue was created.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). Q217: Experience shows few problems remain unresolved with running on SL7 though not all workloads have yet to be migrated. |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise. Q416: SL5 no longer an issue. Testing on CentOS7 coming along well. Q217: Continued testing at a larger sampling of sites.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. - Q217: Continued moved to HTC. Only smaller sites remain on TM. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. Q217: Failure to meet WLCG timelines is the new form of this risk. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
Hardware reaching end-of-life without spares available - leading to reductions in capacity Q217: This is increasingly becoming an issue rather than a risk, however new hardware has been deployed so impacts will be minimal. |  |  |  |  | Ensure H/W grants appropriately distributed and timely to allow replacements. (Note many sites are well over capacity so the risk is about maintaining resource levels not yet meeting pledges).
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams. Q414 - Durham continues with issues but has progressed testing
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Durham disk becoming unreliable. |  |  |  |  | Replace disks and disable RAID verify/scrub which has led to previous problems.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* VO NAGIOS is not supported beyond SL5 and ARGO development of similar functionality for regional use is not planned. Q416 - this will soon be an issue. There is no regional option being made available. |  |  |  |  | * Escalate concerns to EGI. * Perhaps trial on SL6!
* Lancaster NAT may not cope with federated access demands * Lancaster headnode out of warranty and may fail |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.
Glasgow: Air Condition/power issues leading to damaged equipment |  |  |  |  | Site admins working with estates to supply new data facility, now scheduled for Aug 2017
*ECDF use of RDF disk in production may lead to performance impacts. |  |  |  |  | Work closely with RDF team. Document the operations approach. .
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
UK pakiti instance available for initial tests |  |  |  |  | 2017-06-30 |  | Tests run
IPv6-only WN tests completed for LHC Vos |  |  |  |  | 2017-06-30 |  | Tests on IPv6 WN (at Brunel in first instance) completed
Further progress on CentOS07 deployments |  |  |  |  | 2017-06-30 |  | CentOS7 instances tested and functioning
2017-06-30
See Tier-2 reports for site specific objectives (e.g. MISP for content sharing, further work on tarball WN, setting up pakiti, maintain patching levels, update configuration managers (e.g. to Puppet 3)). |  |  |  |  | Various |  | Various
Update the GridPP users guide (created by Tom Whyntie) |  |  |  |  | 2017-06-30 |  | User guide updated.
New hardware (currently in test) in production during the quarter. |  |  |  |  | 2017-06-30 |  | Hardware in production
Progress to phasing out YAIM |  |  |  |  | 2017-03-31 |  | Clarity on plans to remove YAIM.
See also deliverables in T2 reports.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
Singularity evaluation completed |  |  |  |  | 2017-08-30 |  | Results from ECDF group
Ansible based deployment of ARC progressed |  |  |  |  | 2017-08-30 |  | Scripts available for those sites needing it (e.g ECDF).
Continued migration to SL7/CentOS7 |  |  |  |  | 2017-09-30 |  | Increased resources on SL7/CentOS7
Additional sites with dualstack Ses |  |  |  |  | 2017-09-30 |  | At least two more sites with dualstack SE
GridPP5 HW purchases undertaken |  |  |  |  | 2017-09-30 |  | Remaining sites procure h/w (e.g. Liverpool)
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016 | Successes Q4 2016 | Concerns Q4 2016 | Successes Q1 2017 | Concerns Q1 2017 | Successes Q2 2017 | Concerns Q2 2017
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus. Not much detail reported but DIRAC did run into limitations recently. Contributing to ROD. |  |  |  | * Continued development of modules for DIRAC. Service generally run with good uptime.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  |  |  | * EGI ops engagement and WLCG security work continues (focus on Bro)
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete. |  | Steady contributions. Some work on tarball. |  |  |  | * Produced tarball updates * Great ticket reviews at ops meetings.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS? |  |  | Focus elsewhere. |  |  | * Supporting some of our 'other Vos' * Organisation of WLCG workshop
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes. |  | Useful contributions to documentation and following up on procedures. |  |  |  | * Document review and cull this quarter.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7. |  | * Good WLCG & experiment feedback on tests being undertaken with CentOS7. |  |  |  | * CentOS7/SL7 testing
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD |  | * VAC/Vcycle improvements and rollout. * Good support of SKA VO. * ROD |  |  |  | * Continuted focus on T2 evolution.
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD |  | * GridPP Nagios & ROD |  |  |  | * ROD work
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh. |  | * Occasional attendance at ops meeting to discuss perfSONAR mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October). |  | * Good engagement with other Vos but reporting could be improved. | * Fresh look at ops tasks needed. Fewer people in team and changing priorities (plus split with evolution group) means things less well managed. | * Business as usual for most of the above areas. | Loss of VO Nagios gives less visibility for core ops team to be proactive spotting smaller VO problems.

## Narrative Q317
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * Sussex resolved BDII conflict so now correctly publishing. * QMUL: Tendered and brought and physical installed an additional 2.4PB of storage (1.7PB actual after raid and formatting) ; Brought and installed new rack for storage; Brought and tested a consumer GPU node (Nvidia GTX1080Ti) * Storage accounting publishing introduced at several sites. |  |  |  |  | * ECDF Scheduling issues on OpenStack led to reduced cluser usage. * Birmingham: Airconf failure led to extended time with 1/2 capcity. * Bristol: 2 day outage due to powercut * VAC REBUS numbers wrong (noted by Cambridge). * Sussex removing old 64-core nodes.
Vos | * Birmingham has a new VO box for ALICE * Cambridge VAC set up on five recently purchased servers. Support for skatelescope.eu added to VAC and storage. * NA62 and skatelescope Vos enabled at Lancaster * VAC running at RHUL for LHCb * In September running LHCb production MC in Docker and Singularity containers on Vac. |  |  |  |  | * LHCb usage affected by disk configuration issue at Glasgow. * Some Vos require SL6 preventing (e.g. Lancaster) full move to CentOS7.
Middleware/services | * Additional sites have moved services to SL7 (Durham) or in testing (e.g. Sheffield) * Majority of Lancaster resources now on CentOS7 * Investigating GPU queues with some Vos. |  |  |  |  | * Birmingham has issues with torque. * RALPP suffered ARGUS node failure.
Site infrastructure | * ECDF hypervisor issues resolved/mitigated. * Glasgow containerised WNs running ATLAS multocore jobs * Oxford moved to native IPv6 support on edge router. * Liverpool completed machine room move. * Networking forward look document updated (contributions from many sites). |  |  |  |  | * Durham suffered a datacentre power outage led to a network switch failure. * Oxford networking issues during August. * RALPP perfSONAR node crashes. * Bristol perfSONAR responsibilities switched back to group.
Other | * Teng Li joined the ECDF team (joint GridPP DM and LSST). * New BRO and MISP instances at Glasgow. * New CentOS7 WN documentation using Puppet3/Hiera. * Several Vos decommisioned (e.g. the regional Vos). * Vac-in-a-Box running on CentOS7. |  |  |  |  | * Oliver Smith left Durham which removes their backup sysadmin (remaining sysadmin Adam now overcommited?) * Bristol reports shortages of staff impacting operations. * Vac-in-a-box issues encountered in July with respect to firewwalls. * Bug in Safari on macOS caused random Apple generated client cert to be presented to www.gridpp.ac.uk in September
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). Q217: Experience shows few problems remain unresolved with running on SL7 though not all workloads have yet to be migrated. |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise. Q416: SL5 no longer an issue. Testing on CentOS7 coming along well. Q217: Continued testing at a larger sampling of sites.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. - Q217: Continued moved to HTC. Only smaller sites remain on TM. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. Q217: Failure to meet WLCG timelines is the new form of this risk. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
Hardware reaching end-of-life without spares available - leading to reductions in capacity Q217: This is increasingly becoming an issue rather than a risk, however new hardware has been deployed so impacts will be minimal. |  |  |  |  | Ensure H/W grants appropriately distributed and timely to allow replacements. (Note many sites are well over capacity so the risk is about maintaining resource levels not yet meeting pledges).
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams.
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Durham disk becoming unreliable and site now down to single sysadmin covering grid and local cluster. |  |  |  |  | Replace disks and disable RAID verify/scrub which has led to previous problems. Q317: Durham recruiting a second sysadmin.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* VO NAGIOS is not supported beyond SL5 and ARGO development of similar functionality for regional use is not planned. Q416 - this will soon be an issue. There is no regional option being made available. |  |  |  |  | * Escalate concerns to EGI. * Perhaps trial on SL6!
* Lancaster NAT may not cope with federated access demands * Lancaster headnode out of warranty and may fail |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.Q317: Lancaster headnode still not replaced.
Glasgow: Air Condition/power issues leading to damaged equipment |  |  |  |  | Site admins working with estates to supply new data facility, now scheduled for Aug 2017. Q317: E&B work remains scheduled for August? Needs to be checked.
*ECDF use of RDF disk in production may lead to performance impacts. |  |  |  |  | Work closely with RDF team. Document the operations approach. .
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
Singularity evaluation completed |  |  |  |  | 2017-08-30 |  | Results from ECDF group
Ansible based deployment of ARC progressed |  |  |  |  | 2017-08-30 |  | Scripts available for those sites needing it (e.g ECDF).
Continued migration to SL7/CentOS7 |  |  |  |  | 2017-09-30 |  | Increased resources on SL7/CentOS7
Additional sites with dualstack Ses |  |  |  |  | 2017-09-30 |  | At least two more sites with dualstack SE
GridPP5 HW purchases undertaken |  |  |  |  | 2017-09-30 |  | Remaining sites procure h/w (e.g. Liverpool)
See also deliverables in T2 reports.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
See also deliverables in T2 reports. |  |  |  |  | Various |  | Various
ECDF: Investigation and testing of XRootD Caching |  |  |  |  | 2017-12-31 |  | Will build a XRootD caching test-bed on top of Openstack WNs, to see if everything works properly and how is the performance
Additional resources moved to SL7 (Durham, ) or in test Sheffield |  |  |  |  | 31/09/17 |  | Services on Sl7
(RALPP, Liverpool) new hardware purchased |  |  |  |  | 31/09/17 |  | Order placed and equipment onsite.
Large scale tarball update |  |  |  |  | End of year |  | New tarballs available.
Continued IPv6 rollout |  |  |  |  | Ongoing
Meet CMS singularity requirement for March 2018 |  |  |  |  | Ongoing
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016 | Successes Q4 2016 | Concerns Q4 2016 | Successes Q1 2017 | Concerns Q1 2017 | Successes Q2 2017 | Concerns Q2 2017
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus. Not much detail reported but DIRAC did run into limitations recently. Contributing to ROD. |  |  |  | * Continued development of modules for DIRAC. Service generally run with good uptime.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  |  |  | * EGI ops engagement and WLCG security work continues (focus on Bro)
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete. |  | Steady contributions. Some work on tarball. |  |  |  | * Produced tarball updates * Great ticket reviews at ops meetings.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS? |  |  | Focus elsewhere. |  |  | * Supporting some of our 'other Vos' * Organisation of WLCG workshop
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes. |  | Useful contributions to documentation and following up on procedures. |  |  |  | * Document review and cull this quarter.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7. |  | * Good WLCG & experiment feedback on tests being undertaken with CentOS7. |  |  |  | * CentOS7/SL7 testing
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD |  | * VAC/Vcycle improvements and rollout. * Good support of SKA VO. * ROD |  |  |  | * Continuted focus on T2 evolution.
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD |  | * GridPP Nagios & ROD |  |  |  | * ROD work
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh. |  | * Occasional attendance at ops meeting to discuss perfSONAR mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October). |  | * Good engagement with other Vos but reporting could be improved. | * Fresh look at ops tasks needed. Fewer people in team and changing priorities (plus split with evolution group) means things less well managed. | * Business as usual for most of the above areas. | Loss of VO Nagios gives less visibility for core ops team to be proactive spotting smaller VO problems.

## Narrative Q417
GridPP Quarterly Report
Area | Operations
Year | 2017
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * ECDF deployment of Cloud Scheduler on our Eddie Openstack allocation. Now continually running ATLAS jobs on 25 VMs (400 cores * Many sites have now placed orders for additional hardware (CPU and storage). * Additional 1.6PB storage commissioned at QMUL (site now has 5.1PB) |  |  |  |  | *
Vos | * GridPP DIRAC tests now running at Sussex. * Passed LZ Data-centre review (both IC & GridPP as a whole). * Started receiving production SoLiD data. * CERN@School running machine learning at QMUL |  |  |  |  | * Data loss at Glasgow impacted ATLAS
Middleware/services | * Birmingham now fully VAC enabled. * WMSes decommisioned. |  |  |  |  | *
Site infrastructure | * Increased dual-stacked resources (IPv6) across GridPP sites * xcache work progressing * Proto-success - Glasgow DC expected to commence Q118. * Bristol machine room consolidation undertaken with minimal impact on availability |  |  |  |  | * Migration to CentOS7 not as fast as expected. * RHUL reliability and availability are down this quarter to due to network maintenance
Other | * Improved documentation in a number of areas (accounting audit, VO maintenance, C7 adoption, github) * New sysadmin at Durham * Increased usage/rollout of BRO and MISP * Storage accounting validated for some sites. |  |  |  |  | * Informed Germany is leaving EGI from January 2018. GGUS will continue to be provided for WLCG.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). Q217: Experience shows few problems remain unresolved with running on SL7 though not all workloads have yet to be migrated. |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise. Q416: SL5 no longer an issue. Testing on CentOS7 coming along well. Q217: Continued testing at a larger sampling of sites.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. - Q217: Continued moved to HTC. Only smaller sites remain on TM. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. Q217: Failure to meet WLCG timelines is the new form of this risk. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
Hardware reaching end-of-life without spares available - leading to reductions in capacity Q217: This is increasingly becoming an issue rather than a risk, however new hardware has been deployed so impacts will be minimal. |  |  |  |  | Ensure H/W grants appropriately distributed and timely to allow replacements. (Note many sites are well over capacity so the risk is about maintaining resource levels not yet meeting pledges).
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams.
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Durham disk becoming unreliable and site now down to single sysadmin covering grid and local cluster. |  |  |  |  | Replace disks and disable RAID verify/scrub which has led to previous problems. Q317: Durham recruiting a second sysadmin.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* VO NAGIOS is not supported beyond SL5 and ARGO development of similar functionality for regional use is not planned. Q416 - this will soon be an issue. There is no regional option being made available. |  |  |  |  | * Escalate concerns to EGI. * Perhaps trial on SL6!
* Lancaster NAT may not cope with federated access demands * Lancaster headnode out of warranty and may fail |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.Q317: Lancaster headnode still not replaced.
Glasgow: Air Condition/power issues leading to damaged equipment |  |  |  |  | Site admins working with estates to supply new data facility, now scheduled for Aug 2017. Q317: E&B work remains scheduled for August? Needs to be checked.
*ECDF use of RDF disk in production may lead to performance impacts. |  |  |  |  | Work closely with RDF team. Document the operations approach. .
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
See also deliverables in T2 reports. |  |  |  |  | Various |  | Various
ECDF: Investigation and testing of XRootD Caching |  |  |  |  | 2017-12-31 |  | Will build a XRootD caching test-bed on top of Openstack WNs, to see if everything works properly and how is the performance
Additional resources moved to SL7 (Durham, ) or in test Sheffield |  |  |  |  | 31/09/17 |  | Services on Sl7
(RALPP, Liverpool) new hardware purchased |  |  |  |  | 31/09/17 |  | Order placed and equipment onsite.
Large scale tarball update |  |  |  |  | End of year |  | New tarballs available.
Continued IPv6 rollout |  |  |  |  | Ongoing
Meet CMS singularity requirement for March 2018 |  |  |  |  | Ongoing
See also deliverables in T2 reports.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
Continuned adoption of IPv6 |  |  |  |  | To late 2018
Fuller rollout of CentOS7 |  |  |  |  | To mid-2018
Deploy new hardware |  |  |  |  | 2018-03-31 |  | Hardware on-site.
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016 | Successes Q4 2016 | Concerns Q4 2016 | Successes Q1 2017 | Concerns Q1 2017 | Successes Q2 2017 | Concerns Q2 2017
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus. Not much detail reported but DIRAC did run into limitations recently. Contributing to ROD. |  |  |  | * Continued development of modules for DIRAC. Service generally run with good uptime.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  |  |  | * EGI ops engagement and WLCG security work continues (focus on Bro)
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete. |  | Steady contributions. Some work on tarball. |  |  |  | * Produced tarball updates * Great ticket reviews at ops meetings.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS? |  |  | Focus elsewhere. |  |  | * Supporting some of our 'other Vos' * Organisation of WLCG workshop
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes. |  | Useful contributions to documentation and following up on procedures. |  |  |  | * Document review and cull this quarter.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7. |  | * Good WLCG & experiment feedback on tests being undertaken with CentOS7. |  |  |  | * CentOS7/SL7 testing
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD |  | * VAC/Vcycle improvements and rollout. * Good support of SKA VO. * ROD |  |  |  | * Continuted focus on T2 evolution.
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD |  | * GridPP Nagios & ROD |  |  |  | * ROD work
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh. |  | * Occasional attendance at ops meeting to discuss perfSONAR mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October). |  | * Good engagement with other Vos but reporting could be improved. | * Fresh look at ops tasks needed. Fewer people in team and changing priorities (plus split with evolution group) means things less well managed. | * Business as usual for most of the above areas. | Loss of VO Nagios gives less visibility for core ops team to be proactive spotting smaller VO problems.

## Narrative Q118
GridPP Quarterly Report
Area | Operations
Year | 2018
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * QMUL additional 170TB for ATLAS full. * 140TB deployed at Durham * Revised/improved A/R calculation for WLCG |  |  |  |  | * 10% of Liverpool disk resource now used by non-LHC Vos.
Vos | * IC: 170 TB Solid data already on site. Taking part in LZ Mock Data Challenge * Increased support for DUNE and protoDUNE. * solidexperiment.org added to approved Vos list.
Middleware/services | * New WN/UI tarball available (but testing constrained). * VAC deployed at Glasgow. * VAC 3.0 released. * Sites moved to UMD4.0.
Site infrastructure
Other | * MISP/BRO testing extended. * LHCOPN/LHCONE meeting at RAL in March. |  |  |  |  | * Spectre/meltdown patching very disruptive.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). Q217: Experience shows few problems remain unresolved with running on SL7 though not all workloads have yet to be migrated. |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise. Q416: SL5 no longer an issue. Testing on CentOS7 coming along well. Q217: Continued testing at a larger sampling of sites.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. - Q217: Continued moved to HTC. Only smaller sites remain on TM. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. Q217: Failure to meet WLCG timelines is the new form of this risk. Q!18: University wider support of IPv6 deployment is hindering GridPP T2 work. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
Hardware reaching end-of-life without spares available - leading to reductions in capacity Q217: This is increasingly becoming an issue rather than a risk, however new hardware has been deployed so impacts will be minimal. |  |  |  |  | Ensure H/W grants appropriately distributed and timely to allow replacements. (Note many sites are well over capacity so the risk is about maintaining resource levels not yet meeting pledges).
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams.
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Durham disk becoming unreliable and site now down to single sysadmin covering grid and local cluster. |  |  |  |  | Replace disks and disable RAID verify/scrub which has led to previous problems. Q317: Durham recruiting a second sysadmin.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* VO NAGIOS is not supported beyond SL5 and ARGO development of similar functionality for regional use is not planned. Q416 - this will soon be an issue. There is no regional option being made available. |  |  |  |  | * Escalate concerns to EGI. * Perhaps trial on SL6!
* Lancaster NAT may not cope with federated access demands * Lancaster headnode out of warranty and may fail |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.Q317: Lancaster headnode still not replaced.
Glasgow: Air Condition/power issues leading to damaged equipment |  |  |  |  | Site admins working with estates to supply new data facility, now scheduled for Aug 2017. Q317: E&B work remains scheduled for August? Needs to be checked.
*ECDF use of RDF disk in production may lead to performance impacts. |  |  |  |  | Work closely with RDF team. Document the operations approach. .
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
See also deliverables in T2 reports. |  |  |  |  | Various |  | Various
CentOS7 - further rollout of nodes |  |  |  |  | Ongoing
Continued IPv6 rollout |  |  |  |  | Ongoing
Meet CMS singularity requirement for March 2018 |  |  |  |  | Done
See also deliverables in T2 reports.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
Continuned adoption of IPv6 |  |  |  |  | Until late 2018
Fuller rollout of CentOS7 |  |  |  |  | To mid-2018
Deploy new hardware |  |  |  |  | 2018-07-31 |  | Hardware on-site.
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016 | Successes Q4 2016 | Concerns Q4 2016 | Successes Q1 2017 | Concerns Q1 2017 | Successes Q2 2017 | Concerns Q2 2017
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus. Not much detail reported but DIRAC did run into limitations recently. Contributing to ROD. |  |  |  | * Continued development of modules for DIRAC. Service generally run with good uptime.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  |  |  | * EGI ops engagement and WLCG security work continues (focus on Bro)
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete. |  | Steady contributions. Some work on tarball. |  |  |  | * Produced tarball updates * Great ticket reviews at ops meetings.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS? |  |  | Focus elsewhere. |  |  | * Supporting some of our 'other Vos' * Organisation of WLCG workshop
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes. |  | Useful contributions to documentation and following up on procedures. |  |  |  | * Document review and cull this quarter.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7. |  | * Good WLCG & experiment feedback on tests being undertaken with CentOS7. |  |  |  | * CentOS7/SL7 testing
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD |  | * VAC/Vcycle improvements and rollout. * Good support of SKA VO. * ROD |  |  |  | * Continuted focus on T2 evolution.
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD |  | * GridPP Nagios & ROD |  |  |  | * ROD work
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh. |  | * Occasional attendance at ops meeting to discuss perfSONAR mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October). |  | * Good engagement with other Vos but reporting could be improved. | * Fresh look at ops tasks needed. Fewer people in team and changing priorities (plus split with evolution group) means things less well managed. | * Business as usual for most of the above areas. | Loss of VO Nagios gives less visibility for core ops team to be proactive spotting smaller VO problems.

## Narrative Q218
GridPP Quarterly Report
Area | Operations
Year | 2018
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * Additional GridPP5 HW resource has come online (e.g. Liverpool) * RALPP 560TB new disk deployed, (380TB old DIsk retired).12 New WNs (192 slots@11.39 = ~6.5kHS06) also installed |  |  |  |  | * Old storage nodes (>5yrs) noted as failing (e.g. RHUL). * Birmingham has had reduced CPU available due to aircon issues.
Vos | * Birmingham - xrootd storage decomissioned and resources moved over to EOS for ALICE. * skatelescope.eu now can use multicore on VAC at Cambridge. * Oxford added support for the DUNE and solid VO's * Liverpool ramping up support fo DUNE. * Steady progresse supporting LSST DESC data challenge on GridPP resources. * Approved VOs now contains two new SKA VOMS servers (at Oxford and Imperial, as well as Manchester)
Middleware/services | * Services moved to UMD4.0 at several sites (e.g. Glasgow) * Sussex resolved issue preventing DIRAC jobs from running * In June "Universal" DIRAC VMs deployed in production for GridPP DIRAC and LHCb * LHCb Docker containers in production testing at Manchester |  |  |  |  | * VAC timeouts seen at Liverppol.
Site infrastructure | * New racks and PDUs at QMUL. * Durham: work with JISC and University IT (CIS) has moved the 10GB/s Network connection forwards and an end is in sight! * ECDF Increase of Eddie ringfence allocation to >1,000 cores. * Glasgow: A building warrant has been issued for the construction of the new Data Centre which will allow construction to commence. |  |  |  |  | * Intermittent problems with time sync on SE causing storage failures, and some worker nodes. Tomcat often gets stuck on Ces at RHUL * A number of sites waiting on campus networking for any further IPv6 progress. * ECDF: Increased pressure to reduce rackspace at Advanced Computing Facility
Other | * Ongoing ansible work at a number of sites (improves autmation): QMUL and Lanacaster for example. * Good support for Authorization & Authentication Infrastructure for WLCG workshop. * Annual review of GOCDB information completed (under EGI activity). |  |  |  |  | * Staff reductions seen at RHUL in April (site is trying to maintain services now with 0.5FTE) and Glasgow lost David Crooks (1FTE). * Quarterly reports from Tier-2s this quarter very late and somewhat sparse in places (perhaps reflecting reducing effort available). * Bristol mention several activities not being undertaken due to staff shortages.
Note:To get multiple lines per box use Alt-Return | [5 empty] | * Staff reductions seen at RHUL in April. Site is trying to maintain services now with 0.5FTE.
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). Q217: Experience shows few problems remain unresolved with running on SL7 though not all workloads have yet to be migrated. |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise. Q416: SL5 no longer an issue. Testing on CentOS7 coming along well. Q217: Continued testing at a larger sampling of sites.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. - Q217: Continued moved to HTC. Only smaller sites remain on TM. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. Q217: Failure to meet WLCG timelines is the new form of this risk. Q!18: University wider support of IPv6 deployment is hindering GridPP T2 work. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
Hardware reaching end-of-life without spares available - leading to reductions in capacity Q217: This is increasingly becoming an issue rather than a risk, however new hardware has been deployed so impacts will be minimal. |  |  |  |  | Ensure H/W grants appropriately distributed and timely to allow replacements. (Note many sites are well over capacity so the risk is about maintaining resource levels not yet meeting pledges).
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams.
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Durham disk becoming unreliable and site now down to single sysadmin covering grid and local cluster. |  |  |  |  | Replace disks and disable RAID verify/scrub which has led to previous problems. Q317: Durham recruiting a second sysadmin.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* VO NAGIOS is not supported beyond SL5 and ARGO development of similar functionality for regional use is not planned. Q416 - this will soon be an issue. There is no regional option being made available. |  |  |  |  | * Escalate concerns to EGI. * Perhaps trial on SL6!
* Lancaster NAT may not cope with federated access demands * Lancaster headnode out of warranty and may fail |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.Q317: Lancaster headnode still not replaced.
Glasgow: Air Condition/power issues leading to damaged equipment |  |  |  |  | Site admins working with estates to supply new data facility, now scheduled for Aug 2017. Q317: E&B work remains scheduled for August? Needs to be checked.
*ECDF use of RDF disk in production may lead to performance impacts. |  |  |  |  | Work closely with RDF team. Document the operations approach. .
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
See also deliverables in T2 reports. |  |  |  |  | Various |  | Various
CentOS7 - further rollout of nodes |  |  |  |  | Ongoing
Continued IPv6 rollout |  |  |  |  | Ongoing
See also deliverables in T2 reports.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
Continuned adoption of IPv6 |  |  |  |  | Until late 2018 - T2s should have dual stack storage by the end of 2018.
Fuller rollout of CentOS7 |  |  |  |  | Continuous
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016 | Successes Q4 2016 | Concerns Q4 2016 | Successes Q1 2017 | Concerns Q1 2017 | Successes Q2 2017 | Concerns Q2 2017
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus. Not much detail reported but DIRAC did run into limitations recently. Contributing to ROD. |  |  |  | * Continued development of modules for DIRAC. Service generally run with good uptime.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  |  |  | * EGI ops engagement and WLCG security work continues (focus on Bro)
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete. |  | Steady contributions. Some work on tarball. |  |  |  | * Produced tarball updates * Great ticket reviews at ops meetings.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS? |  |  | Focus elsewhere. |  |  | * Supporting some of our 'other Vos' * Organisation of WLCG workshop
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes. |  | Useful contributions to documentation and following up on procedures. |  |  |  | * Document review and cull this quarter.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7. |  | * Good WLCG & experiment feedback on tests being undertaken with CentOS7. |  |  |  | * CentOS7/SL7 testing
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD |  | * VAC/Vcycle improvements and rollout. * Good support of SKA VO. * ROD |  |  |  | * Continuted focus on T2 evolution.
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD |  | * GridPP Nagios & ROD |  |  |  | * ROD work
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh. |  | * Occasional attendance at ops meeting to discuss perfSONAR mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October). |  | * Good engagement with other Vos but reporting could be improved. | * Fresh look at ops tasks needed. Fewer people in team and changing priorities (plus split with evolution group) means things less well managed. | * Business as usual for most of the above areas. | Loss of VO Nagios gives less visibility for core ops team to be proactive spotting smaller VO problems.

## Narrative Q318
GridPP Quarterly Report
Area | Operations
Year | 2018
Reported by | Jeremy Coles
Progress over last Quarter
Work area | Successes |  |  |  |  | Problems/Issues
Site resources available | * Additional GridPP5 HW resource has come online (e.g. Liverpool) * RALPP 560TB new disk deployed, (380TB old DIsk retired).12 New WNs (192 slots@11.39 = ~6.5kHS06) also installed * Work starting on IRIS H/W deployments |  |  |  |  | * Old storage nodes (>5yrs) noted as failing (e.g. RHUL). * Birmingham has had reduced CPU available due to aircon issues.
Vos | * Birmingham - xrootd storage decomissioned and resources moved over to EOS for ALICE. * skatelescope.eu now can use multicore on VAC at Cambridge. * Oxford added support for the DUNE and solid VO's * Liverpool ramping up support fo DUNE. * Steady progresse supporting LSST DESC data challenge on GridPP resources. * Approved VOs now contains two new SKA VOMS servers (at Oxford and Imperial, as well as Manchester) |  |  |  |  | * Waiting for ATLAS to decide if and how to move SAM tests to VAC
Middleware/services | * Services moved to UMD4.0 at several sites (e.g. Glasgow) * Sussex resolved issue preventing DIRAC jobs from running * In June "Universal" DIRAC VMs deployed in production for GridPP DIRAC and LHCb * LHCb Docker containers in production testing at Manchester * Singularity installed and working at a number of sites. |  |  |  |  | * VAC timeouts seen at Liverpool. * Instabilities with VAC3 on CS7 (especially with singlecore factories) an issue (VAC3 on SL6 is OK). * Latest DOME release causing teething issues at several sites (e.g. Liverpool).
Site infrastructure | * New racks and PDUs at QMUL. * Durham: work with JISC and University IT (CIS) has moved the 10GB/s Network connection forwards and an end is in sight! * ECDF Increase of Eddie ringfence allocation to >1,000 cores. * Glasgow: A building warrant has been issued for the construction of the new Data Centre which will allow construction to commence. |  |  |  |  | * Intermittent problems with time sync on SE causing storage failures, and some worker nodes. Tomcat often gets stuck on Ces at RHUL * A number of sites waiting on campus networking for any further IPv6 progress. * ECDF: Increased pressure to reduce rackspace at Advanced Computing Facility * Major issues with cooling and two planned power outages limited operations over the summer at QMUL. Two new cooling units have been installed and commissioned replacing two broken units. The building where the Cluster is located now has an additional power supply.
Other | * Ongoing ansible work at a number of sites (improves autmation): QMUL and Lanacaster for example. * Good support for Authorization & Authentication Infrastructure for WLCG workshop. * Annual review of GOCDB information completed (under EGI activity). * Sussex availability much improved. |  |  |  |  | * Staff reductions seen at RHUL in April (site is trying to maintain services now with 0.5FTE) and Glasgow lost David Crooks (1FTE). * Quarterly reports from Tier-2s this quarter very late and somewhat sparse in places (perhaps reflecting reducing effort available). * Bristol mention several activities not being undertaken due to staff shortages. * Sussex also mention issues with manpower.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  |  |  |  | Mitigating Action
* Middleware/experiment software does not run smoothly on SL7/CentOS7. Q116 SL5 is receiving a deadline so sites wanting to move directly to CentOS7 may now have to step via SL6. Q216 - SL7 testing work is going well at several sites. This risk is reducing. Q316 - testing continues but some sites have poor utilisation as a consequence of resources being on CentOS7.(A related risk is that it turns out a few hidden nodes across sites are still running on SL5 - these must be removed by March 2017). Q217: Experience shows few problems remain unresolved with running on SL7 though not all workloads have yet to be migrated. |  |  |  |  | * Work with WLCG middleware readiness group and experiments directly to test against SL7/Centos7 Q415: Work has started on this at ECDF. Q316: Good progress but problems continue to arise. Q416: SL5 no longer an issue. Testing on CentOS7 coming along well. Q217: Continued testing at a larger sampling of sites.
Many sites are on torque/maui which is unsupported. This risk is reducing as momentum towards other batch systems - particularly condor - has increased. - Q3 2015: Further reduction in risk as more sites running test batch systems or have moved from torque/maui. - Q4 2015: HTC CE now also available at Bristol - Q2 2016: Further moves away from Maui. E.g. Bristol. - Q217: Continued moved to HTC. Only smaller sites remain on TM. |  |  |  |  | Encourage sites to share experiencse with new batch systems and options.Update in Q114 - there is increasing testing and deployment of new batch systems. As of Q2 2015 the majority of GridPP sites have looked at alternatives and many have deployed. There remains a risk though with about 5 sites still relying on Torque-Maui.
Transition to IPv6 is not smooth - this is a WLCG wide risk - or end-to-end network problems are difficult to trace to their source. Campus readiness remains a concern. Risk remains in Q115 - many WLCG T1 sites missed an IPv6 target for the end of March. Q415: This risk is reducing in terms of middleware/experiment services tested against IPv6 but the transition at sites is extremely slow. This risk remains. Q216: WLCG plans seem to have slipped. Site progress within GridPP sites remains slow. Q217: Failure to meet WLCG timelines is the new form of this risk. Q!18: University wider support of IPv6 deployment is hindering GridPP T2 work. |  |  |  |  | Contribute effort to IPv6 testing activities. Continued good UK contributions. Site progress and position is now actively being tracked.
Insufficient manpower at sites - either due to people leaving or to cope with level of resources now in production at sites. This has reduced slightly in Q1 2014. - Q3 2015: Increase seen with Durham long-term leave issue and Sussex sysadmin will be leaving in Q4. - Q2 2016: * Effort/Resources: Sussex resource is too low to maintain efficient contribution. (Matt RB recently left… ). Oxford have had to refocus on core business due to staff moves. Additional unfunded sites in GridPP5. RALPP lost FM. |  |  |  |  | Sites are adopting a steady approach and learning about issues through each other. Good communicaiton is important. GridPP is also contributing to the WLCG discussion about minimum/baseline versions and a transition strategy: https://twiki.cern.ch/twiki/bin/view/LCG/WLCGBaselineVersions. Contribute actively to the staged rollout of EMI/UMD components.
Vulnerability updates disrupt normal site operations or ability to make progress with new areas of work. |  |  |  |  | Quick assessments to ensure updates needed. Automate as much as possible of the update process. Ensure sites communicate tricks and tips!
Hardware reaching end-of-life without spares available - leading to reductions in capacity Q217: This is increasingly becoming an issue rather than a risk, however new hardware has been deployed so impacts will be minimal. |  |  |  |  | Ensure H/W grants appropriately distributed and timely to allow replacements. (Note many sites are well over capacity so the risk is about maintaining resource levels not yet meeting pledges).
Q318: IRIS obligations dominate staff time needed for WLCG activities. |  |  |  |  | Ensure clear actions and plans are shared together with expectations on prioritisation of activities (Note GridPP is part of IRIS).
New technology testing does not converge on a straightforward deployable product. Experiment approaches diverge or fail to exploit new hardware. Multicore use has picked up in Q115 but site efficiencies have dropped. Some sites indicate a lack of spare resources for testing/expanding of resources |  |  |  |  | Engage with WLCG operations task forces and ensure good input to UK projects such as the cloud working group. Encourage sites to look at ways to smoothly cope with changing workloads.
Insitute or area specific risks
Risk |  |  |  |  | Mitigating Action
* Several sites are experiencing firewall or other network bottlenecks (e.g. Bristol, Durham..). Durham's situation exacerbated by DiRAC transfer work. |  |  |  |  | Ensure/encourage engagement with central IT networking teams.
Several sites still need to move away from YAIM (e.g. Lancaster and Sheffield). Q414: DPM 1.8.9 does not support YAIM. |  |  |  |  | Ensure good engagement of sites with Puppet developments and best practice.Arrange training?
* Durham disk becoming unreliable and site now down to single sysadmin covering grid and local cluster. |  |  |  |  | Replace disks and disable RAID verify/scrub which has led to previous problems. Q317: Durham recruiting a second sysadmin.
* Sussex has inadequate infrastructure monitoring |  |  |  |  | * Share approaches used at other sites
* Lancaster NAT may not cope with federated access demands * Lancaster headnode out of warranty and may fail |  |  |  |  | Continue monitoring closely and share potential issues/solutions between sites.Q317: Lancaster headnode still not replaced.
*ECDF use of RDF disk in production may lead to performance impacts. |  |  |  |  | Work closely with RDF team. Document the operations approach. .
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output/Outcome
See also deliverables in T2 reports. |  |  |  |  | Various |  | Various
CentOS7 - further rollout of nodes |  |  |  |  | Ongoing
Continued IPv6 rollout |  |  |  |  | Ongoing
See also deliverables in T2 reports.
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  |  |  |  | Due Date |  | Metric/Output
Continuned adoption of IPv6 |  |  |  |  | Until late 2018 - T2s should have dual stack storage by the end of 2018. |  | Number of sites meeting target (storage and perfSONAR dual stacked)
Fuller rollout of CentOS7 |  |  |  |  | Continuous |  | Additional resources on CS7.
Additional sites have deployed and configured singualrity |  |  |  |  | 2018-12-31 |  | Singularity available at additional sites (>1 more)
Migrate DPM backends to DOME |  |  |  |  | Ongoing
Core Ops Task contributions
Name | Area | Successes Q1 2016 | Concerns Q1 2016 | Successes Q2 2016 | Concerns Q2 2016 | Successes Q3 2016 | Concerns Q3 2016 | Successes Q4 2016 | Concerns Q4 2016 | Successes Q1 2017 | Concerns Q1 2017 | Successes Q2 2017 | Concerns Q2 2017
Daniala Bauer | Staged Rollout | * Continued work on DIRAC * UK ROD work |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus including fixing bugs. |  | * DIRAC has been main focus. Not much detail reported but DIRAC did run into limitations recently. Contributing to ROD. |  |  |  | * Continued development of modules for DIRAC. Service generally run with good uptime.
David Crooks | Monitoring ?? | * See below |  | * Moved to focus on Security Operations Centre work. Going well with several GDB presentations and workshop's undertaken. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  | * Further SOC work undertaken. Conrtibuting to security team meetings. * Attending EGI ops meetings and following up on SL5 status across UK. |  |  |  | * EGI ops engagement and WLCG security work continues (focus on Bro)
Matt Doidge | Tickets & helpdesk | * Ticket updates * Maintained WN and UI updates. |  | * Doing good job with ticket reviews. * SL7 tarball work. |  | *Joined the GridPP security team. * Ticket reviews remain very useful and complete. |  | Steady contributions. Some work on tarball. |  |  |  | * Produced tarball updates * Great ticket reviews at ops meetings.
Alessandra Forti | Accounting/Security/Monitoring | * Support for LSST |  | * Good support work for several smaller Vos but particularly LSST. * More ATLAS focus? | * Less visible now. No security team participation. | * Focus has been on ATLAS? |  |  | Focus elsewhere. |  |  | * Supporting some of our 'other Vos' * Organisation of WLCG workshop
Stephen Jones | Documentation | * General documentation updates * HTC management control |  | * Documentation for cgroups. * General VO ops portal/config follow-up work. |  | * Improvements to portal entries, updates to approved Vos list and maintenance of VO RPM. * Contributing HTC/ARC fixes. |  | Useful contributions to documentation and following up on procedures. |  |  |  | * Document review and cull this quarter.
Raul Lopes | Testing/middleware | * Further WLCG MW testing work |  | * CentOS7 work with CMS. Contributing to middleware readiness activities. |  | * Continued focus on CentOS7. |  | * Good WLCG & experiment feedback on tests being undertaken with CentOS7. |  |  |  | * CentOS7/SL7 testing
Andrew McNab | Documentation/webserver | * Various VAC updates * UK ROD |  | * Various VAC updates. * ROD shifts |  | * VAC/Vcycle improvements and rollout. * ROD |  | * VAC/Vcycle improvements and rollout. * Good support of SKA VO. * ROD |  |  |  | * Continuted focus on T2 evolution.
Kashif Mohammad | Regional tools | * UK ROD * Maintaining gridppnagios and VO Nagios |  | * ROD shifts * VO nagios (note GridPP nagios being removed). |  | * ROD |  | * GridPP Nagios & ROD |  |  |  | * ROD work
David Crooks/ Raul | Interoperation | * Pulled together SL5 status update for EGI * Presented at GDB on SoC * Joining security team discussions |  | * Only 2 EGI ops meetings this quarter. Attended and prepared ops summary. * Tracked SL5 progress
Duncan Rand | Perfsonar | * Pulled together IPv6 updates for GridPP36 * Worked on IPv6 connection over LHONCE |  | * Some tickets raised related to networking issues * Attended IPv6 F2F and pre-GDB on topic of FTS tuning. | * Now seconded to JISC? Less active in ops. | * Some perfSONAR results reviews. * Working on IPv6 mesh. |  | * Occasional attendance at ops meeting to discuss perfSONAR mesh.
General | General | * Managed a core ops meeting. Not full attendance but useful. * Core docs reviewed. Need to action the review! |  |  | * Core ops work - ideas and actions suffering from less JC time available. | * Many solid contributions in run up to CHEP and WLCG workshop (October). |  | * Good engagement with other Vos but reporting could be improved. | * Fresh look at ops tasks needed. Fewer people in team and changing priorities (plus split with evolution group) means things less well managed. | * Business as usual for most of the above areas. | Loss of VO Nagios gives less visibility for core ops team to be proactive spotting smaller VO problems.

## EVAL
This page structure needs to be improved. Tier-2 reports record their individual contributions.
Q2 2015 + updates
Publications | Date | Notes
GridPP Preparing for Run-II | 2015-05-01 | Jeremy Coles - CHEP talk and paper
Dissemmination events | Date | Notes
GridPP developments and directions | 2015-04-01 | Jeremy Coles - talk at ISGC 2015
EVAL Notes Q1
Publications | Date | Notes
The Power behind CERN' article in Dec 2012 Linux Format Magazine | 2012-10-15 | Followed from an interview with Pete Gronbech (Project Manager)
CHEP Publications | 2014-01-01 | A contributions from ScotGrid (3 paper from ECDF, 3 papers from Glasgow) accepted for publication
Collaborations | Date | Notes
Landslides |  | Bristol
CAMONT |  | Cambridge/Birmingham?
VoxTox/Accel-RT | starting 09/12 | Cambridge - investigating GRID techniques
CobeBase | Ongoing | Initial steps to collaboration with Startup company in ScotGrid
Neurogrid | Aug-sep 2012 | Completed setup of the VO. Still need to help them start using it.
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs. | 2015-09-01 | Manchester
LSST | Ongoing | Marcus Ebert 50% LUSC DAC Team.
HyperK | Ongoing | ECDF aiding in moving workloads to the Grid.
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST users to adapt their workflow to use grid resources | 2015-09-01 | Manchester
Further Funding (eg external grants) | Date | Notes
Robert Frank salary currently paid by the University of Manchester | 01/09/2012-31/12/2013
Destination of ex staff and recruitment issues | Date | Notes
Santanu Das - Cambridge Sys Admin | 2012-05-24 | Left to work for DataPipe, but then moved to the Financial Times.
Mark Mitchell | 2014-03-31 | Moved to University of Glasgow - Big Data for Urban Studies Institute
Oliver Smith leaving for Gibraltar and William Hill | 2017-08-28 | Durham supported by Adam Boutcher
Marcus Ebert | 2017-04-01 | University of Victoria (Canada)
Dissemmination events | Date | Notes
Particle Physics Masterclass | 12-13/3/12 | P. Gronbech gave GridPP talk at Oxford
ISGC, "Harnessing the Power of Threat Intelligence in Grids and Clouds: WLCG SOC Working Group" | 2018-03-20 | David Crooks
WLCG/HSF Joint Workshop, Security Parallel Session / Security Session Summary in Closing Plenary | 28/3/2018 / 29/3/2018 | David Crooks (co-convener)
WLCG/HSF Joint Workshop, Metrics & Monitoring | 2018-03-28 | Gareth Roy (presented by Markus Schulz)
ATLAS ADC Technical Coordination Board, "XCache status at Edinburgh" | 2018-02-05 | Teng Li
"Code Review and CI with Gitlab", Software carpentry workshop, Edinburgh | 2018-02-20 | Andrew Washbrook
"Software quality update", ATLAS software coordination meeting | 2018-03-22 | Andrew Washbrook
"Software Build and Testing Platform As A Service", SSI Collaborations Workshop, Cardiff | 2018-03-26 | Andrew Washbrook
| 18-19/4/13 | P. Gronbech gave GridPP talk at Oxford | Q2?
International Symposium on Grids and Clouds, Taipei | 17-22/3/13 | UK e-Infrastructure talk by Jeremy Coles
Alessandra Forti presentations at: Atlas S&C week, WLCG Ops Planning, | 23/10/2013, 07/11/2013
Alessandra Forti presentations: "Multicore", 13/01/2014, Hepsysman, Birmingham "WLCG Multicore Task Force", 21/01/2014, Multicore Task Force meeting "Multicore Task Force", 11/02/2014, WLCG Ops Coordination F2F, CERN "Moving to BigPanDAmon", 27/02/2014, Atlas S&C week, CERN "ADC Monitoring", 28/02/2014, Atlas S&C week, CERN "Multicore", 25/03/2014, GridPP32 Pilotcry | 13/01/0214, 20/01/2014, 11/02/2014, 27/02/2014, 28/02/2014, 25/03/2014
Andrew McNab presentations: | 24/02/2014, 25/03/2014
“LHCb T2-D Update”, 24 Feb 2014, LHCb National Computing Board, CERN.
"Running real jobs in virtual machines”, 25 Mar 2014, GridPP32, Pitlochry.
Monitoring presentation at UK HEPSYSMAN event | 2014-06-03 | Given by Dave Crooks
Invited talk on HPC at Atlas Software Week | 2014-06-04 | Given by Andrew Washbrook
Invited Talk at WLCG Monitoring Consolidation Meeting | 2014-07-04 | Given by Dave Crooks
OpenMP Tutorial for Atlas Computing | 2014-09-12 | Given by Andrew Washbrook
UKI-LT2-Brunel: GPU 2014 workshop | August 2014 reg | https://agenda.infn.it/conferenceDisplay.py?confId=7534
Invited Talk at Atlas ADC meeting (cgroups) | 2014-11-24 | Gang Qin
Invited Talk at Atlas Jamboree (cgroups) | 2014-12-04 | Gang Qin
HPC(Archer) update at the ATLAS HPC meeting | 2014-12-10 | Andrew Washbrook
DPM Workshop - Naples | 2014-10-09 | Wahid Bhimji
ATLAS S&C week (ADC shifter Feedback) | 2014-12-04 | Wahid Bhimji
ISGC, "WLCG Security Operations Centres Working Group" | 2017-03-07 | David Crooks
Ran ATLAS Code Review Shift Tutorial, CERN | 2017-02-02 | Andrew Washbrook
ATLAS Software Quality presentation, CERN | 2017-03-15 | Andrew Washbrook
CERN IT Technical Forum, Manchester Workshop report, Security & Trust (slide preparation/given by proxy) | 2017-07-07 | David Crooks
GDB, Manchester Workshop report, Security & Trust (slide preparation/given by proxy) | 2017-07-12 | David Crooks
"Continuous software quality analysis for the ATLAS experiment", 18th International Workshop on Advanced Computing and Analysis Techniques in Physics Research (ACAT 2017), Seattle, USA | 2017-08-22 | Andrew Washbrook
Continuous software quality analysis for the ATLAS experiment, Workshop on Sustainable Software for Science: Practice and Experiences (WSSSPE5.1) Manchester, UK | 2017-09-06 | Andrew Washbrook
A container model for resource provision at a WLCG Tier-2 (ACAT 2017), Seattle, USA | 21-25/8/2017 | Gareth Roy
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Alessandra is one of the GridPP representatives in the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; SL6 TF leader ends this quarter; Multicore TF leader starts this quarter. | 01/10/2013-31/12/2013; 01/10/2013-31/10/2013; 01/12/2013-31/12/2013 | Joint-Chair WLCG Operations Coordination Team
Pete Gronbech | Current | Chairman HEPSYSMAN
Jeremy Coles | Current | Member - EGI Operations Management Board
Jeremy Coles | Current | UK member - WLCG Grid Deployment Board
WLCG Monitoring Consolidation working Group | Present | Attended by David Crooks
Chair of WLCG Storage Evolution Group W. Bhimji | Present | UK Data Storage
Member of Scientific Programme Comittee and Convenor of the "Data Stores, Data Bases, and Storage Systems" track for CHEP 2013 | Present | CHEP 2013
UK Members of DPM Collaboration | Present | UK Data Storage (W. Bhimji & S. Skipsey)
Active members of Multi-core taskforce (representing Scotgrid distributed Tier 2) | Present | Attended by S. Skipsey
WLCG Traceability & Isolation WG | Present | David Crooks
SOC Working Group | Present | co-lead by David Crooks
UK Members of DPM Collaboration | Present | UK Data Storage (S. Skipsey)
HTTP Deployment Working Group | Present | S. Skipsey
Member of Tier-2 Evolution Working Group | Present | S.Skipsey
ATLAS Software Quality Coordinator | Present | Andrew Washbrook
Andrew McNab is the Deputy LHCb Computing Coordinator. He is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group and leading the GridPP Tier-2 Evolution project. He is leader of the WLCG "Machine Features” task force, and a member of the "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces, and the Grid Deployment Board steering group.
Jeremy Coles | Current | UK NGI Management Board
Other outputs and Knowledge | Date | Notes
Pete Gronbech | 2013-12-06 | GridPP talk at the IATUL Workshop
UI/WN Tarball
Involved with CentOS 7 adoption for atlas, MW Readiness WG
CentOS7 progress at the ATLAS ADC weekly 14/09/2016 Update on ATLAS benchmark | 2016-08-16 | A Forti.
TO be merged
Publications | Date | Notes
Glasgow EGI (3) | 08/04//2013 | Papers at EGI Community Forum
CHEP |  | Papers to student Societies
Glasgow CHEP (4) | 2013-03-30 | Paper Submission
UKI-LT2-Brunel: GPU 2014 workshop | 2014-12-31 | https://agenda.infn.it/conferenceDisplay.py?confId=7534
ECDF CHEP (2) | 2013-03-30 | Paper Submission
Collaborations | Date | Notes
EMC Data transfer programme | Ongoing | Support for commercial academic FP7 Grant
TechCube installation of a new cluster |  | ScotGrid
ECDF Big data Workshop ECDF | Ongoing
Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs. | Q416 - ongoing | Northgrid
Working with LSST and SKA users to adapt their workflows to use grid resources | Q416 - ongoing | Northgrid
Further Funding (eg external grants) | Date | Notes
Manchester - Extra data server purchased by the University | 2013-06-01
Destination of ex staff and recruitment issues | Date | Notes
Mike Johnson | 2013-12-31 | Moved to William Hill as a systems Admin. Safe bet. :-)
Dissemmination events | Date | Notes
Glasgow Public Outreach (2) | 09/04//2012 | Papers to student Societies
MEW24 | 2013-11-27 | M Mitchell presented on behalf of LAN3 regarding network equipment
Manchester (Alessandra Forti): presentations at: WLCG Monitoring Consolidation; ADC weekly; GDB; ADC weekly; WLCG Monitoring Consolidation | 05/07/2013, 16/07/2013, 11/09/2012, 17/09/2013, 26/09/2013
Andrew: presentations at: pre-GDB, CERN; LHCb National Computing Board meeting, Krakow; EGI Technical Forum, Madrid; GridPP31, Imperia | 09/07/2013, 11/09/2013, 16-20/09/2013, 24/09/2013
Cloud and virtualisation workshop | 2013-07-01
11/10/216 Memory handling in the ATLAS submission system, CHEP2016 11/10/2016 Analysis of empty ATLAS pilot jobs and subsequent resource usage on grid sites, poster, CHEP2016 25/11/2016 CentOS7 testing update, ADC weekly | Q416 | NorthGrid
HEPSYSMAN, "WLCG Federated Access" | 2016-11-07 | David Crooks
GDB, "SOC Working Group Report" | 2016-12-14 | David Crooks
HEPiX, "ZFS on Linux" | 2016-10-19 | Marcus Ebert
CHEP, "Evaluation of ZFS as an efficient WLCG storage backend" | 2016-10-10 | Marcus Ebert
Presentation on Static Code Analysis in ATLAS for Software Quality Analysis workshop, CERN | 2016-11-23 | Andrew Washbrook
ATLAS Coordination of 2nd Openlab/Intel Workshop on Code Optimisation (summary talk given to ATLAS software community on 15/12/2016) | 24-25/11/2016 | Andrew Washbrook
UK sites representative for the ARC Brainstorming Camp (summary talk given in UK Ops meeting on 13/12/2016) | 28/11/2016 - 02/12/2016 | Andrew Washbrook
HEPSYSMAN (WLCG Workshop security session) | 2017-06-15 | David Crooks
HEPSYSMAN (Glasgow Site Report) | 2017-06-15 | David Crooks
WLCG Workshop (Security & Trust) | 2017-06-19 | David Crooks (convener)
HEPSYSMAN talks on setting up HV at Edinburgh and site summary | 13,15/6/2017 | Rob Currie
Manchester/NorthGrid: EGI community forum (three posters: VOMS, perfSonar monitoring and LHCb usage of the Tier2). Presentations at the GDB: WLCG Ops Coord summary report, Atlas S&C: SL6 status report, French perfsonar day: WLCG requirements | 08-12/04/2013, 10/6/2013, 11/6/2013, 04/04/2013
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
N/A
Roles held on committees and boards | Date | Notes
HEPIX IPv6 M.Mitchell | Present | Global Network Group
Monitoring consolidation group - David Crooks | Present
LHCONE M.Mitchell | until Q1 2014 | Global Network Group
Member of SQUID Monitoring TF | Present | David Crooks
UK Members of DPM Collaboration | Present | UK Data Storage (W. Bhimji & S. Skipsey)
Active members of Multi-core taskforce (representing Scotgrid distributed Tier 2) | Present | Attended by S. Skipsey
Chair of WLCG Stroage Evolution Group W. Bhimji | Present | UK Data Storage
Alessandra Forti | Current | GridPP representative in the WLCG Ops Coordination, SL6 TF leader, Atlas monitoring coordinator and member of the atlas distributed computing coordination
Alessandra is one of the GridPP representatives in the WLCG Ops Coordination, SL6 TF leader, Atlas monitoring coordinator and member of the atlas distributed computing coordination | 01/07/2013-31/03/2014
Andrew is deputy leader of the GridPP technical group, the LHCb Tier-2 co-ordinator, a Grid Expert On Call member of the LHCb distributed computing team, and a member of the WLCG Machine features task force | 01/07/2013-31/03/2014
Pete Gronbech | Current | Chairman HEPSYSMAN
Jeremy Coles | Current | Member - EGI Operations Management Board
Jeremy Coles | Current | UK member - WLCG Grid Deployment Board
Jeremy Coles | Current | UK NGI Management Board
Member of Scientific Programme Comittee and Convenor of the "Data Stores, Data Bases, and Storage Systems" track for CHEP 2013 | Present | CHEP 2013
Other outputs and Knowledge | Date | Notes
Glasgow Impact | 2013-05-01 | Press Release Completed
Good engagement with High Performance Networking Special Interest Group meeting | 2013-07-01
TO be merged
Collaborations | Date | Notes
Manchester: Worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs. | Q415
Dissemmination events | Date | Notes
Alessandra Forti chaired session on opportunistic resources at the ATLAS TIM https://indico.cern.ch/event/437170/timetable/#all.detaile | 2015-12-02
Andrew McNab presentations: “Batch and Cloud overview”, UK-T0 kickoff meeting, 20 Oct 2015. “LHCb infosystem plans” and “Publishing GLUE2 in JSON”, WLCG Information System Task Force meeting, 12 Nov 2015. | 20/10/2015 and 12/11/15
TO be merged
Publications | Date | Notes
Collaborations | Date | Notes
Manchester worked with Datacentred Ltd in MediaCity, Salford, to use the Vcycle system developed by Manchester to manage VMs for GridPP and run GridPP DIRAC jobs.
Working with LSST users to adapt their workflow to use grid resources
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Gang Qin - Sussex University | 2016-04-01 | Gang has moved to Sussex as the Grid admin there.
Dissemmination events | Date | Notes
Alessandra Forti: - Organised Ganga Tutorial and HEPsysman in Manchester 14-15/1/2016 - HEPsysman, WLCG workshop: Info sys, accounting, benchmarking 15/1/2016 - ATLAS Jamboree, chair of the Infrastructure and sites recommendation 27-29/1/2016 - ATLAS Jamboree, "On memory and batch systems", 27/1/2016 - WLCG workshop, chair of the Info sys, accounting, benchmarking session, 1/2/2016 - WLCG workshop, session introduction, 1/2/2016 - WLCG workshop, session Summary, 3/2/2016 - ATLAS S&C week, "WLCG workshop and jamboree summaries", 1/3/2016 | 14-15/01/2016 27-29/01/2016 01/02/2016 03/02/2016 01/03/2016
GDB | 2016-03-07 | David Crooks - Security Operations Centre Update (with Liviu Valsan)
Andrew McNab presentations: “Cloud use by LHCb”, CC-IN2P3 Annual Meeting, Lyon, 9 Feb 2016. “Vacuum platform”, EGI Operations Management Board, 25 Feb 2016. “LHCb Operations Report”, LHCb National Computing Board, 7 Mar 2016. | 09/02/2016 25/02/2016 07/03/2016
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Alessandra is one of the GridPP representatives and one of the co-chairs of the WLCG Ops Coordination, Atlas monitoring coordinator and member of the atlas distributed computing coordination; Multicore TF co-leader; WLCG workshop 2016 planning committee.
Andrew is the Deputy LHCb Computing Coordinator and LHCb Distributed Computing and Operations Coordinator. He is the LHCb UK Computing Coordinator and the LHCb UK representative on the LHCb-wide National Computing Board and GridPP Project Management board, deputy leader of the GridPP technical group and leading the GridPP Tier-2 Evolution project. He is leader of the WLCG "Machine Features” task force, and a member of the "Cloud Traceability”, “Cloud Resource Reporting”, and “Information Systems Evolution" task forces.
Other outputs and Knowledge | Date | Notes