## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Experiment Support |  |  | Close to target
Year | 2018 |  |  | Not OK
Reported by | Matt Doidge |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q117 | Q217 | Q317 | Q417 | Q118 | Q218 | Q318 | Q418 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417 | Comment Q118 | Comment Q218 | Comment Q318 | Comment Q418 | Comment Q119
3.4.6 | ATLAS reporting to T1 expt Liaison and resource meetings | Roger Jones | Pete Gronbech | ATLAS support check | [8 empty] | Meeting held 22.3.17 | No resources meeting held this quarter, but Liaison held as normal. | T1 Resource meeting held on 30.08.17 | T1 Resource meeting held on 29.11.17 | T1 Resource meeting held on 28.3.18 | T1 Resource meeting held on 25.7.18
3.4.7 | CMS reporting to T1 expt Liaison and resource meetings | Dave Colling | Pete Gronbech | CMS support check | [8 empty] | Meeting held 22.3.17 | No resources meeting held this quarter, but Liaison held as normal. | T1 Resource meeting held on 30.08.17 | T1 Resource meeting held on 29.11.17 | T1 Resource meeting held on 28.3.18 | T1 Resource meeting held on 25.7.18
3.4.8 | LHCb reporting to T1 expt Liaison and resource meetings | Resource Review minutes | Pete Gronbech | 3 out of 4 meetings/ year | [8 empty] | Meeting held 22.3.17 | No resources meeting held this quarter, but Liaison held as normal. | T1 Resource meeting held on 30.08.17 | T1 Resource meeting held on 29.11.17 | T1 Resource meeting held on 28.3.18 | T1 Resource meeting held on 25.7.18
3.4.9 | Unit testing of code within area of responsibility | Report from Ulrik | Ulrik Egede | Coverage of over 75% of code | [8 empty] | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded
3.4.10 | Provide new releases of Ganga | Report from Ulrik | Mark Smith | A new minor release at least every 6 weeks | [8 empty] | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded
3.4.11 | Support provided for new user communities | Report from Ulrik | Rob Currie | Have a turn-around time of less than 1 month for a prototype | [8 empty] | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded | No longer Funded
3.4.12 | Number of new user groups using the T1/UK Grid | T1 and T2 accounting. Email requests, etc | Pete Gronbech | >1 per year | [9 empty] | osg vo started running jobs |  | no new VOs this quarter | no new VOs this quarter |  | no new VOs this quarter | no new VOs this quarter | no new VOs this quarter
3.4.13 | Summary of Work done by support posts | Dan Proropopescu quarterly report | Pete Gronbech | [9 empty] | Not funded this quarter. | ATLAS: - development of a prototype ATLAS grid job memory monitoring toolset, that would allow job profiling and optimisation of the slot allocations (see http://memmon.ppe.gla.ac.uk) NA62* - implemented concurrent production round capabilities - improved builtin file catalogue - added new features to the UI - infrastructure debugging work in collaboration with IC Dirac admins - optimised file transfers and accounting - set up and run production and reconstruction with na62fw v0.10.0 (see https://na62.gla.ac.uk/index.php?task=stats&view=prod) Note: NA62 grid production uses custom software, database and servers in Glasgow, which work in conjunction with Dirac and previously gLite. This software is developed and maintained by me and the servers and DB are managed in collaboration with Glasgow PPE IT and GridPP support teams. | ATLAS: - work to upgrade and extende functionality of the ATLAS grid job memory monitoring toolset to include new job containerisation tools installed on the Glasgow cluster NA62 - production and reconstruction with na62fw v0.10.0 continued - implemented more efficient job accounting - set up and run production and reconstruction with na62fw v0.11.0 - optimised database backend - optimised and streamlined UI, and added new features - added CERN EOS endpoint - infrastructure debugging work in collaboration with IC Dirac admins - implemented site metrics monitoring - implemented smarter job submission algorithms - added new sites/resources (all the above accounted for a tenfold increase of throughput, see https://na62.gla.ac.uk/index.php?task=stats&view=prod) - added detailed online stats - started implementation of grid-enabled data analysis | ATLAS: - update/patch ATLAS grid job memory monitoring toolset to work with updated Glasgow cluster - development of new graphics interface for above toolset NA62: - production and reconstruction with na62fw v0.11.0 continued - added new CERN CE to NA62 grid resources - added VAC resources from several UK sites - benchmarked builtin Dirac output management (DMS) - continued work on implementation of grid-enabled data analysis - implemented new site performance metrics - implemented automatic recovery from CE and SE failures - configured new features in the UI - preparations for and setup of na62fw v0.11.1 prod/reco round - ran production and reconstruction with na62fw v0.11.1 (all through the holidays) https://na62.gla.ac.uk/index.php?task=stats&view=prod Note: NA62 grid production uses custom software, database and servers in Glasgow, which work in conjunction with Dirac and previously gLite. This software is developed and maintained by me and the servers and DB are managed in collaboration with Glasgow PPE IT and GridPP support teams. | ATLAS: - grid job memory monitoring toolset development, including improved graphics via D3 JS NA62: - production and reconstruction with na62fw v0.11.1 continued - implemented job callbacks for increased responsivity - setup of na62fw v0.11.2 prod/reco round (this includes liaising with developers to prepare grid-ready releases) - configured new features for v0.11.2, including in the web UI - production and reconstruction with na62fw v0.11.2 - improvements to NA62 own scheduling efficiency (these algorithms override some of Dirac’s) - web UI security enhancements - database cleanup https://na62.gla.ac.uk/index.php?task=stats&view=prod Note: NA62 grid production uses custom software, database and servers in Glasgow, which work in conjunction with Dirac. This software is developed and maintained by me and the servers and DB are managed in collaboration with Glasgow PPE IT and GridPP support teams. | ATLAS: - grid job memory monitoring toolset development: data collection scripting NA62: - production and reconstruction with na62fw v0.11.2 continued - continued implementation of data analysis on grid beta features - setup of na62fw v0.11.3 prod/reco round, including fast-sim, new web UI features, etc. - improved output transfer algorithms - implemented more s/w safeguards to cope with site/Dirac/EOS outages - database cleanup (archived old productions up to v0.10.0) - production and reconstruction with na62fw v0.11.3 (ongoing) https://na62.gla.ac.uk/index.php?task=stats&view=prod Note: NA62 grid production uses custom software, database and servers in Glasgow, which work in conjunction with Dirac. This software and services are developed and maintained 24/7 by me and the servers and DB are managed in collaboration with Glasgow PPE IT and GridPP support teams. | ATLAS: - grid job memory monitoring tools now part of the standard ATLAS setup -> task finished NA62: - production and reconstruction with v0.11.3 (continued) - improved output transfer algorithms and file accounting - setup of na62fw v1.0.0 prod/reco round, including new MC and web UI features, etc. - production and reconstruction with v1.0.0 - database optimisations, scripts cleanup, debug CC7 issues - new metrics and stats added to web UI https://na62.gla.ac.uk/ | NA62: - setup of na62fw v1.0.1 prod/reco round and started production - finalised round with v1.0.0 - archived rounds with versions below v21 (v1.0.0) - setup of na62fw v1.0.2 prod/reco round, including new MC and web UI features, etc. - finished round with v1.0.1 - web UI improvements - moved robots (cron jobs) to new server for increased redundancy - production and reconstruction with v1.0.2, see https://na62.gla.ac.uk/index.php?task=stats&view=prod - database and algorithms optimisations, debug CC7 and gfal2 and xrootd issues - major data recovery carried out, with 663344 root files of a total of 29TB copied from RAL tape to CERN EOS, see https://na62.gla.ac.uk/index.php?task=recovery | NA62: - production and reconstruction with v1.0.2 (continued) - EOS storage cleanup - analysis tests with v1.0.3 - setup of na62fw v1.0.4 and updates to the UI - code updates, UX optimisations, new stats - debugging na62fw on CC7 grid environment - production and reconstruction with v1.0.4, see https://na62.gla.ac.uk/index.php?task=stats&view=prod
3.4.14 | Summary of Work done by support posts | Janusz Martyniak quarterly report | Pete Gronbech | [9 empty] | MICE: - Completed installation of the CDB C-API for the cooling channel, absorber and state machine Web Services - Minor correction to the CDB Viewer - C++ CDB API released and installed in MAUS analysis software - Work on CDB geometry API update started - CHEP 2016 paper preparation and submission NA62: - maintenance of the data moving system (File Transfer Controller) | MICE: - Modification and bug fixes for the CDB state machine Web Services for the 2017 autumn run - Installation of a new version of MAUS software on the `Grid - Adding a new service to the CDB to allow easier run selection for data analysis - Work on CDB geometry API update completed Solid - design and development of a data mover. The primary aim of the mover is to transfer experiment raw data onto permanent CASTOR storage at RAL. The tool uses Dirac Python API to select any new data available and FTS Python API to perform CASTOR upload. | MICE: - Maintenance of raw and data moving software during Nov 2017 run - Small fixes and updates to the Configuration Database. - Adding a new service to the CDB to allow easier run selection for data analysis - ongoing - MICE shifts Solid - design and development of a data mover system - ongoing. - work on data-mover Web based monitor started - reserving and testing Castor space for the experiment. In progress. User support - help on Dirac given to Sally Radwan, a PhD student from Royal Holloway. | MICE: - Maintenance of raw and reconstruction data moving software during Dec 2017 run - Configuration Database maintenance. SoLid: - development of a data mover system - beta ready for testing as soon as the link quality between BEgrid-ULB-VUB (source SE) and the UK improves. - work on data-mover Web based monitor continued, Data Transfer tool: Work on an open source Globus-online equivalent data transfers system started. My task is design and development of a user management RESTful Web Service and a command line interface to interact with it. The tool is written in Python. User support - help on Dirac given to local SoLid users. | MICE: - Maintenance reconstruction data moving software for reprocessing, modified the data mover tool to use RAL PPD farm. - Configuration Database maintenance. - Software installation on CVMFS SoLid: - The data mover development finished. The software is installed on a dedicated machine and works well. It uses Dirac Python API to collect new data files and FTS based program to upload files to Castor at RAL. Data Transfer tool: Work on the DiRAC data transfer tool continued in this quarter. We Integrated the demo system which included the user database and the CLI written by me. Work will continue in the next quarter. User support - help on Dirac given to local SoLid users. | MICE (my activity here is now rather limited since the experiment is finished): - Maintenance of the reconstruction data mover tool, including Grid certificate installation on a hardware dongle. - Configuration Database maintenance. - MAUS software installation on CVMFS. - Grid meetings every 2 weeks. SoLid: - Maintenance of the data mover. The software is installed on a dedicated machine and works well. A talk give at CHEP 2018 in Sofia. Data Transfer tool: Work on the DiRAC data transfer tool (PDM) continued in this quarter and work on it takes most of my time. We are now working on the PDM stage 2. I work on the User Command-line Interface, user database and GFAL2 based transfer back-end. Work will continue in the next quarter. User support - help on Dirac given to local SoLid users. | MICE (rather limited since the experiment does not take data anymore): - maintenance of the reconstruction data mover tool - Configuration Database maintenance - Grid meetings (occasional) SoLid: - Maintenance of the data mover. The software is installed on a dedicated machine and works well and rarely requires a manual intervention. Data Transfer tool: Work on the DiRAC data transfer tool (PDM) is my main activity. In the Stage 2 development phase we integrated GFAL2 back-end with the framework and the GUI. Some enhancements to the Command Line Interface were also added. Various bugs discovered during in-house testing have been fixed. - T2K Preparation to port the GPU oriented experiment software to the Grid. - Dirac support for local SoLid users. | MICE (rather limited since the experiment does not take data anymore): - Re-designing the reconstruction data mover tool after the LFC failure at RAL, plans are to move to Dirac - Configuration Database maintenance - Grid meetings (occasional) SoLid: - Maintenance of the data mover. The software is installed on a dedicated machine and works well and rarely requires a manual intervention. Work on Dirac: converting current Dirac metadata database to handle data from multiple Virtual Organisations. This is my primary activity which will continue in next quarters. | MICE: - work on moving existing MICE MC data and reconstruction data to CASTOR at RAL and registering them in Dirac - ongoing - reco datamover maintenance, occasional grid meetings. SoLid: Maintenance of the data mover. Dirac: Work on converting current Dirac metadata database to handle data from multiple Virtual Organisations. Work on Dirac Resource Status and Management systems for multiple Vos

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Experiment Support |  |  | Overdue
Quarter | 2018 |  |  | Not yet due
Reported by | Matt Doidge |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
| Modernise test suite | Rob Currie | 2015-11-01 | 2016-03-01 | The continuous testing is running on all pull requests | There is still a few legacy tests running but they are by now marginal compared to the new test system.
| Migration to Cmake for LHCb | Rob Currie | 2016-01-01 |  |  | Has been delayed by increasing support for other VOs
| Updated authentication system | Matt Williams | 2016-04-01 |  |  | Has been delayed by taking over the milestone for Jenkins and the milestone on updating the lock system.
| Implement new lock system for multi-thereaded operation |  | 2016-04-01 | 2016-03-01 | Much fewer user support issues related to the job monitoring getting into deadlock situations. | Very much a collective responsibility by everybody involved.
| Improve scalability of submissions to Dirac backend | Rob Currie | 2016-06-01 | 2016-06-01 | The submission time of subjobs has gone from about 10s per job to 3 s per job.
| Provide support for IgangaFile objects everywhere in the sytem | Rob Currie | 2016-08-01 |  | This is complete with the 6.2 series of Ganga.
| Prototype of support for production system of LZ | Alex Richards | 2016-09-01 |  | The prototype that is talking to the LZ production database has been completed.
| Prototype for LSST analysis | Rob Currie | 2016-06-01 | 2016-05-01 | The use of this was reported as a success in a report submitted to the UKT0 working group.

## Manpower Q117
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu
Imperial | User Support | Janus Martyniak | 0.5 | 0.5 | 0.5
Liverpool | Ganga | Rob Fay
Total |  |  | 0.5 | 0.5 | 0.5 | 0 | 0 | 0

## Manpower Q217
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Manpower Q317
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Manpower Q417
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Manpower Q118
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Manpower Q218
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2016
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Manpower Q318
GridPP Quarterly Report
Area | Experiment Support
Quarter | Q3 18
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Manpower Q418
GridPP Quarterly Report
Area | Experiment Support
Quarter | Q4 18
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1 |  |  |  | These figures are blindly copied and pasted.
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Manpower Q119
GridPP Quarterly Report
Area | Experiment Support
Quarter | Q1 19
Reported by | Matt Doidge
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
Imperial | Ganga | Alex Richards
Imperial | Ganga | Ulrik Egede
Imperial | Ganga | Rob Currie
Imperial | Ganga | Mark Smith
Glasgow | User Support | Dan Proropopescu | 0.5 | 0.5 | 0.5
Imperial | User Support | Janus Martyniak | 1 | 1 | 1 |  |  |  | These figures are blindly copied and pasted.
Liverpool | Ganga | Rob Fay
Total |  |  | 1.5 | 1.5 | 1.5 | 0 | 0 | 0

## Narrative Q117
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2017 Q1
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
There is no longer any funding for Ganga from GridPP so no longer any objectives/deliverables in that direction. |  |  |  | New user engaement Officer post may be able to contribute to supporting Ganga at a low level.

## Narrative Q217
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2017 Q2
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
There is no longer any funding for Ganga from GridPP so no longer any objectives/deliverables in that direction. |  |  |  | New user engaement Officer post may be able to contribute to supporting Ganga at a low level.

## Narrative Q317
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2017 Q3
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the ganga project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower or alternative tools. Increased support for users using DIRAC is now on line.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q417
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2017 Q4
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the ganga project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower or alternative tools. Increased support for users using DIRAC is now on line.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q118
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2018 Q1
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the ganga project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower or alternative tools. Increased support for users using DIRAC is now on line.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q218
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2018 Q1
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the ganga project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower or alternative tools. Increased support for users using DIRAC is now on line.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q318
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2018 Q3
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
The loss of the two key developers for the ganga project means that new developments are essentially dormant. New projects will also not be able to receive any substantial support for integration. |  | Find new manpower or alternative tools. Increased support for users using DIRAC is now on line.
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q418
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2018 Q4
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q119
GridPP Quarterly Report
Area | Experiment Support
Quarter | 2019 Q1
Reported by | Matt Doidge
Progress over last Quarter
Work area | Successes |  | Problems/Issues
GangaAtlas |  |  | Nothing to report. Effort no longer funded.
GangaLHCb |  |  | Nothing to report. Effort no longer funded.
GangaCore |  |  | Nothing to report. Effort no longer funded.
Ganga other |  |  | Nothing to report. Effort no longer funded.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Alex Richards | 2013-04-01 | Went to an STFC core funded computing position at Imperial
Matt Williams | 2016-09-30 | went to Bristol, I *think* on an Research Engineer UK grant with some Computational Biology group
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes