## Metrics
GridPP Quarterly Report |  |  |  | OK
Area | Security |  |  | Close to target
Year | 2018 |  |  | Not OK
Reported by | Dave Kelsey |  |  | Not yet able to be measured
Suspended
Metric no. | Description | Source | Owner | Target | Q117 | Q217 | Q317 | Q417 | Q118 | Q218 | Q318 | Q418 | Q119 | Q219 | Comment Q117 | Comment Q217 | Comment Q317 | Comment Q417 | Comment Q118 | Comment Q218 | Comment Q318 | Comment Q418 | Comment Q119 | Comment Q219
3.3.1 | Number of Tier 2 security incidents in the last quarter |  | Dave Kelsey | Green <=1, Amber 2 or 3 and Red >=4 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 incident (10 March) at Glasgow involving an old non-GRID NA62 system. No impact on any GridPP systems [EGI-20170310] | None | None | 1 incident (1 Nov) notified by Janet CSIRT involving the DiRAC cluster at Durham. No impact on any GridPP systems [EGI-20171101] | None | None | None | None | 1 incident (4th Feb 2019) notified by Imperial [EGI-20190204-01] Comprised Server using known vulnerability. No impact on GridPP systems. | 1 incident (17 May 2019) notified by RALPP Tier 2 [EGI-20190517-01]. Non Grid Jenkins Server compromised. No impact on GridPP systems.
3.3.2 | Number of sites responding poorly to a security incident in last quarter |  | Dave Kelsey | Green 0, Amber 1 Red >=2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Very well handled |  |  | Very well handled |  |  |  |  | Very quickly fixed and handled. Final report on 11th Feb 2019. | Quickly fixed and handled. Final report on 1st July
Note on B10: gronbech: Green 0, Amber 1, Red >=2

## Milestones
GridPP Quarterly Report |  |  |  | Complete
Area | Security |  |  | Overdue
Year | 2018 |  |  | Not yet due
Reported by | Dave Kelsey |  |  | Suspended
Milestone no. | Description | Owner | Due date | Date complete | Evidence | Comment
3.3.3 | Security Service Challenge | Ian Neilson | 2017-12-31 | 2018-08-31 | https://indico.cern.ch/event/736483/contributions/3094164/attachments/1706811/2750365/GridPP41_Security_Update.pdf | Ian Neilson's departure put plans for a fuller security challenge on hold. A full Security Communication Challenge was performed by EGI CSIRT (and DC) in early August. UK sites did well and work earlier on correcting communication failures paid off. DC presented the results at GridPP41 in Ambleside (28-31 Aug)
3.3.4 | UK HEP Sysman Security Training/Workshop | Ian Neilson | 2018-12-31 | 2017-06-13 | https://indico.cern.ch/event/592622/ | Milestone 3.3.3 has been delayed, but in the meantime we achieved milestone 3.3.4 early. Ian Neilson organised a one-day security workshop for HEP SYSMAN at RAL concentrating on the topic of IPv6 security
3.3.5 | Security plans for the future beyond end of GridPP5 | Dave Kelsey | 2019-12-31

## Manpower Q117
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.35 | 0.4 | 0.26
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.78 | 0.51 | 0.84
RAL | Vulnerabilities | Linda Cornwall | 0.2 | 0.2 | 0.2 | 0.13 | 0.13 | 0.4
RAL | Policy | Dave Kelsey | 0.18 | 0.16 | 0.2 | 0.39 | 0.21 | 0.23
Total |  |  | 1.51 | 1.27 | 1.5 | 0.52 | 0.34 | 0.63

## Manpower Q217
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.23 | 0.07 | 0.32
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.6 | 0.86 | 0.82
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.17 | 0.17 | 0.25 | 0.28 | 0.4
RAL | Policy | Dave Kelsey | 0.1 | 0.16 | 0.52 | 0.1 | 0.16 | 0.15
Total |  |  | 1.1 | 1.26 | 1.83 | 0.35 | 0.44 | 0.55

## Manpower Q317
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.28 | 0.21 | 0.47
RAL | Deployment | Dave Kelsey
RAL | Deployment | Ian Neilson | 0.78
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.17 | 0.17 | 0.5 | 0.3 | 0.42
RAL | Policy | Dave Kelsey | 0.18 | 0.27 | 0.19 | 0.17 | 0.09 | 0.17
Total |  |  | 1.41 | 0.65 | 0.83 | 0.67 | 0.39 | 0.59

## Manpower Q417
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.51 | 0.51 | 0.15
RAL | Deployment | Dave Kelsey | 0.15 | 0.15 | 0.05
RAL | Deployment | Ian Neilson
RAL | Vulnerabilities | Linda Cornwall | 0.17 | 0.17 | 0.17 | 0.43 | 0.44 | 0.29
RAL | Policy | Dave Kelsey | 0.15 | 0.19 | 0.09 | 0.26 | 0.25 | 0.09
Total |  |  | 0.98 | 1.02 | 0.46 | 0.69 | 0.69 | 0.38

## Manpower Q118
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Deployment | Linda Cornwall | 0.35 | 0.09 | 0.22
RAL | Deployment | Dave Kelsey | 0.1 | 0.1 | 0.1
RAL | Deployment | Ian Neilson
RAL | Vulnerabilities | Linda Cornwall | 0.3 | 0.3 | 0.3 | 0.17 | 0.2 | 0.25
RAL | Policy | Dave Kelsey | 0.18 | 0.2 | 0.47 | 0.4 | 0.35 | 0.25
Total |  |  | 0.93 | 0.69 | 1.09 | 0.57 | 0.55 | 0.5

## Manpower Q218
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Operations | Linda Cornwall | 0.12 | 0.43 | 0.29 | 0.45 | 0.4 | 0.48
RAL | Operations | David Crooks |  | 0.17 | 1.17
RAL | Operations | Dave Kelsey | 0 | 0 | 0.1 | 0.2 | 0.2 | 0.2
RAL | Trust & Identity | Dave Kelsey | 0.13 | 0.13 | 0.19 | 0.2 | 0.2 | 0.2
Total |  |  | 0.25 | 0.73 | 1.75 | 0.85 | 0.8 | 0.88
Note: David Crooks in June 2018 = 1.17 FTE. This means he took no leave. This averages out over the year.

## Manpower Q318
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Operations | Linda Cornwall | 0.39 | 0.32 | 0.4 | 0.45 | 0.35 | 0.4
RAL | Operations | David Crooks | 1.23 | 1.17 | 1
RAL | Operations | Dave Kelsey | 0.05 | 0.05 | 0.05 | 0.2 | 0.2 | 0.2
RAL | Trust & Identity | Dave Kelsey | 0.25 | 0.28 | 0.28 | 0.2 | 0.2 | 0.2
Total |  |  | 1.92 | 1.82 | 1.73 | 0.85 | 0.75 | 0.8
Note: David Crooks in August 2018 = 1.17 FTE. This means he took no leave. This averages out over the year.

## Manpower Q418
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Operations | Linda Cornwall | 0.5 | 0.36 | 0.19 | 0.43 | 0.46 | 0.4
RAL | Operations | David Crooks | 1.23 | 0.92 | 0.84
RAL | Operations | Dave Kelsey | 0.05 | 0.05 | 0.05 | 0.21 | 0.12 | 0.05
RAL | Trust & Identity | Dave Kelsey | 0.27 | 0.14 | 0.12 | 0.21 | 0.13 | 0.06
Total |  |  | 2.05 | 1.47 | 1.2 | 0.85 | 0.71 | 0.51
Note: David Crooks in October 2018 = 1.23 FTE. This means he took no leave. This averages out over the year.

## Manpower Q119
GridPP Quarterly Report
Area | Security
Year | 2019
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Operations | Linda Cornwall | 0.41 | 0.37 | 0.4 | 0.48 | 0.44 | 0.48
RAL | Operations | David Crooks | 1.12 | 1.12 | 1.17
RAL | Operations | Dave Kelsey | 0.05 | 0.05 | 0.05 | 0.12 | 0.2 | 0.22
RAL | Trust & Identity | Dave Kelsey | 0.31 | 0.24 | 0.24 | 0.13 | 0.21 | 0.22
Total |  |  | 1.89 | 1.78 | 1.86 | 0.73 | 0.85 | 0.92
Note: David Crooks' effort is greater than 1.0. This means he took limited or no leave. This should average out over the year.

## Manpower Q219
GridPP Quarterly Report
Area | Security
Year | 2019
Reported by | Dave Kelsey
Effort (FTE)
|  |  | GridPP Funded |  |  | Unfunded
Site | Work area | Name | Month 1 | Month 2 | Month 3 | Month 1 | Month 2 | Month 3
RAL | Operations | Linda Cornwall | 0.4 | 0.36 | 0.41 | 0.33 | 0.42 | 0.46
RAL | Operations | David Crooks | 1.06 | 1.17 | 1.12
RAL | Operations | Dave Kelsey | 0.05 | 0.05 | 0.05 | 0.12 | 0.11 | 0.11
RAL | Trust & Identity | Dave Kelsey | 0.22 | 0.46 | 0.45 | 0.13 | 0.12 | 0.12
Total |  |  | 1.73 | 2.04 | 2.03 | 0.58 | 0.65 | 0.69
Note: David Crooks' effort is greater than 1.0. This means he took limited or no leave. This should average out over the year.
We are booking too much effort right now - we will correct as the financial year goes on

## Narrative Q117
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. Another security communication challenge was successfully carried out for the UKNGI and problems with two sites were identified were fixed. Played active role in WLCG/EGI operational security. We attended the CSIRT F2F meeting in Prague (Jan 2017). Neilson took his share of weekly duties in EGI IRTF. Several security incidents were handled (not including UK). Patching to fix critical vulnerabilities was coordinated - there was one major campaign (VOMS Admin). |  | Please note that the security effort booked to GridPP5 was too large in May to August. The excess was funded by EGI.eu but while the income was agreed, the project codes in STFC SCD for this were not setup until September, from when Cornwall and Kelsey are booking less to GridPP. The costs have indeed balanced out over the full financial year - 1.5 FTE effort used.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. Eight advisories were issued on the public wiki. Work on security risk assessment with continued active participation in SIG-ISM and the WISE RAW group.
Policy | Work continued on revising EGI/WLCG security policies in collaboration with EGI-Engage. Three new policies formally adopted during the quarter (top-level policy, Data Protection and Acceptable Authentication). Prepared for and delivered security workshop at the ISGC2017 conference in Taipei (March). Completed and submitted the CHEP2016 paper on IPv6 Security. Attended EUGridPMA meeting in Florence (Jan). Lots of work on the WISE SCIv2-WG including a full-day workshop at the Nikhef WISE meeting in Amsterdam (March). New EGI continuation E_INFRA12 proposal was prepared and submitted (now called EOSC-Hub).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q217
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. Played active role in WLCG/EGI operational security. We attended the CSIRT F2F meeting in Lisbon (May 2017). Neilson took his share of weekly duties in EGI IRTF. Several security incidents were handled (not including UK). Patching to fix critical vulnerabilities was coordinated. We attended and presented at the EGI Conference in Catania (May 2017). Organised an IPv6 Security Workshop at RAL as part of UK HEP SYSMAN (June 2017). Continue work on new EGI CSIRT web.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. Eight advisories were issued on the public wiki (4 of which were HIGH). Published WISE security risk assessment template. Leading new SIG-ISM working group 1 on Inventory for Security Officers. Working on updates to SVG strategy and procedures. Continue work on EGI security risk assessment.
Policy | Work continued on revising EGI/WLCG security policies in collaboration with EGI-Engage and AARC2. Two draft Community/VO security policies worked on. Chaired EGI SPG meeting in Karlsruhe (June). Attended EUGridPMA meeting in Ljubljana (May). Finalised and published WISE SCI version 2. SCI version 2 was endorsed on 1st June by many Infrastructures in a ceremony at TNC17. Attended TAGPMA meeting in Washington DC as part of Internet2 Global Summit (April).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q317
GridPP Quarterly Report
Area | Security
Year | 2017
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. Ian Neilson went on leave of absence at end of July. UK NGI Security team takes over after he leaves - still run by STFC (David K and Linda C). Played active role in WLCG/EGI operational security. Neilson took his share of weekly duties in EGI IRTF (July only). Patching to fix critical vulnerabilities was coordinated. New EGI CSIRT web was released. EGI report on CSIRT was worked on and then published by EGI Communications. Attended UK IPv6 Security one-day workshop in London. |  | Ian Neilson (on leave of absence from start of August) has resigned from the post of GridPP security officer. STFC has to recruit to replace - in progress. In the meantime other STFC staff (Kelsey and Cornwall) will do some of the work, and spend some of the effort funds.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter.8 advisories were issued on the public wiki (1 of which was CRITICAL and 2 HIGH). Presented updated SVG strategy at the July EGI OMB meeting. Continue to lead GEANT SIG-ISM working group on Inventory for Security Officers; prepare for October meeting.
Policy | Work continued on revising EGI/WLCG security policies in collaboration with EGI-Engage and AARC2. Two draft Community/VO security policies were finalised and distributed for wider comment. Chaired EGI SPG meeting in Amsterdam (July). Organised and co-chaired a one-day WISE workshop as part of the NSF Cybersecurity summit in Arlington VA. Attended and co-organised EUGridPMA/IGTF All Hands meeting in Manchester (Sep). Organised and co-chaired two-day FIM4R meeting at McGill University, Montreal. Talk at WLCG GDB in Sep on Security policies.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q417
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. During absence of GridPP security officer, the UK NGI Security team continues to cover - still run by STFC (David K and Linda C). Played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. Represented WLCG and EGI at APGridPMA meeting in Japan (15 Oct) before HEPiX. DPK member of WLCG AuthZ working group including full pre-GDB meeting 7 Nov. Co-chaired EGI CSIRT F2F meeting Helsinki 15-17 Nov. Much of this planning for start of EOSC-hub in Jan 2018 |  | STFC still has to recruit to replace Ian Neilson - in progress. In the meantime other STFC staff (Kelsey and Cornwall) will do some of the work, and spend some of the effort funds.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter.7 advisories were issued on the public wiki (2 of which were CRITICAL and 1 HIGH). Updated SVG strategy now approved by EGI OMB. Continue to lead GEANT SIG-ISM working group on Inventory for Security Officers; attended 5-6 October meeting in Brussels.
Policy | Work continued on revised EGI/WLCG security policies in collaboration with AARC2. Two draft Community/VO security policies were finalised and sent for final approval. Chaired EGI SPG Vidyo meetings. Attended DI4R conference in Brussels (end of Nov). Lots of planning for EOSC-hub era in 2018.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q118
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Deployment | Lead UK NGI security team and its fortnightly meetings. During absence of GridPP security officer, the UK NGI Security team continues to cover - still run by STFC (David K and Linda C). Played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. Represented WLCG and EGI at EUGridPMA (Prague, 22-24 Jan 2018). DPK member of WLCG AuthZ working group. Start of EOSC-hub project. STFC is leading WP4 Task 4.4 Operational Security. Co-chaired F2F EOSC-hub/EGI CSIRT at CERN 29-31 Jan. Lots of work on FIM4R Identity Mangement paper version 2. DPK appointed as new chair of WISE Steering Committee. Host WISE workshop at Coseners House 26-28 Feb. Spoke on FIM at ISGC2018. DPK Attended and spoke at WLCG Collaboration Workshop Naples 26-29 March |  | STFC has recruited to replace Ian Neilson - will be in post in 2Q18. In the meantime other STFC staff (Kelsey and Cornwall) will do the important parts of the work, and spend some of the effort funds.
Vulnerabilities | Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter.Advisories were issued on the public wiki. Continue to lead GEANT SIG-ISM working group on Inventory for Security Officers.
Policy | Work continued on revised EGI/WLCG security policies in collaboration with AARC2. Chaired EGI SPG Vidyo meetings. Mainly work on the AARC2 Policy Deveopment Kit with work on new standard baseline AUP and changes required in Data Protection for GDPR. Lots of planning starting work on policy harmonisation in EOSC-hub.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q218
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Operations | Lead UK NGI security team and its fortnightly meetings. Played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. DC starts in post and hits ground running at full speed! DC co-leading WLCG SOC working group, including leading workshop at CERN on 27-29 June. All are members of WLCG AuthZ working group. DPK is leading EOSC-hub WP4 Task 4.4 Operational Security. Continue to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. 4 advisories were issued on the public wiki. Continue to lead GEANT SIG-ISM working group on Inventory for Security Officers. Co-chaired F2F EOSC-hub/EGI CSIRT in Glasgow 18-20 June and hosted by DC. DPK as new chair of WISE Steering Committee, planning for WISE at NSF Cybersecurity Summit USA in August. Attended and gave talks at EOSC-hub public event in Malaga 16-20 April. DPK chaired Security and Networking track at HEPiX (Madison 14-18 May) and spoke on IPv6 and FIM. Planning for Security Communication Challenge to happen in August 2018. |  | STFC has recruited to replace Ian Neilson. David Crooks started on 28 May 2018 but also did some security work before that (paid by Glasgow). During start of quarter, other STFC staff (Kelsey and Cornwall) did the important parts of the work.
Trust & Identity | Work continued on revised EGI/WLCG security policies in collaboration with AARC2. Chaired EGI SPG Vidyo meetings. Mainly work on the AARC2 Policy Deveopment Kit with work on new standard baseline AUP and changes required in Data Protection for GDPR. Starting work on policy harmonisation in EOSC-hub. Lots of work on FIM4R Identity Mangement paper version 2, joint with AARC2. DPK is one of chief editors. Final Draft of paper published and presented at TNC18 conference Trondheim (10-14 June). Spoke on FIM4R at Internet2 Global Summit in San Diego (7-10 May). Attended and spoke on and led policy sessions (joint with AARC2) at EUGridPMA (Karlsruhe 22-25 May).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q318
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Operations | DC leads UK NGI security team and its fortnightly meetings. All played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. DC co-leading WLCG SOC working group. All are members of WLCG AuthZ working group. DPK and DC attended CHEP2018 in Sofia (9-13 July). Talks and posters on WLCG SOC, IPv6, WISE. DPK is leading EOSC-hub WP4 Task 4.4 Operational Security. LC continues to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. 5 advisories were issued on the public wiki. DPK and DC played leading roles in WISE workshop at NSF Cybersecurity Summit USA (21-23 Aug). DC ran the security Communication Challenge in early August 2018 and reported on this at GridPP41. UK sites all did well.
Trust & Identity | Work continued on revised EGI/WLCG security policies in collaboration with AARC2. DPK chaired F2F EOSC-hub/AARC2/EGI/EUDAT/WLCG security policy meeting at CERN (18-20 July). Mainly work on the AARC2 Policy Deveopment Kit with work on new standard baseline AUP and changes required in Data Protection for GDPR. Work continues on policy harmonisation in EOSC-hub. FIM4R Identity Mangement paper version 2, joint with AARC2, finally published plus talks at UK AAI workshop (July) and GridPP41 (Aug). Attended and spoke on and led policy sessions (joint with AARC2) at EUGridPMA (Toulouse 24-26 Sep). DPK gave Trusted CI Webinar on Security for Collaborating Infrastructures on 24 Sep. Planning for FIM session at Internet2 TechEx meeting (for Oct).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q418
GridPP Quarterly Report
Area | Security
Year | 2018
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Operations | DC leads UK NGI security team and its fortnightly meetings. All played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. DC co-leading WLCG SOC working group. All are members of WLCG AuthZ working group - attended F2F meeting at CERN on 11 Dec. LC and DC attended DI4R in Lisbon (8-10 Oct). DPK is leading EOSC-hub WP4 Task 4.4 Operational Security. LC continues to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. 7 advisories were issued on the public wiki. DK attended HEPiX in Barcelona (8-12 Oct). Chaired Networking and Security track. New HEPiX AAI-SIG created. DC planning for WLCG-SOC F2F meeting in Abingdon (Feb 2019). DC/DPK wrote background paper on Security for GridPP6 proposal.
Trust & Identity | Work continued on revised EGI/WLCG security policies in collaboration with AARC2. DPK chaired F2F EOSC-hub/AARC2/EGI/EUDAT/WLCG security policy meeting in Juelich (12-15 Nov). Mainly work on the AARC2 Policy Deveopment Kit with work on new standard baseline AUP and changes required in Data Protection for GDPR. Work continues on policy harmonisation in EOSC-hub. Planning for FIM4R F2F meeting in Vienna (Feb 2019). Attended FIM sessions at Internet2 TechEx meeting Orlando (15-19 Oct) and TAGPMA meeting at end of week (19 Oct).
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q119
GridPP Quarterly Report
Area | Security
Year | 2019
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Operations | DC leads UK NGI security team and its fortnightly meetings. All played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. DC co-leading WLCG SOC working group. All are members of WLCG AuthZ working group. DPK is leading EOSC-hub WP4 Task 4.4 Operational Security. LC continues to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. LC much work on new procedures for SVG. 2 critical SVG advisories were issued. DK co-chaired an EGI CSIRT meeting in Coseners House (Feb 2019). DC hosted a WLCG-SOC workshop in Abingdon (Feb 2019). Work on GridPP6 proposal. DC and DK participated in ISGC2019 Security Workshop (March 2019).
Trust & Identity | Work continued on new/revised EGI/WLCG security policies in collaboration with AARC2. New AUP and Data Privacy Notice prepared for WLCG. DPK chaired F2F EOSC-hub/AARC2/EGI/EUDAT/WLCG security policy meeting at CERN (21-23 Jan). Much work on policy harmonisation in EOSC-hub. DK chaired FIM4R F2F meeting in Vienna (Feb 2019). Attended and spoke on FIM4R at TIIME meeting Vienna (Feb 2019). Represented WLCG at EUGridPMA meeting at CERN (Jan 2019) and attended regular monthly TAGPMA meetings.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## Narrative Q219
GridPP Quarterly Report
Area | Security
Year | 2019
Reported by | Dave Kelsey
Progress over last Quarter
Work area | Successes |  | Problems/Issues
Operations | DC leads UK NGI security team and its fortnightly meetings. All played active roles in WLCG/EGI operational security. Patching to fix critical vulnerabilities was coordinated. DC co-leading WLCG SOC working group. All are members of WLCG AuthZ working group. DPK is leading EOSC-hub WP4 Task 4.4 Operational Security. LC continues to lead EGI Software Vulnerability Group. Handled new vulnerabilities as reported during the quarter. LC continued work on new procedures for SVG. 4 SVG advisories were issued. DC led EGI Security Challenge in UK (end of March), but analysis performed during this quarter. DK co-chaired an EGI CSIRT meeting in Ljubljana (June 2019). Attended EGI Conference in Amsterdam (May). Ran a security day at UK HEP Sysman (May). Joint WISE/SIG-ISM meeting in Kaunas, Lithuania (April).
Trust & Identity | Work continued on new/revised EGI/WLCG security policies. Taking output from AARC2 project forward. New AUP and Data Privacy Notice close to final for WLCG. DPK chaired F2F EOSC-hub/AARC2/EGI/EUDAT/WLCG security policy meeting in Ljubljana (June). Represented WLCG at EUGridPMA meeting in Utrecht (May 2019) and attended regular monthly TAGPMA meetings. Spoke on WISE at Security workshop (TNC19, Tallinn, June). Spoke on FIM4R status at REFEDS just before TNC19.
Note:To get multiple lines per box use Alt-Return
General Risks
Risk |  | Mitigating Action
Insitute or area specific risks
Risk |  | Mitigating Action
Objectives and Deliverables for Last Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output
Objectives and Deliverables for Next Quarter
Objective/Deliverable |  | Due Date |  | Metric/Output

## EVAL
EVAL Notes
Publications | Date | Notes
Collaborations | Date | Notes
Further Funding (eg external grants) | Date | Notes
Destination of ex staff and recruitment issues | Date | Notes
Dissemmination events | Date | Notes
Intellectual Property | Date | Notes
Spin out companies | Date | Notes
Roles held on committees and boards | Date | Notes
Other outputs and Knowledge | Date | Notes